## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 2 - Fencing | itp |  |  |  |  | ITP 2 - Fencing
section | 1 - Existing Fencing
checkpoint | 1.1 - Removal
label | ACCEPTANCE CRITERIA: Specified fence is removed
label | FREQUENCY: Ad-hoc
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 1.2 - Segregation of Fence Timber and Wire
label | ACCEPTANCE CRITERIA: Wire is removed from removed fencing and scrapped, timber fencing is segregated from other waste
label | FREQUENCY: Post-removal
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 2 - Supply of Fencing Components
checkpoint | 2.1 - Supply of Posts
label | ACCEPTANCE CRITERIA: Posts are to be 2.7m long, 110mm small end diameter, treated to hazard class H4
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 2.2 - Supply of Strainer Posts
label | ACCEPTANCE CRITERIA: Strainer posts are to be 3m long, 175mm small end diameter, treated to hazard class H4
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 2.3 - Supply of Fencing Mesh
label | ACCEPTANCE CRITERIA: Fence mesh is to be 2.5mm diameter high tensile zinc-aluminium coated wire, 13 wires, 150mm stay wire spacing, 1.9m high (Cyclone 13/1900/150HT or similar)
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 2.4 - Supply of Fencing Staples
label | ACCEPTANCE CRITERIA: Post and strainer staples must be zinc aluminium coated, a minimum gauge of 4mm, at least 50mm long and barbed.
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 2.5 - Supply of Gates
label | ACCEPTANCE CRITERIA: Minimum height of gate to be 1.9m
label | • 2x10I gates
label | • 1x12I gate
label | • Gates are to be hot-dip galvanized
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 2.6 - Supply of Hinges
label | ACCEPTANCE CRITERIA: Hinges and gudgeons to be a minimum diameter of 20mm
label | • Hinges and gudgeons are to be hot-dip galvanized
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 4 - Fencing
checkpoint | 4.1 - Construction
label | ACCEPTANCE CRITERIA: Posts shall be at 5m centres, driven 0.7m into the ground
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 4.2 - Construction
label | ACCEPTANCE CRITERIA: Strainers are to be installed at all changes in direction of the fence and at both sides of the gate. Strainers shall also be installed on straight lines of fence so that the maximum distance between two strained posts on flat terrain is 400m.
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 4.3 - Construction
label | ACCEPTANCE CRITERIA: Must have a single strained bottom wire. The line wire must be attached to, or close to, the bottom wire of the netting with a maximum spacing between wires of 50mm.
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W