## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 4 - Environmental Management | itp |  |  |  |  | ITP 4 - Environmental Management
section | 1 - Swale Drains
checkpoint | 1.1 - Construction
label | ACCEPTANCE CRITERIA: The sides of the swale shall include a layer of 100mm of lightly compacted topsoil/ unsuitable material.
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 1.2 - Construction
label | ACCEPTANCE CRITERIA: Shall be grassed in a rye clover mix sown at the supplier’s recommended rate
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 2 - Silt Fence
checkpoint | 2.1 - Construction
label | ACCEPTANCE CRITERIA: To be installed as per drawing BESS-UZA-DS-01-65 of Specification 17.1
label | • Waratah posts at maximum 4m centres
label | • Geotextile to be minimum 200mm trenched into the ground
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection/photos
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H, Principal’s Representative
holdpoint | HOLD POINT
section | 3 - Bunds
checkpoint | 3.1 - Construction
label | ACCEPTANCE CRITERIA: The Contractor shall ensure each layer of fill is not over saturated and is free of surface water before the next layer is placed
label | FREQUENCY: Prior to commencement of each layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Reporting to Internal Project Engineer / Project Manager
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 3.2 - Construction
label | ACCEPTANCE CRITERIA: To be minimum 2m width at base
label | • To be minimum 300mm high on the uphill side or 550mm high on the downhill side
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Reporting to Internal Project Engineer / Project Manager
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 3.3 - Compaction
label | ACCEPTANCE CRITERIA: The Contractor shall place the bund fill in layers no greater than 150mm
label | • The contractor shall ensure each layer is properly compacted via track rolling before the next layer is placed
label | FREQUENCY: Per layer
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Reporting to Internal Project Engineer / Project Manager
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 4 - Decanting Earth Bund – BESS site
checkpoint | 4.1 - Supply
label | ACCEPTANCE CRITERIA: To have 150mm uPVC discharge pipe
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets, Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 4.2 - Supply
label | ACCEPTANCE CRITERIA: Spillway stabilized with BIDIM A19 geotextile
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets, Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 4.3 - Construction
label | ACCEPTANCE CRITERIA: The silt retention pond on the BESS site shall be constructed as shown on the drawing number BESS-UZA-DS-01-65 of Specification 17.1 To have a 250mm spillway
label | FREQUENCY: As constructed
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection/photos
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 5 - Borrow Site Sediment Control
checkpoint | 5.1 - Removal and Reinstatement
label | ACCEPTANCE CRITERIA: On acceptance of completion of the works on the Borrow site, all erosion and sediment control measures shall be removed and reinstated. This includes the removal of all swales, silt fencing and bunds, and removal of the sedimentation pond.
label | FREQUENCY: Post Earthworks
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 5.2 - Removal and Reinstatement
label | ACCEPTANCE CRITERIA: The land shall be re-profiled to match the surround landform, topsoiled and grassed in a rye clover mix sown at the supplier’s recommended rate, or hydroseeded and mulched.
label | FREQUENCY: Post Earthworks
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection/Photos
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W