## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 5 - Permanent Drainage | itp |  |  |  |  | ITP 5 - Permanent Drainage
section | 1 - Culverts
checkpoint | 1.1 - Supply
label | ACCEPTANCE CRITERIA: RCRRJ culverts and rings, Class 4, 300mm diameter
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 1.2 - Supply
label | ACCEPTANCE CRITERIA: RCRRJ culverts and rings, Class 4, 450mm diameter
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 1.3 - Supply
label | ACCEPTANCE CRITERIA: RCRRJ culverts and rings, Class 4, 600mm diameter
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 1.4 - Construction
label | ACCEPTANCE CRITERIA: The Contractor shall have each pipe checked for level as it is laid, by a competent technician using an approved Principals Representatives’ level, laser instrument or other approved equipment. Pipes shall be laid on uniform gradients between successive designated bends within the specified tolerances.
label | FREQUENCY: Per installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: QF 008 Check Sheet
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: H
holdpoint | HOLD POINT
checkpoint | 1.5 - Construction
label | ACCEPTANCE CRITERIA: Shall be bedded on 100mm GAP 20
label | FREQUENCY: Per installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 2 - Wingwalls
checkpoint | 2.1 - Supply
label | ACCEPTANCE CRITERIA: 300mm diameter concrete wingwall
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 2.2 - Supply
label | ACCEPTANCE CRITERIA: 450mm diameter concrete wingwall
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
checkpoint | 2.3 - Supply
label | ACCEPTANCE CRITERIA: 600mm diameter concrete wingwall
label | FREQUENCY: Per delivery
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Delivery Dockets
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 3 - Backfill
checkpoint | 3.1 - Construction
label | ACCEPTANCE CRITERIA: Outside of roadway – shall be backfilled with sand in layers no greater than 150mm
label | • Under roadway - shall be backfilled with GAP 65 in layers no greater than 150mm
label | FREQUENCY: Per installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W
section | 4 - Jointing with rubber rings
checkpoint | 4.1 - Construction
label | ACCEPTANCE CRITERIA: The Contractor must take special care during the installation of concrete pipes to ensure that cracks or chips do not occur at connection points
label | • Only sound pipes shall be laid and all pipes shall be checked immediately before placing in the trench
label | FREQUENCY: Per installation
label | CERTIFYING DOCUMENTATION, RECORD OR CHECKSHEET: Visual Inspection
label | INTERNAL VERIFICATION AUTHORITY OR RESPONSIBILITY: Internal Project Engineer / Project Manager
label | CRITICAL HOLD POINT AUTHORITY: W