## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-036
[11 empty] | Revision : 1 | Date : 23/06/23
Client: |  |  |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Kerb Access Ramp Bluestone Footpath |  | Name: Jake Cardillo |  | Name: | Aaron Hatch |  | Name: Shaun Kent
Contract No: |  |  |  | Specifications: City of Melbourne Standard Drawings and Specification: 1P 50201
|  |  |  | Structure / Component: Kerb & Kerb Access Ramp |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 23/06/23 |  | Date : 23/06/23 |  |  | Date : 23/06/23
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Activity | •Ensure that employees and sub-contractors are using the most current and complete set of drawings | Contract Drawings and Registers | Visual Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Commencing Activity | •All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP | EMP, TMP, SWMS, WP | Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Existing Bluestone Kerb Demolition |  | Each Lot | •Care shall be taken in removing existing bluestone kerb •Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone •Bluestone shall be salvaged and re-used in new kerb alignment where possible | Work Procedure | Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Check Materials |  | Prior to Commencing Activity | •Inspect delivered materials for any chips, cracks or other visible damage. | Receivable Inspection List | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.5 | Setting out |  | Each Lot | •Line and level of reinstated bluestone kerbing shall be set out according to design levels. •Line and level of bluestone pavers, tactiles and inlay shall be set out according to design levels to suit new kerb heights. | Work Procedure | Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction of Access Ramp Bluestone Footpath
2.1 | Re-levelling of bluestone kerbing and ramp |  | Each Lot | •Bluestone kerbing to be re-installed to new design levels. •Bluestone kerb shall be placed on a bed of low slump, 20 Mpa concrete of 75mm minimum thickness. | IFC Drawings CoM Bluestone Paving Specification | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.1 | Base preparation |  | Each lot | •Concrete base shall be inspected to be free of foreign materials and water pooling •After placing and vibration, the concrete shall be screeded and trowelled to the correct level. | CoM Bluestone Paving Specification | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.3 | Mortar Bed |  | Each lot | •Mortar shall be applied at average thickness of 30mm to concrete base •All pavers shall be coated in mortar slurry on rear face before laying | Dwg 1P50201 | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.5 | Cutting of Pavers |  | Each lot | •Pavers shall be cut with a diamond blade and allow a 10mm grout line at such points | Manufacturers Specifications | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.6 | Placement of bluestone pavers |  | Each lot | •Pavers shall be placed in accordance with Dwg 1P50402. •Kerb access ramp wings shall be at an angle of 45° and the ramp gradient shall not exceed 1:8. | Dwg 1P50402 Dwg 1P50201 | Visual Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
2.7 | Curing |  | Each lot | •Pavers shall have >24hrs curing time prior to light traffic •Where required, ply shall be laid over area of works | Manufacturers Specifications | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.8 | Grouting |  | Each lot | •Pavers shall be grouted using agreed colour and mixture | Manufacturers Specifications | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.9 | Installation of Versatac Granite Tactiles and Granite Inlay |  | Each Lot | •Tactiles and inlay shall be placed in accordance with Standard Drawing 1P50201. | Dwg 1P50201 | Verify | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
4 | Completion
4.1 | Completion |  | Each lot | •Pavement area is free of debris and waste •Bluestone pavement is free of mortar stains and cleaned to satisfaction | Visual Inspection | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.