## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-014 - Bluestone Kerb Installation (MCC) | itp |  |  |  |  | ITP-014 - Bluestone Kerb Installation (MCC)
section | Preliminary Works
checkpoint | 1.1 Check for Correct Documentation
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: Ensure that employees and sub-contractors are using the most current and complete set of drawings
label | REFERENCE DOCUMENTS: Contract Drawings and Registers
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.2 Implementation of all measures and controls
label | FREQUENCY: Prior to Commencing Activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP
label | REFERENCE DOCUMENTS: EMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.3 Existing Bluestone Kerb Demolition
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Care shall be taken in removing existing bluestone kerb
label | • Detailed dilapidation survey shall be conducted, noting the size and quantity of pitchers before demolition of heritage bluestone
label | • Bluestone shall be salvaged and re-used in new kerb alignment
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 1.4 Setting out
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Line and level shall be set out according to design plans
label | • Alignment of new kerb shall be marked out using string line
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
section | Construction Works
checkpoint | 2.1 Saw cut (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Saw cuts shall be made to the following depth for existing asphalt pavements:
label | – Footpath: Minimum 75mm
label | – Roadway: Minimum 125mm
label | • Excavate to allow for design heights
label | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 2.0
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.2 Concrete Placement and Setting
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bluestone kerb shall placed on a bed of low slump 20MPa concrete, minimum 75mm thickness
label | • Gaps of >10-30mm< shall be provided and filled with mortar
label | REFERENCE DOCUMENTS: CoM STD 1P 50406
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | 2.3 Mortar Mix
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Joints shall be filled with mixed grout composed of the following:
label | – 16% cement
label | – 16% stonedust
label | – 67% blended wash sand
label | – 1% lime ready mix grout
label | REFERENCE DOCUMENTS: CoM TS Sawn Bluestone cl 4 AS 3972 CoM SD 1P 50406
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
textbox | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: