## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | FM 13 - ITP - Concrete |  |  |  |  | Yes | FM 13 - ITP - Concrete | b87615e5-0fc1-49d3-89c3-4b12cef2e737
checkpoint-group | Formwork
checkpoint-status | Formwork ITP completed and sighted
checkpoint-group | Vesta Pre-pour Check
checkpoint-status | Steel has been inspected and has been installed as per the latest structural drawings. Eg. Ligatures and Bars positioned correctly
checkpoint-status | All Cast in Elements installed and to the correct locations. Eg. Threaded Couplers, and Cast in Items installed to correct spec and location, RL.
checkpoint-status | Provide adequate cover to beam, top and bottom reinforcement of slab.
label | -Measure and check cover of reinforcement against formwork is as specified
label | -Minimum cover to elements as per point 9 of the concrete notes on drawing S001 Stage C.
checkpoint-status | Ensure reinforcement has been properly tied and structure is rigid as per specifications
label | - Tie wire to be Annealed steel 1.25 mm diameter (minimum)
label | - Reinforcement Bar Correct Size
checkpoint-status | Steel surface condition free from thick rust, grease, mud etc.
checkpoint-status | Ensure reinforcement has been properly tied and the below lap lengths maintained.
checkpoint-status | Concrete pour area cleaned of steel fixers off-cuts and other steel fixers rubbish
holdpoint | SIGN OFF
checkpoint-group | Services, Builder to confirm (HOLD POINT)
checkpoint-status | Plumbing inserts etc. installed - tape ends
checkpoint-status | Electrical conduits in place - tape ends
checkpoint-status | Penetrations, setdowns and inserts installed
checkpoint-status | Voids and penetrations
checkpoint-status | Services and conduits
holdpoint | SIGN OFF
checkpoint-group | Concrete Pre-pour Inspections
checkpoint-status | Finished Concrete Level
text | RL:
checkpoint-status | Concrete Strength, Aggregate,Slump
text | Mix:
checkpoint-status | Waterproofing Additives / Waterstop
checkpoint-status | The Curing required
checkpoint-status | The Testing required
label | AS3600
checkpoint-status | The Finish required
text | Type:
checkpoint-group | Handover
checkpoint-status | Concrete dockets copied and attached
checkpoint-status | Work area is clean
checkpoint-status | Spot level checks performed
checkpoint-status | QA documents submitted to Builder
checkpoint-status | Test results to be forwarded once received
checklist-flat | FM 08 - Pre Pour Inspection - (METAL DECK KF57) p2 |  |  |  |  | Yes | FM 08 - Pre Pour Inspection - (METAL DECK KF57) p2 | ab4b8425-e8f1-44df-9c7d-dd7733d6aec5
checkpoint | Sole Boards
checkpoint | Base Plates
checkpoint | Frame spacing
checkpoint | Frame bracing
checkpoint | Frame extensions
checkpoint | Location pins (telescopic inner) Bearer size & spacing
checkpoint | Joist size & spacing Canter levering supports Prop spacing
checkpoint | Prop bracing
checkpoint | Eccentric loading
checkpoint | Prop inclination
checkpoint | Timber condition
checkpoint | Steel condition
checkpoint | Nails in plates as req'd
signoff | SIGN OFF
checklist-flat | FM 14 - Pre Pour Inspection - (prefab column tubes). |  |  |  |  | Yes | FM 14 - Pre Pour Inspection - (prefab column tubes). | f6e49165-2e1b-4ce4-af34-8576dbe3fd3f
checkpoint | 1. Manufacturer recognised quality check is clearly visible on the external of the column tube
checkpoint | 2. Tube Damage - External liner
checkpoint | 3. Tube Damage - Internal liner
checkpoint | 4. Column end tape in position,secure and free from deterioration
checkpoint | 5. Stripping tape - long section to the top & short section at the base of the column
checkpoint | 6. Stripping tape orientation facing internal of the building (where possible - subject to architectural requirement!)
checkpoint | 7. Column base support / plywood yolks in position & secure - column tube captive
checkpoint | 8. Column top support / plywood yolks in position & secure - column tube captive
checkpoint | 9. Column Uplift restraints in position & secure - Timber secure through reo cage at top of column and fix with approved anchor to formwork deck
checkpoint | 10. Column Uplift restraints in position & secure - Nails at base through the tube
checkpoint | 11. Floor surface at base of column is level & even without gaps allowing leakage
checkpoint | 12. Concrete placement rate restrictions m/hr (if any) are discussed with concrete contractor
checkpoint | 13. Concrete discharge height limitations - refer to specification / minimise where possible
signoff | SIGN OFF
checklist-flat | FM 06 - Pre Pour Inspection - (MEVA DECK) |  |  |  |  | Yes | FM 06 - Pre Pour Inspection - (MEVA DECK) | 17638346-5873-4dd6-a57a-fed4c0715217
checkpoint | Sole Boards
checkpoint | Prop spacing & capacity
checkpoint | Prop inclination
checkpoint | MD / ME prop locating pins
checkpoint | MEP Prop - SAS quick lowering system
checkpoint | MD drop heads in pos. & secure
checkpoint | MD prop heads in pos. & secure
checkpoint | Bracing bays correctly located
checkpoint | MEP brace frame - secure
checkpoint | Primary beams - secure
checkpoint | Primary beams - capacity, size, spacing
checkpoint | Secondary beams spacing
checkpoint | MD pans - condition
checkpoint | Infill strips
checkpoint | Forkheads
checkpoint | Cantilevering supports
checkpoint | MD beam stiffeners (cantilevered areas)
checkpoint | Safety chains
checkpoint | Compensation beams
checkpoint | MD assembly locks
checkpoint | Plywood condition
checkpoint | Timber condition
checkpoint | Equipment/System condition
checkpoint | Eccentric loading
signoff | SIGN OFF
checklist-flat | FM 04 - Pre Pour Inspection - (CONVENTIONAL SLABS) |  |  |  |  | Yes | FM 04 - Pre Pour Inspection - (CONVENTIONAL SLABS) | 1cb72e2b-c9e4-440d-a39a-18c3c691b576
checkpoint | Sole Boards
checkpoint | Base Plates
checkpoint | Frame spacing
checkpoint | Frame bracing
checkpoint | Frame extensions
checkpoint | Location pins (telescopic inner)
checkpoint | Bearer size & spacing
checkpoint | Joist size & spacing
checkpoint | Canter levering supports
checkpoint | Prop spacing
checkpoint | Prop bracing
checkpoint | Eccentric loading
checkpoint | Prop inclination
checkpoint | Timber condition
checkpoint | Steel condition
checkpoint | Nails in plates as req'd
checkpoint | Column framing
checkpoint | Column bracing
checkpoint | Plywood Condition
signoff | SIGN OFF
checklist-flat | FM 05 - Pre Pour Inspection - (CONVENTIONAL WALLS) |  |  |  |  | Yes | FM 05 - Pre Pour Inspection - (CONVENTIONAL WALLS) | 2207b22a-5932-4a10-83bf-61907571b115
checkpoint | LVL Whaler condition & spacing
checkpoint | LVL Soldier condition & spacing
checkpoint | Lap & lace of whaler timbers between soldiers Tie rods suitably located
checkpoint | Nuts & plates in pos. & secure
checkpoint | Stop ends suitably secured
checkpoint | Openings & voids suitably secured
checkpoint | Corners suitably secured
checkpoint | Concrete pour rate advised (Ref concrete type / notes)
checkpoint | Push pull props in pos. & secure
checkpoint | Sufficient bracing to support forms
checkpoint | Base of form suitably secured / braced Scaffold brackets correctly pos. & secure Guard rail post in pos. & secure
checkpoint | Pour platform in position and secure
checkpoint | Plywood condition
signoff | SIGN OFF
checklist-flat | FM 13 - Pre Pour Inspection - (Easy Stair) |  |  |  |  | Yes | FM 13 - Pre Pour Inspection - (Easy Stair) | 53d0d910-27f0-49be-90e5-637100f1f1dc
checkpoint | Mid Landing Prop Spacing
checkpoint | Primary Bearer Spacing
checkpoint | Secondary Bearer Spacing
checkpoint | Top Landing Prop Spacing
checkpoint | Stair throat Prop Spacing
checkpoint | Ezy stairs fixed in position
checkpoint | Handrail attached
signoff | SIGN OFF
checklist-flat | FM 07 - Pre Pour Inspection - (MEVA WALL FORMWORK) |  |  |  |  | Yes | FM 07 - Pre Pour Inspection - (MEVA WALL FORMWORK) | 984e9ac8-aabd-4667-9190-9f29ef6098e8
checkpoint | Startec panel condition
checkpoint | Alustar panel condition
checkpoint | Mammut panel condition
checkpoint | Alkus / Plywood surface condition
checkpoint | Shutter / panel configuration
checkpoint | Tie rods suitably located
checkpoint | Nuts & plates in pos. & secure
checkpoint | Assembly locks - correctly positioned
checkpoint | Uni assembly locks - correctly positioned
checkpoint | Alignment rails in pos. & secure
checkpoint | Stop ends suitably secured
checkpoint | Openings & voids suitably secured
checkpoint | Corners in pos, & secure
checkpoint | Hinged corners in pos. & secure
checkpoint | Infill strips suitably reinforced (Align. Rails!)
checkpoint | Flange screws - secure
checkpoint | Concrete pour rate advised (Ref concrete type / notes)
checkpoint | Push pull props in pos. & secure
checkpoint | Sufficient bracing to support forms
checkpoint | Scaffold brackets correctly pos. & secure
checkpoint | Guard rail post in pos. & secure
checkpoint | Pour platform in position and secure
checkpoint | Timber condition
checkpoint | Plywood condition
signoff | SIGN OFF
checklist-flat | Concrete Delivery Checklist |  |  |  |  | Yes | Concrete Delivery Checklist | 748b5392-54ee-4715-9b68-1f7c5a1a4cf0
checkpoint-status | Concrete Record
text | LOCATION OF POUR:
text | SUPPLIER:
text | OVERALL QUANTITY: |  |  | M3
text | CONCRETE STRENGTH: |  |  | Mpa
select | DELIVERED TO LOCATION BY: | PUMP-LINE,MOBILE BOOM,TOWER BOOM,KIBBLE,Other
text | DOCKET NUMBERS:
select | ON SITE TESTING REQ'D: | Yes,No
checklist-flat | F19A – PRE-POUR INSPECTION & TEST PLAN – PT |  |  |  |  | Yes | F19A – PRE-POUR INSPECTION & TEST PLAN – PT | 3ea62c39-dbd1-4d40-981f-3b0464076031
checkpoint-status | 1. Current Drawings and Revisions
text | Drawing Number
text | Revision
select | Issued For Construction | Yes,No
checkpoint-status | 2. Are the Anchorages securely fixed and anti-burst installed?
checkpoint-status | 3. Is the duct placed in the correct position and alignment, with joints sealed?
checkpoint-status | 4a. Has the strand been installed with the correct number and type?
checkpoint-status | 4b. Strand Information
checkpoint-status | Strand Type
text | 12.7mm / 15.2mm
text | Coil Number
text | 12.7mm / 15.2mm
text | Coil Number
text | 12.7mm 15.2mm
text | Coil Number
text | 12.7mm 15.2mm
checkpoint-status | 5. Are the dead ends, including anti-burst installed (onion or swage)?
checkpoint-status | 6. Are tendons profiled correctly and supporting chairs secured?
checkpoint-status | 7. Are grout hoses installed with anchorages sealed?
checkpoint-status | 8. Has the post-tensioning system been inspected and signed off by an Engineer?
checkpoint-status | PRE-POUR SIGN OFF
text | AusPT LEADING HAND
text | Date:
holdpoint | SIGN OFF
checklist-flat | F19B – POST-POUR INSPECTION & TEST PLAN – PT |  |  |  |  | Yes | F19B – POST-POUR INSPECTION & TEST PLAN – PT | 6bcb8014-4e9d-4f05-94aa-f4227cb39fa6
checkpoint-status | 1. Current Drawings and Revisions
text | Drawing Number
text | Revision
select | Issued For Construction | Yes,No
checkpoint-status | 2. Are the anchor blocks and wedges installed?
checkpoint-status | 3. Has an initial stress been carried out as per design requirements?
checkpoint-status | 4. Has AusPT sighted the concrete test report prior to commencement of full stress?
checkpoint-status | 5. Has the concrete test results reached minimum required strength as per Engineer’s requirements?
checkpoint-status | 6. Has a full stress been carried out as per the design requirements?
checkpoint-status | 7. Have the extensions been recorded and submitted?
checkpoint-status | 8. Have the extensions been approved and received?
checkpoint-status | 9. Have the tendons been cut & sealed?
checkpoint-status | 10. Have the tendons been grouted?
checklist-sectioned | Vesta Pre-pour Check |  |  |  |  | Yes | Vesta Pre-pour Check | f020b964-4a99-4772-b98d-7b692c1c45e3
checkpoint-group | Reinforcement
checkpoint-status | Steel has been inspected and has been installed as per the latest structural drawings. Eg. Ligatures and Bars positioned correctly
checkpoint-status | All Cast in Elements installed and to the correct locations. Eg. Threaded Couplers, and Cast in Items installed to correct spec and location, RL.
checkpoint-status | Provide adequate cover to beam, top and bottom reinforcement of slab.
label | -Measure and check cover of reinforcement against formwork is as specified
label | -Minimum cover to elements as per point 9 of the concrete notes on drawing S001 Stage C.
checkpoint-status | Ensure reinforcement has been properly tied and structure is rigid as per specifications
label | - Tie wire to be Annealed steel 1.25 mm diameter (minimum)
label | - Reinforcement Bar Correct Size
checkpoint-status | Steel surface condition free from thick rust, grease, mud etc.
checkpoint-status | Ensure reinforcement has been properly tied and the below lap lengths maintained.
checkpoint-status | Concrete pour area cleaned of steel fixers off-cuts and other steel fixers rubbish
signoff | SIGN OFF