## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 012 - Architectural Fittings | itp |  |  |  |  | ITP 012 - Architectural Fittings
section | 1.0 Louvres and doors
checkpoint | 1.1 Producer statement
label | Type of inspect / Test and Frequency - Producer statement/ warranty from supplier
label | Acceptance Criteria - Documentation
label | Inspection Responsibility: BCL - D
label | Verification Records of Inspection(s) / Test(s) - Producer statement
checkpoint | 1.2 Care and maintenance
label | Type of inspect / Test and Frequency - Care and maintenance manual
label | Acceptance Criteria - Documentation
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Manual
section | 2.0 Roofing
checkpoint | 2.1 Warranty
label | Type of inspect / Test and Frequency - Material Warranty and care guide
label | Acceptance Criteria - Documentation
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - I
label | Verification Records of Inspection(s) / Test(s) - Warranty documentation
checkpoint | 2.2 Producer statement
label | Type of inspect / Test and Frequency - Producer statement/ warranty from supplier
label | Acceptance Criteria - Documentation
label | Inspection Responsibility: BCL - D
label | Verification Records of Inspection(s) / Test(s) - Producer statement
section | 3.0 Drainage
checkpoint | 3.1 DWV product manual
label | Type of inspect / Test and Frequency - Product manual/technical specs
label | Acceptance Criteria - Documentation
label | Inspection Responsibility: BCL - D
label | Verification Records of Inspection(s) / Test(s) - Technical manual
section | 4.0 As built
checkpoint | 4.1 Redline Drawings
label | Type of inspect / Test and Frequency - Redline drawings of install
label | Acceptance Criteria - N/A
label | Inspection Responsibility: BCL - D
label | Verification Records of Inspection(s) / Test(s) - Redline Drawings Issued
checklist | ITP 013 - Civil Concrete Works | itp |  |  |  |  | ITP 013 - Civil Concrete Works
section | 1.0 Documentation
checkpoint | 1.1 Construction Drawings
label | Type of inspect / Test and Frequency - All drawings are for construction and latest revision.
label | Acceptance Criteria - Latest IFC Drawings
label | Inspection Responsibility: BCL - I
label | Inspection Responsibility: Client - S
label | Verification Records of Inspection(s) / Test(s) - Drawing Register, RFIs
checkpoint | 1.2 Concrete mix design
label | Type of inspect / Test and Frequency - Submitted to Beca for approval
label | Acceptance Criteria - Approved RFI
label | Inspection Responsibility: BCL - H
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - RFI
holdpoint | HOLD POINT
section | 2.0 Excavation
checkpoint | 2.1 Subgrade inspection
label | Type of inspect / Test and Frequency - Scala testing to confirm subgrade is of sufficient strength
label | ○ Witness by engineer
label | ○ Minimum of 2 tests per bund pour
label | Acceptance Criteria - Minimum of 4 blows per 100mm
label | Inspection Responsibility: BCL - H
label | Inspection Responsibility: Client - A
label | Verification Records of Inspection(s) / Test(s) - Scala Test Results
holdpoint | HOLD POINT
section | 3.0 Post Excavation
checkpoint | 3.1 >100mm compacted hard fill under bund (GAP40)
label | Type of inspect / Test and Frequency - Clegg hammer testing, 5x5 grid,
label | Acceptance Criteria - Clegg CIV>25
label | Inspection Responsibility: BCL - T
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Clegg results
section | 4.0 Concrete works
checkpoint | 4.1 Reinforcing (material)
label | Type of inspect / Test and Frequency - Review documentation for each pour
label | Acceptance Criteria - Reinforcing to be Grade 500E to ASS/NZS4671
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - W
label | Verification Records of Inspection(s) / Test(s) - Mill certificates, Detail sheet
checkpoint | 4.2 Sump Construction
label | Type of inspect / Test and Frequency - Reinforcing check, dimension check, Formwork check
label | Acceptance Criteria - As per IFC drawings
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - W
label | Verification Records of Inspection(s) / Test(s) - Concrete pour record
checkpoint | 4.3 Reinforcing install
label | Type of inspect / Test and Frequency - Measure to check cover, bar size and arrangement, lap length and type.
label | ○ Complete prior to pouring concrete
label | Acceptance Criteria - Reinforcing matches IFC drawings, any deviations recorded and acceptance agreed with engineer prior to pour
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - W
label | Verification Records of Inspection(s) / Test(s) - Concrete pour record, Photos
checkpoint | 4.4 Reinforcing install
label | Type of inspect / Test and Frequency - Starter bars for nibs
label | Acceptance Criteria - Matches IFC drawing
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - W
label | Verification Records of Inspection(s) / Test(s) - Concrete pour record, Photos
checkpoint | 4.5 Concrete pour
label | Type of inspect / Test and Frequency - Embedded items located in slab
label | – Ducting
label | – Pits
label | Acceptance Criteria - Matches IFC drawings
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - W
label | Verification Records of Inspection(s) / Test(s) - Concrete pour record, photos
checkpoint | 4.6 Concrete pour
label | Type of inspect / Test and Frequency - Level check, formwork check, cover check.
label | ○ Inspections prior to every pour
label | Acceptance Criteria - Matches IFC drawing dimensions and notes
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - W
label | Verification Records of Inspection(s) / Test(s) - Concrete pour record
checkpoint | 4.7 Pour inspection/Approval to pour
label | Type of inspect / Test and Frequency - Pre pour inspection by Beca Engineer (hold Point)
label | Acceptance Criteria - Approval from Engineer to pour
label | Inspection Responsibility: BCL - H
label | Inspection Responsibility: Client - A
holdpoint | HOLD POINT
checkpoint | 4.8 Concrete strength
label | Type of inspect / Test and Frequency - Test certificate
label | ○ 7 and 2no 28day tests required for each pour day or per 70m3
label | Acceptance Criteria - 28 day compressive strength >40mPa
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - Test certificate
section | 6.0 As-builts
checkpoint | 6.1 Redline Drawings
label | Type of inspect / Test and Frequency - Redline Civil Drawings Sets post construction
label | Acceptance Criteria - N/A
label | Inspection Responsibility: BCL - D
label | Inspection Responsibility: Client - R
label | Verification Records of Inspection(s) / Test(s) - As built drawings