## Master List Templates
Id | Type | Name | Values | Prompting Name | Resource Id
980cdcd8-9db9-56b7-a7b9-a54fae4daefa | checklist | Add - Consultant Inspection Checklist (V3) |  | Consultant Inspection - | 1a39894f-1959-48ce-a38c-c424149ab37d
e8990030-85ae-510a-9b59-3dae883ce9c0 | checkpoint | Consultant inspection completed, attached and any relevant observations closed out
7b7a025d-81fa-4409-9ef9-3281b2d64523 | textbox | Date of Inspection
dd36bd0b-3ee0-4704-912f-3f8f961a2cb6 | textbox | Type of Inspection
da74bdd5-b086-41a1-94ef-12814f41c3f5 | textbox | Area inspection relates to
e495e118-490c-453e-af9d-13b99904e2dc | tickbox | Consultant Inspection attached
0f8e78cc-ac2e-4458-b897-ef644c2cb994 | button | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed) | PASS, N/A
1f26a12b-97a7-4354-afab-298bf48ac079 | note | "PASS" once corrective closeout evidence has been attached
5b90254d-0b5f-40ab-b626-60f2f7e09379 | note | If there are no corrective action requirements select "N/A"
3d06351b-6af4-431a-909b-5a78ef041b49 | textbox | Corrective Actions (listed here if required)
808fd23b-6f12-5668-a72f-c41826505051 | signoff | Request Signoff
7117f3ef-66f3-5bc2-9756-3ff38f28cbea | checklist | Add - Council Inspection Checklist (V3) |  | Council Inspection - | 1a732614-648c-4004-b460-d06c77a7584c
46f3e0e4-fa86-577d-9b9b-6aa5b774ee2f | checkpoint | Council inspection completed, attached and any relevant observations closed out
3444c651-e5e2-4a4d-87f9-f06b48de741d | note | PASS once all information is attached including Observations/Failed comments with evidence of closeout
dc83a024-74b8-4254-9ddd-e5098acc1bd8 | textbox | Date of Inspection:
9078e12c-052d-4e8e-aaa0-bf0ee4a8e674 | textbox | Type of Inspection:
52f91732-bf1d-45c6-bd07-b9da5bc92d07 | textbox | Area inspection relates to
b4da29de-ea63-439e-a19e-c0f75d938880 | dropdown | Inspection Outcome | Pass, Fail, Partial Pass,Completed, N/A
e163160e-48f6-4a1e-925a-fc9517380516 | tickbox | Council Inspection attached
202aee45-e7db-4a11-a3cd-d58c1ed02669 | textbox | Failed Comment(s) & Required Action
3c7bfeb2-48cc-4c75-8c53-db434c64e996 | note | Select N/A if there are no Observations/Failures requiring closeout
5fc35eaa-61ff-4a6a-85df-bfb72c73a67d | button | All Relevant Observation Closeout evidence attached below if applicable (Pass once completed) | Pass, N/A
e6833de8-a856-5775-917e-a06de75d641e | signoff | Request Signoff
e537bcf6-cec5-5029-8959-e2e408303786 | checklist | Add CCC Code Compliance Certificate Checklist (V3) |  | Code Compliance Certificate - BC0 - | b01340bf-8996-47c7-813d-163150838ebe
5d33cd01-a5dd-5dff-b46b-cc044bccf973 | section | Code Compliance Certificate Lodgement
03d128d5-9f44-5ced-a1fc-ee924de0ef24 | checkpoint | Code Compliance Certificate lodgement form completed/received and attached
e1d54ab8-482b-427f-b519-9161821ddbcd | note | Attach confirmation of CCC lodgement and PASS above checkpoint when CCC has been applied for
4dbed02f-80a0-5cc8-8013-60a16cfbb214 | checkpoint-no-value | Code Compliance Certificate RFI's
ac49bbbf-c59a-45b8-be0c-a2238e2f5d08 | section-nested-checklists | Code Compliance Certificate RFI's
8fa0dabd-4bdf-512e-b218-3df6c12843a5 | section | Code Compliance Certificate Approval
e3fcee41-308e-5e2b-9f7c-87d5d213bb97 | checkpoint | Final Code Compliance Certificate (approved & attached)
815e192e-db1f-43e4-9563-62f741fbf108 | section | Code Compliance Certificate Approval
7517fd1a-bb0f-420a-b47d-74b67a3b5786 | checkpoint | Final Code Compliance Certificate (approved & attached)
339edcee-2b88-4e6d-abc0-6eb47f59ca1d | note | Attach approved Code Compliance Certificate and PASS above checkpoint when CCC has been approved
a3dd95cc-31a7-5dcf-a358-c68d5bb5ab15 | checklist | Add CCC RFI Checklist (V3) |  | RFI - | c58de946-dbb5-4dfb-9b71-454762b91047
c48a5cb8-bbbd-5cb0-ae17-7aae5547d818 | section | RFI Status
64045a5c-a57e-5823-8de0-aaad21e5289a | checkpoint | RFI Status - Pass once approved by Council
c3c60ca2-29d0-4391-a572-3d5f30a041b1 | note | Use the "RFI Management of Individual Items" folder to manage and close out the individual RFI items
6be915f4-b900-42f5-8690-eb77aaa4cab3 | note | Final "PASS" once all RFI items have been responded to/actioned and approved
9c2c1506-cf20-4bdf-973e-807e089ebba7 | textbox | Date RFI was received from Auckland Council
2164cf0e-1749-4ccd-ae2a-7fe3311404e6 | tickbox | RFI Attached
7b4124fa-1949-44ae-87c5-c39734267641 | textbox | Date Main Contractor/Builder sent response to RFI
f6d690e7-d406-4c0b-b07b-2a29d56227b9 | textbox | Date of response/approval from Council
4d67cd25-9ce8-5b8e-a3e3-ff3d484e0ee1 | section-nested-checklists | RFI Management of Individual Items
71dd6600-06f1-5035-8c62-a4067e14167d | checklist | Add CCC RFI Individual Item Checklist (V3) |  | Individual RFI - | c6210e0b-acd9-4949-911f-970573160ebc
d2b7eac0-8713-5069-9d5a-10ef5d4f75d6 | checkpoint | RFI Item Status - pass once answered/actioned
3e4ddc18-d0a7-4ad1-a02f-d6ad4683ba1b | textbox | Description of RFI Item
7c142801-2bc7-4643-9829-8403d6028ee0 | textbox | Action Required
51ac393b-9522-4cf5-bf29-8c4f224ebdfe | note | Relevant documentation / close out evidence attached
3dbac79f-8845-58fd-9d5e-dadc3d5531ef | checklist | Add Council BC Amendment Checklist (V3) |  | Council BC Amendment - | 82360c94-120f-4dd9-8ae7-cffc53ba63f7
dafa6da7-2d4d-5605-8584-a72e9c92a575 | checkpoint | Building consent amendment status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
d98f29dd-33e5-491e-a711-395516a2b7d0 | note | PASS above checkpoint when amendment is approved
13ec50bf-c00e-4072-b748-5e7184045207 | note | If amendment is a FAIL - document why below and follow appropriate corrective actions
3ac5e947-9f3e-472d-80b5-cc37078c23f1 | textbox | Date of application
6aed6b13-06af-402c-b599-1b9386a6b3a4 | textbox | Reason for application
f7aadbe4-bd83-484c-92f2-1420b81e75c8 | textbox | Date of approval / acceptance
d5b1824d-d66e-41a8-953e-7d5759affa90 | textbox | How was the amendment approved? e.g. email from council, site meeting etc
b919d047-81f4-483a-a98b-7655bddda5e9 | tickbox | Council approval of amendment attached
828274cd-74c3-4f32-baeb-614afdf4064d | textbox | Update building consent number (including amendment)
3800231c-74fa-4e51-a23b-0fdbb73d0f16 | tickbox | Latest building consent including amendment has been attached in the "Latest Building Consent" folder to superseed the previous consent
c93744fa-e3ba-44dc-903a-441321ca4ec9 | note | Ensure this amendment and respective changes are communicated to any relevant parties
ea024c39-9605-5a40-ad2f-297425d88e4c | checklist | Add Council BC Minor Variation Checklist (V3) |  | Council BC Minor Variation - | 23f538fc-821b-426d-a468-f44765e0cd22
203a050b-3039-5e0f-b885-ea9f3e0d32f9 | checkpoint | Minor variation status (PASS once approved & all information is attached including observations, correspondence & close out evidence)
39cfa62b-530c-435d-8c31-5ab24ebcb3d6 | note | PASS above checkpoint when variation is approved
c5a175be-3b1a-445a-9336-4c5e4810c3ff | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
a88179f2-77b1-4269-9f04-8c5059bb8975 | textbox | Date of application
2ddfe846-481f-4a8a-b0ae-2b214a1997f4 | textbox | Reason for application
f01f557d-4086-43f4-a7ee-16bb2a52089f | textbox | Date of approval / acceptance
ae299b30-acf7-438f-ac12-da27eef39fab | textbox | How was the minor variation approved? e.g. email from council, site meeting etc
a1fe9857-6309-49c9-8fe5-e06aaf747a30 | tickbox | Council approval of minor variation attached
f778aad6-b641-49d0-9b65-ea18fd7f65d3 | note | Ensure this minor variation and respective changes are communicated to any relevant parties
676b4296-eb6b-5b17-a35f-524912fc80d9 | checklist | Add Council BC Upload Checklist (V3) |  | Building Consent - | 84eb61bc-bf6e-4f9b-b1a8-f5c8c6ab87bd
f49061ca-344f-5e8c-a6b0-38c7e9397860 | checkpoint | Latest building consent attached (superseded and attached as required)
a9de507b-5933-4720-b76c-375bcb740674 | note | If a new building consent is issued as a result of an amendment upload here
03cb769d-c524-54da-9ab4-05c90b420268 | checklist | Add Drawings & Programme Checklist (V1) |  | Drawings & Programme | ba496c6a-d1a4-45ed-8dba-ed2acabf5615
d70018a2-e094-597d-bff2-fb621af85370 | checkpoint | Relevant Drawings Uploaded
c382a13c-0cf7-5299-8820-929638b60544 | checkpoint | Construction Programme Uploaded
a534b979-f3d6-5b0d-86b0-a4590665dd53 | checklist | QA - Backfill Checklist (V1) |  | Backfill - | 8c2ce3d1-5608-4958-b64f-f1bf64637f84
1a7871a3-b01c-54ca-b03d-93f45a419160 | checkpoint | Backfill methodology and material confirmed
1a98d6af-e728-59e7-8818-b67e6216ef16 | checkpoint | Any formwork/ debris removed from area
c18466d1-8e12-5b3a-9d1e-a693503d3ad9 | checkpoint | Any waterproofing/ drainage / service requirements completed and inspected
de35a785-cfde-572c-a584-95fb2bef8e65 | checkpoint | Approval given to commence backfill - attach any other relevant inspections and observations closeout
29cbf63a-f7e3-5e24-ba4e-19e6f1ec4ec7 | checkpoint | General photos and observations during backfill
37162b00-a2ce-51ec-a2e7-ae79f156105c | checkpoint | Backfill completed correctly and heights checked/ correct - desired compaction achieved
17bdc79c-e784-452a-99a4-fb83371c3f0c | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
06086830-9801-49e2-a664-44ca3869ec91 | tickbox | Trades QA received & attached as applicable
29d962f7-5160-56b2-8b23-b87ae5a9a2a8 | checklist | QA - Concrete Pour FOUNDATION Checklist (V1) |  | Concrete Pour - | a473598c-3f59-4454-8d35-97034f975163
0b503ac3-4407-56c6-9f14-5013369f7a3b | section | Concrete - Pre Pour
f381cd64-59e4-5bc6-a309-5654bca8806e | checkpoint | Area Accessible & Approval to start
b6a78275-ca50-56c5-9981-9f2d14bc7ad8 | checkpoint | Formwork - Correct Dimensions & Heights
673d8b70-a15c-5453-9da0-49c46a33a06f | checkpoint | Formwork cleaned, oiled and braced sufficiently
9624553a-ed7a-5ef2-9fdb-7bce7ca2c60c | checkpoint | Any/All cast in items checked / correct (location and size)
2b35d3b7-5087-5fe0-adc1-a8455339190e | checkpoint | Penetrations correctly formed/located, checked and accurate
e481600a-88eb-528f-b35a-52e8371f20ce | checkpoint | Reinforcing checked and correct
e4c2dec8-ae7c-4dfe-b825-d3428fd0612a | button | Size and type correct to specification | Yes, N/A
704b0cf7-319f-4fde-a9a9-69b6f130fe04 | tickbox | Reinforcing spacing and location correct
3d3193fa-0ccd-43bf-8af1-048f37f7b9ee | tickbox | Specified covers checked/correct
53f05949-f284-473a-8971-88ccad352568 | tickbox | Splice laps checked/correct
0e615d2a-4bb1-44b9-b269-437eb0872ec1 | tickbox | Any starter bars are installed correctly (location, size and spacing )
2ebffacc-3a83-418c-8b81-4b139d0cea0a | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
14a5c700-1d9b-5e7a-886c-b28c1fe6f398 | checkpoint | Waterproofing (checked and correct)
5694a40a-3035-59b3-928e-385a7ee5610d | checkpoint | Bottom of concrete pour is clean and free of debris/roughened
2818af65-9ae2-518e-9f0c-b9ebabd01439 | checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
f267fb4e-8763-51d1-a04f-ecc0379847d5 | signoff | Request Signoff
29208467-9eb7-5c26-a61b-e25797643cc6 | section | Concrete - Pour /Post Pour
46db1c08-8b29-5345-8f75-8d235ce048a5 | checkpoint | Concrete checked on arrival & correct (slump, MPa etc)
b6373989-333f-475a-ac74-24e2d76a699b | tickbox | All concrete dockets photographed/attached here
cf325651-49cd-5786-a717-b75fdef1cb1f | checkpoint | General photos/comments/observations during placement
b3cbc631-0f29-52c9-ba2b-032a8118effb | checkpoint | Concrete surface finish to specifications
e0c347e3-07a8-5bbe-a026-44b53bb4bae2 | checkpoint | Concrete Pour completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
d8280fe4-960c-4214-82de-2808b94d159a | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
ce508a38-d6ff-4593-a9dd-a47094abe648 | tickbox | Trades QA received & attached as applicable
a98f3ced-1d5a-5907-8575-1bd7be5b19b1 | checklist | QA - Detailed Excavation Checklist (V1) |  | Detailed Excavation - | 72d99bbb-d347-4848-b021-e2e2df5071ee
fca7fdf9-e2cf-514e-8606-04001f456c0e | checkpoint | General Photos / Comments / Observations during excavation
3b947f33-f04d-595e-ad54-c6ad809e98f2 | checkpoint | Excavation checked, correct and approved
44b11573-9a80-47ed-8f5f-4b2516b78465 | tickbox | Location accurate
7cbd784f-6f9c-482a-bee7-6cd5f508d0eb | tickbox | Depth correct (allow for site concrete if required)
240f12b5-8297-4a76-b009-d33f90b28600 | tickbox | Width correct (allow for boxing if required)
9f0fc8d0-6ff3-5613-b248-bb4a82348ddb | checkpoint | Any relevant excavation for services is completed and accurate (use underground services checklist to QA service install)
e23a42b7-4555-5780-8a28-fac17d808a60 | checkpoint | Excess Material Cleaned up and removed as required
42591e81-a83d-5485-8b9e-d8bdae180147 | checkpoint | Detailed excavation completed, reviewed and approved
b01560f3-933e-4ec0-bcf6-3ac688f2e87e | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
91a8366b-e0fb-4816-8003-4c352c94db3f | tickbox | Trades QA received & attached as applicable
4d6166a1-16f2-5a17-9bc1-278faaedb7a0 | checklist | QA - Service Location / Isolation Checklist (V1) |  | Service Location / Isolation | 7d2495e3-2d67-4d04-aa21-159c2e127030
3f204935-0fb9-5950-93bb-03535323ec17 | checkpoint | Power located
8bbe5550-ec97-5aff-94b8-8a5e42cc0f2e | signoff | Raise remedial / request trades QA / signoff
e361ce0a-7d68-5166-9306-a3dfeaf4243c | checkpoint | Water Supply located
8b0425af-9913-52bd-9e2b-89432b35c0e7 | signoff | Raise remedial / request trades QA / signoff
8c119626-9f68-5e08-a60c-6f8b81da4ac1 | checkpoint | Sewer located
02c91796-0936-527f-8445-0fc249d9e0f5 | signoff | Raise remedial / request trades QA / signoff
681edc50-45bd-590a-99fc-596aad145c5a | checkpoint | Stormwater located
f1247067-a7aa-5a69-934f-a3fbb76d765a | signoff | Raise remedial / request trades QA / signoff
f3ece9a4-54a9-5585-87b9-b158156e028a | checkpoint | Telecommunication/Fibre located
b35ad45a-abc0-596a-9aa4-159602530c66 | signoff | Raise remedial / request trades QA / signoff
c39fe1a3-c63e-52ea-9c28-b610c8faee63 | checkpoint | Any other relevant services located/ isolated
735f6636-f2aa-5ecf-8541-72e35efb4052 | signoff | Raise remedial / request trades QA / signoff
9927e914-c767-544a-bb2e-0b0fe53ecf39 | checkpoint | All Services located/ isolated (Pass once all services are located/isolated)
cad830c0-cec4-5224-9032-7db9f5f9dfd0 | signoff | Raise remedial / Request signoff
c850bdf3-689e-5bcb-a08e-88d1be9b6eec | checklist | QA - Setout / Surveying Checklist (V1) |  | Setout / Surveying - | 26b40be6-8dda-40b3-a96e-ac0979d6173f
4376658f-d638-59de-93b9-873e8c0cb437 | checkpoint | Any RL's setout are correct, labelled and photographed
c5f03814-6df4-51f8-8a39-ab3ba6eb75b5 | checkpoint | Any grid setout are correct, labelled and photographed
89c77542-40d2-539c-a5bf-1bb8ca2e6098 | checkpoint | Any other relevant setout/ survey documentation attached
cc2d4efb-9fb8-5164-aec1-0967cd40f0f3 | checkpoint | Survey work completed, checked and accurate
41567184-a1c3-509f-83f1-cbc29f28a760 | checklist | QA - Site Establishment Checklist (V1) |  | Site Establishment | 3beb5133-9a2a-430e-abcf-485d3c5c2143
ced6d878-21a9-5e31-a3bf-422da8c8b47e | checkpoint | Existing site conditions captured (pass once relevant information documented)
9b8d5d2f-7e23-5a4b-aabb-04a1bfbc1783 | checkpoint | Attach relevant site establishment photos/ documents
d956900d-c800-543e-a944-e3950f203a32 | checkpoint | Appropriate site fencing installed
cdf169fd-6c91-5719-82dd-f0cdc08bb27f | checkpoint | Site establishment completed
d8c9af44-cdfd-576d-ad8a-0614f7e6372d | signoff | Raise Remedial / Request Signoff
eef2587e-b33b-55b1-addd-91d35a77bca8 | checklist | QA - Underslab Services Install Checklist (V1) |  | Underslab Services - | fdf6d07a-ee49-48ff-aeb7-c869d5ecbc53
cc9082f9-f5a6-5763-a6a7-97a146c47778 | checkpoint | ELECTRICAL services/ conduits installed, fixed in correct location, backfilled and correct as per design
14cfb955-ff53-567f-b580-a26ed0cc50ce | checkpoint | HYDRAULIC services installed, fixed in correct location, backfilled and correct as per design
2cb6cfa1-4ce2-5041-bf65-a4a24ef2c052 | checkpoint | GAS services installed, fixed in correct location, backfilled and correct as per design
24dd5a02-935c-5329-8ff3-9a1d9517e0eb | checkpoint | MECHANICAL services installed, fixed in correct location, backfilled and correct as per design
7cbd7b70-1d4f-5d59-a784-8e8381f6b946 | checkpoint | DATA/COMMS services installed, fixed in correct location, backfilled and correct as per design
c3dda3c2-6bcb-5069-9954-3ef5c30bf668 | checkpoint | Any other services installed, fixed in correct location, backfilled and correct as per design
f13d57ed-f560-56b9-a089-8a113daca3cf | checkpoint | Underslab Services completed correctly to specification & within tolerance in respective area(s) (photographic evidence provided below)
7a46d5a6-661d-43a6-9bc4-0d745305036d | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
778fcbab-dab2-4a0c-9f65-3e7539e33f4e | tickbox | Trades QA received & attached as applicable
72f04c9a-401d-532a-b9c6-9507493454de | checklist | QA - Waterproofing Checklist (V1) |  | Waterproofing Checklist - | c888aabb-7390-4a7a-ae87-215944b99d7f
cfc738ee-f4b5-587b-9a00-fc7f29f2fe7a | checkpoint | Preparation / Substrate acceptable
799b02b1-f3c5-5cb3-b86e-e078a7dab480 | checkpoint | Correct product delivered and checked - approval given to install
6b6279bd-4dd4-56a1-93af-cd9c556f2299 | checkpoint | General photos/comments during install
cfa19140-0e58-5423-b6a4-930138e73461 | checkpoint | Any inspections / observations documented, reviewed and closed out
720d179b-c8fd-5d65-b833-9e2559cfd4e0 | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
954cb805-cfd4-46ea-94f8-c2f061ec1b97 | note | FINAL - Pass when work(s) are completed, area clean & tidy (any issues please comment below)
8d7ba9b9-a9e1-4d4b-bbb6-364cdc1d324a | tickbox | Trades QA received & attached as applicable

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | Aluminium Battened Soffit |  | Aluminium Battened Soffit | a2b28bd5-6102-4dfc-a1e1-b0e194ba1c87
| checkpoint | 50x50 aluminium box powder coated with Dulux Eternity Metro Silver Pearl Kinetic
| checkpoint | Spacing as per drawing
| checkpoint | Alignment as per drawing
| checkpoint | Batten adequately fixed and no damage
| signoff | Request Signoff
| checklist | Cast In Items |  | Cast In Items | 7951885b-c342-419b-8630-6d9e4bbee089
| checkpoint | Drawings are marked for construction, are the latest revision and are entered on drawing register
| checkpoint | All cast in items installed to correct positions
cc41aebf-a028-5557-b7a8-e10d6475795b | note | Ends sealed for in slab conduits
0031cb8c-460b-5653-9c68-4696e00d803f | note | Is the correct size
24940fc0-bf35-5042-9161-1ea565abc37d | note | Is securely fixed
211723e9-792b-57c2-a813-8462104687d3 | note | Saddled and tied in position
| checkpoint | Concrete pour has been observed to ensure cast in items have not been damaged
| checkpoint | Final as installed drawings have been drafted
| checklist | Curtain Wall Steel Post |  | Curtain Wall Steel Post | d076f3d8-4f45-4ff5-bfb0-0e4595cb0b6e
| checkpoint | Post location correct
| checkpoint | Post welding to cast in plate done properly
| checkpoint | Steel fin straight and not bent
| checkpoint | Bolts and nuts used as per detail
| checkpoint | Minimum 20mm gap at top and joint of the fin
4a8dd184-308e-58db-9ff3-e2ba1c9d07e2 | dropdown | Intumescent paint applied | Completed, Not completed, N/A
| checkpoint | Paint colour as per specification
| checkpoint | Paint undamaged
420fe702-c83e-59b5-8653-a4998d1e48c7 | tickbox | Protection around post is installed
| signoff | Request Signoff
| checklist | Curtain Wall System |  | Curtain Wall System | 4848b33c-9566-46db-8f3b-f11cf2e83c95
| section | Pre-installation. Waterproofing membrane
| checkpoint | Surface clean and free from dust, oil, grease, sealant etc..
| checkpoint | Sikalastic 152 applied before and after Sika Tape F. Continuous and 100mm up to the wall
| checkpoint | Sikaseal Tape F applied as per specification
| checkpoint | Dress at steel fin done in correct sequence
| checkpoint | Reveal shield applied with 150mm overlapping
| checkpoint | Liquiflash continuously applied and as per drawing
3cf476a5-4d96-560e-be48-05d3c4792c26 | dropdown | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section | Hanging Brackets
| checkpoint | Brackets type (aluminium/steel) used as per drawing. L0-L1 Aluminium. L2 Steel
| checkpoint | Bracket thickness and dimension as per drawing
| checkpoint | Bracket finish as per specified (powdercoated/intumicent painted/galvanized painted, etc...)
| checkpoint | Washer size and type as per specification.
| checkpoint | Bolt fixing used as per specification. Size,embedment depth, edge distance checked
8f4a609f-e8b0-588a-97b9-ab31bfdd120c | dropdown | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section | Seismic frame installation
| checkpoint | Sill frame undamaged, straight and plumb
| checkpoint | Sill frame screw fixing using Hilti HUS4 HR10x115, 75mm each side of mullion. Oversealed
| checkpoint | Drainage slot 8x50mm size, 100mm from both ends and each side of mullion
| checkpoint | End stops 100mm ht, fully sealed to structure
| checkpoint | Jamb undamaged, straight and plumb
| checkpoint | Jamb screw using M6x30 SS to steel, HUS HRS M6x70 to conc, 12G screw to timber with 450mm C/C max
| checkpoint | Corner reinforcement as per detail
| checkpoint | 20mm GAP between jamb frame and head channel
| checkpoint | Screws oversealed
| checkpoint | Head channel undamaged, straight and plumb
| checkpoint | Head channel fixed with M12 SS screws at 350 mm C/C min
| checkpoint | Screws oversealed
| checkpoint | Sikagard 52 is applied as per specification
8347358b-9aa3-5c5a-99db-2dc865b18aa1 | dropdown | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section | Sealant works
| checkpoint | Sika primer 3N/aktivator 205 is applied before sealant
| checkpoint | PEF rod correct size and in good location
| checkpoint | Gap 10mm +/-4
| checkpoint | Continuous AT Façade applied all round air seal properly tooled
328ef0cd-4fe6-542f-98c2-728a64ecf220 | dropdown | QA done ready for panel install | Pass, Fail, Partial Pass, N/A
| section | Curtain wall panel install
| checkpoint | Panel frame free from dents, dings and scratches
| checkpoint | Glass undamaged and free from scratches
| checkpoint | Gaskets and wedge in good condition
| checkpoint | Wip holes unblocked
| checkpoint | Gaps consistent to the drawings
| checkpoint | Panels aligned and plumb
| checkpoint | Angle closer installed as per drawing
| signoff | Request Signoff
| checklist | Curtain Wall Timber Framing |  | Curtain Wall Timber Framing | 89d15098-ce2c-4b55-a8e5-26872b7274f2
| checkpoint | Set out from gridline correct
| checkpoint | Dimension of wall opening correct
| checkpoint | DPM installed where required
| checkpoint | Timber frames type as per specification
| checkpoint | Frame square and plumb
f412ae3c-a205-51ca-8fd4-990163c48013 | dropdown | Council inspection done. Preline | Pass, Fail, Partial Pass, Completed, N/A
| checkpoint | Board type (RAB) as per drawing
| checkpoint | Fixing used as per specification
| checkpoint | Fixing spacing and edge distance correct
| checkpoint | Board no damage and in good condition
780342de-9ddb-509e-a5e8-3895624b67cc | dropdown | Council inspection done. Postline | Pass, Fail, Partial Pass, Completed, N/A
| signoff | Request Signoff
| checklist | Doors |  | Doors | 306a22ab-18f8-4157-a4d3-e27abfaa0b4f
| checkpoint | Door frames plumb and straight
| checkpoint | Door size and opening as per drawing
| checkpoint | Hinges, latches, knob, and other mechanical fixture in good condition
| checkpoint | Motors/door closer working properly
| checkpoint | If fire door, sealant applied as per speficied
| checkpoint | Sealant along frames correct size and thickness
| checkpoint | Correct sealant on PEF rod
| checkpoint | Door protection installed
| signoff | Request Signoff
| checklist | Facia Plate |  | Facia Plate | f45702c5-7856-48d8-88c0-4e21e33cb80d
| checkpoint | Waterproofing QA done bafore start work
| checkpoint | Plate using 6mm 5052 aluminium powder coated plate with countersunk fixing
| checkpoint | Powdercoated Dulux eternity metro silver pearl kinetic
| checkpoint | Max edge distance 100mm of fixing
| checkpoint | 10mm gap at joints with 150mm joint at seismic gap
| checkpoint | Fixing 2x 10g countersunk s/s screws with 75mm embedment at 600mm c/c spacing
| checkpoint | Plate spaced of structure with 2 50x50x6 SS washer with 6mm EPDM washer maintaining 12mm min clear gap
| checkpoint | Normal length 2.4m per sheet
| checkpoint | Facia overall depth covers all of facia structure
| checkpoint | Facia align to each other
| checkpoint | No scratches, dents or damages
| signoff | Request Signoff
| checklist | Flashing QA |  | Flashing QA | ac4dcb4c-b155-4f37-a89d-af43a9efc8f6
| checkpoint | Flashing material and color as specified
3934dd4f-c4ae-527f-9574-102dff354d4b | dropdown | Flashing Type | Sill flashing, Jamp flashing, Head flashing, Cap flashing, Soffit flashing, Other type
| checkpoint | Flashing height, depth, width as per drawing
| checkpoint | Flashing fixed with appropriate fixing type and cetre-centre spacing
| checkpoint | Flashing joints done with enough overlapping/soaker legth and as per drawing
| checkpoint | Flashing cavity or space between structure/frame as per drawing
| checkpoint | Screw oversealed if necessary
| checkpoint | Enough fall
| checkpoint | Staight and plumb
| checkpoint | Upstand height as per drawing
| checkpoint | Flashing tape applied as necessary
| checkpoint | No scartches, dents and any damages
| checkpoint | Flashing protection installed
| signoff | Request Signoff
| checklist | Flat Slab Placement |  | Flat Slab Placement | bbe48d53-d902-48a8-a399-a67483dc6821
| checkpoint | Check RL of landing place
| checkpoint | Mark out flat slab layout on site
| checkpoint | Install bearing strip
| checkpoint | Set heights for midspan
| checkpoint | Check dimensions of the panel - on delivery
62ab6a79-7faf-5d01-af19-9cc327cb7b18 | button | If applicable cut flat slab | Yes,No
| checkpoint | Place flat slab
| checkpoint | Photos and observations
| checklist | Insitu Concrete Inspection |  | Insitu Concrete for area: | cfde5b5b-cee7-4589-b1fc-824f5a87a9f5
| section | Formwork
| checkpoint | Installed as per formwork design
| checkpoint | Dimensions correct
| checkpoint | Position and orientation correct
| checkpoint | Forms vertical, plumb and true
| checkpoint | Forms coated with release agent
| checkpoint | Forms clean and clear of debris
| checkpoint | Joints sealed
| checkpoint | Pour level marks
| section | Reinforcement
| checkpoint | Starters bars included if required
| checkpoint | Refer to Brilliance Steel QA
| checkpoint | All Cast in elements checked and correct
| checkpoint | Penetrations checked and correct
| section | Construction Joints
| checkpoint | Correct location
| checkpoint | Adequately prepped
| checkpoint | Joint board installed
| section | Concrete Orderd
| checkpoint-no-value | Details
7127c40a-69b5-5c10-bd86-34f1389db71b | textbox | Mix Type
5e7fb3c2-b9db-5d94-a7e0-08a917ada65c | textbox | Volume
| section | Post Pour
| checkpoint | General photos/comments/observations
| checklist | James Hardie Easylap Cladding at L1 Terrace Canopy Area |  | James Hardie Easylap Cladding at L1 Terrace Canopy Area | e4d95f95-25b9-455a-9f60-78f5901fdf0e
| checkpoint | Timber framing using 90x45 SG8 with 600 C/C spacing
| checkpoint | Wall Therman Insulation R2.9 140mm Greenstuff thermal blanket fitted into wall
| checkpoint | Council inspection done. Preline
| checkpoint | RAB exposed cut edge to be primed
| checkpoint | 2-4mm gap in between joints
| checkpoint | Nail with 12mm edge distance and 200mm c/c minimum spacing
| checkpoint | Nail flush with board surface
| checkpoint | RAB free of dust, oil, grease, etc
| checkpoint | Steel plate dressed properly with aluminium saddle flashing with continuous sealant to plate
| checkpoint | Council inspection done. Postline
| checkpoint | Revealshield done as per specification
| checkpoint | Curtain wall head flashing installed in good condition
| checkpoint | JH PVC vent strip installed at the bottom with 600mm c/c max
| checkpoint | Cavity batten fixed at 600 c/c apart with 250mm c/c nail fixing to the structure
| checkpoint | Easylap edges is sealed
| checkpoint | 11 FC sealant is applied at the cavity batten before the Easylap panel is installed
| checkpoint | Panel is fixed with SS fixing at 150mm C/C flush to the face
| checkpoint | Painted as per specification
| checklist | Lift Glass |  | Lift Glass | 1e829b73-eb91-4199-bce2-34223e2e98b5
| checkpoint | Steel structure painted and handed over prior to start of work
| checkpoint | Spider fixing type as per specified (metroglass)
| checkpoint | Spider fixing installed as per drawing
| checkpoint | Spider fixing in good condition without damage to all parts
| checkpoint | 18mm single structural glass installed as per drawing layout (metroglass)
| checkpoint | Glass is 50mm offset to steel structure and 15 glass gap at the bottom of L0 and 10mm elsewere
| checkpoint | Glass logo visible
| checkpoint | Clear sealant on gap
| checkpoint | Spider centre at 120-130 edge distance to glass edge
| checkpoint | Conduit penetration in the correct location
| checkpoint | Glass free from scratch, chips or any damages
| checkpoint | Glass protection installed
| signoff | Request Signoff
| checklist | Nuraply Waterproofing Membrane at Green Roof |  | Nuraply Waterproofing Membrane at Green Roof | 9188e00f-4709-47e1-af42-ff93fda119f5
| checkpoint | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint | Nuralite bitumen LM fillet at internal corners
| checkpoint | 5mm fillet radius at external corners
| checkpoint | Worker is approved applicator to do the job
| checkpoint | Nuralite Nuraflux primer installed continuously to cover whole area
| checkpoint | Nuraply 3PB-SA installed continuously without any damage
| checkpoint | Nuraply 3PB membrane installed continuously without any damage installed in accordance to specification
| checkpoint | Nuralite aluminium tape to separate sealant and membrane
| checkpoint | Nuraply base sheet reinforcing strip on primer installed at precast joint
| checkpoint | Termination bar mechanically fixed as per manufacturers manual
| checkpoint | No visible cracks, holes, damages into the membrane
| checkpoint | Joint overlapping fully welded
| checkpoint | Double thickness application at all internal and external corner
| checkpoint | Pipe penetration done with ring clamp
| checkpoint | All penetration done properly
| signoff | Request Signoff
| checklist | Nuraply Waterproofing Membrane at Terrace to Warehouse Roof |  | Nuraply Waterproofing Membrane at Terrace to Warehouse Roof | 4b20bfcd-999a-4318-a8ce-000ced158916
| section | Nuraply Waterproofing Membrane at Terrace to Warehouse Roof
| checkpoint | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint | Worker is approved applicator to do the job
| checkpoint | Nuralite Nuraply 3PM double layer torch on system installed continuously
| checkpoint | No visible cracks, holes, damages into the membrane
| checkpoint | Joint overlapping fully welded
| checkpoint | Nuraglaze sealer is applied to portion of roof as shown in the architectural drawing
| checkpoint | Sheets fully adhered to plywood
| checkpoint | Double thickness application at all internal and external corner
| checkpoint | Pipe penetration done with ring clamp
| section | At Seismic Joint
| checkpoint | 5mm powder coated aluminium scupper rebated to ply at seismic gap fix to 1 end only
| checkpoint | Nuradeck bandage flashing with 50mm overlap to 3PM at scupper
| checkpoint | Membrane dressed over seismic end cap at 70mm min
| signoff | Request Signoff
| checklist | Nuwall Soffit Lining |  | Nuwall Soffit Lining | 994dd3b9-5a2a-4f61-9313-7ec18bdcf5b6
| checkpoint | Timber framing using 90x45 SG8 with 600 C/C spacing
3ddaba91-86aa-507c-b0da-30666b62f0e1 | dropdown | Council inspection done. Preline | Pass, Fail, Partial Pass, Completed, N/A
| checkpoint | RAB exposed cut edge to be primed
| checkpoint | 2-4mm gap in between joints
| checkpoint | Nail with 12mm edge distance and 200mm c/c minimum spacing
| checkpoint | Nail flush with board surface
| checkpoint | RAB Joints and corner sealed with 75mm wide tape
| checkpoint | RAB free of dust, oil, grease, etc
5a8d3f2c-156c-54db-a994-11fef4a26ff8 | dropdown | Council inspection done. Postline | Pass, Fail, Partial Pass, Completed, N/A
| checkpoint | Flashings needed installed before batten if required
| checkpoint | 20mm H3.2 castellated cavity batten at 600 c/c spacing. Castellation againts RAB
| checkpoint | Castellated cavity batten fixed to timber frame with 40x12mm SS flat head nail 800 c/c
| checkpoint | Nuwall type and colour as specified. Mono 200 with Dulux eternity metro silver pearl kinetic
| checkpoint | Orientation as per drawing
| checkpoint | 10g SS fixing screw with 30mm min embedment to timber structure
| checkpoint | Isolator strip to underside of all castellated soffit battens by Nuwall
| checkpoint | End Cap installed at all edges p.c. to match soffit
| checkpoint | Soffit Lining free from scratches, dents and damages.
| signoff | Request Signoff
| checklist | Office Roof |  | Office Roof | 49c10cd9-f6e4-4cde-bc18-fd784518e370
| section | Underlays
| checkpoint | Covertek 403 separation layer to purlin structure and cavity battens
| checkpoint | 20mm H3.2 castellated cavity battens installed before plywood
| checkpoint | Nog support timber framing at C purlin level at 600x600 spacing
| checkpoint | 17mm thick H3.2 waterborne CCA treated plywood fixed with 10x50 countersunk screw head
| checkpoint | Plywood used is non LOSP (light organic solvent preservative) or copper nitrate treated
| checkpoint | Screw 150mm c/c at edge and 200mm c/c at body of sheets
| checkpoint | Internal corners with 25mm fillet, external corners with 5mm radius.
| checkpoint | Timber plinth SG8 H3.2 100x50 timber layout as per drawing
| checkpoint | Timber plinth screw head countersunk Hex 14G M10x150 tek fixed at 600mm c/c
| checkpoint | Timber plinth with 45 degree timber fillet at corners
| checkpoint | 90mm Ht Timber diverter installed
| checkpoint | Conduit penetration to roof, location checked as per drawing
| checkpoint | Enough fall to drain
| checkpoint | Gutter and sump area done as per drawing
| checkpoint | No sharp object and all nail head flush to the plywood face
d76fc444-2170-527d-857c-7519a16a9b22 | dropdown | All checked and ready to proceed to next stage | Pass, Fail, Partial Pass, N/A
| section | Roof Membrane
| checkpoint | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint | Worker is approved applicator to do the job
| checkpoint | Nuralite Nuraply 3PM double layer torch on system installed continuously
| checkpoint | No visible cracks, holes, damages into the membrane
| checkpoint | Joint overlapping fully welded
| checkpoint | Nuraglaze sealer is applied to portion of roof as shown in the architectural drawing
| checkpoint | Sheets fully adhered to plywood
| checkpoint | Double thickness application at all internal and external corner
| checkpoint | Conduit penetration done with ring clamp
| checkpoint | All penetration done properly
| signoff | Request Signoff
| checklist | Panel Sealant |  | Panel Sealant | 7b0969cd-2ac3-4cf7-a6a6-90e99faeff01
| checkpoint | Cut and remove existing sealant
| checkpoint | Clean all sealant residue and dirt/dust
| checkpoint | Insert correct size backing (tight fit) rod to correct depth
| checkpoint | Surface clean and dry - ready for application
| checkpoint | Correct depth achieved prior to sealant
| checkpoint | Apply specified sealant primer
| checkpoint | Correct Sealant Applied as per manufacturers instructions
| checkpoint | Sealant properly tooled
| checkpoint | No visible voids, flaws or defect.
| checkpoint | Double seal required from exterior - refer architect's detail
| checkpoint | Double seal installed as per architect's direction (clearly mark double sealed area on elevation)
| checkpoint | Ensure that drain slots are created the lowest point of panel 10mm dia
| checklist | Punch Windows |  | Punch Windows | 0b69beba-6ef1-4623-ba49-598cff1bfb68
| checkpoint | Precast concrete surface no damage
| checkpoint | Precast concrete face free from oil, grease, dirt etc
| checkpoint | Gap 10mm +/-4 between structure and frame
| checkpoint | Frame endstops and corners properly sealed
| checkpoint | Appropriate PEF rod installed continuously
| checkpoint | Sikalastic 152 applied on the opening all round
| checkpoint | Sikaseal Tape F applied as per specification all round
| checkpoint | Fixing HUS4-HR6x70mm @ 350 ctrs. Min 55 embedment
| checkpoint | Fixing oversealed
| checkpoint | HDPE packers installed the right way
| checkpoint | Continues sealant on backing rod properly tooled
| checkpoint | Wip holes cleared and unobstructed
| checkpoint | Wedge and gasket properly mounted
| checkpoint | Glass and frame free of scratches
| checkpoint | Angle closer size correct and offset 6mm from frame
| checkpoint | Window protection installed
| signoff | Request Signoff
| checklist | QA - Concrete Pour (Slabs) |  | Concrete Pour for Area: | 518abdd0-5b55-4662-8c42-477156e7097e
| section | Concrete - Pre Pour
| checkpoint | Set-out correct
| checkpoint | Any/All cast in items checked / correct (location and size)
| checkpoint | Penetrations correctly formed/located, checked and accurate
| checkpoint | Reinforcing checked and correct
4dc878d9-304e-536a-bfc9-1152c453f1dd | button | Size and type correct to specification | Yes, N/A
2394572d-10c5-51c8-b44e-11842d036890 | tickbox | Reinforcing spacing and location correct
63b623d2-cd36-5864-a2c1-065815ca50ee | tickbox | Specified covers checked/correct
a5a3e83a-6e14-5766-94b5-a46868affe87 | tickbox | Splice laps checked/correct
3de42f6b-b5cc-51fa-81c1-eec7aa1c962d | tickbox | Any starter bars are installed correctly (location, size and spacing )
243d6ce0-2160-5538-9532-742903b48e59 | tickbox | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
| checkpoint | Waterproofing (checked and correct)
| checkpoint | Bottom of concrete pour is clean and free of debris/roughened
| checkpoint | Engineer informed of pour checks completed (see consultant folder and ensure observations are closed out)
| signoff | Request Signoff
| section | Concrete - Pour /Post Pour
| checkpoint | General photos/comments/observations
f5024dcb-51b2-5ff4-841c-413ac416afa6 | tickbox | All concrete dockets photographed/attached here
5eb53f38-6e22-5ca8-8b5e-c7a803fa8336 | tickbox | Trades QA received & attached as applicable
| checklist | QA - Drainage |  | QA - Drainage | 46189d8f-c80a-41d4-be65-03143914c93c
| checkpoint | Council inspection records
| checkpoint | General Photos
| checkpoint | Bassett CONQA link/attached
| checklist | QA - Gib Install |  | QA - Gib Install | 20be0197-1d7f-45ac-9c55-2bd814788fbc
| section | Details
| checkpoint | Check nogging around peno's (Fire walls)
| checkpoint | Check wall types (Fire, STC or normal rating)
| checkpoint | Check screw type, length, centres and gaps between gib
| checkpoint | Sealants, fire stopping
de525eee-cc6f-51ff-90a3-91038dca80fe | note | QA complete ready for Inspection
bbd71b7c-65ac-5968-81b8-b6f79cbfd942 | tickbox | Trades QA received & attached as applicable
| checklist | QA - Internal Framing |  | Internal Framing Checklist | 08a1eb8d-79ea-4ab0-993f-684221d05607
| section | Details
| checkpoint | Follow Grid Lines when setting out
| checkpoint | Check wall types from drawings
| checkpoint | Check all fixing type (Fire wall) match wall type
| checkpoint | Nog centres, Fixing centres, Deflection heads
| checkpoint | Plumb, straight
f6e898aa-777d-51bd-8e75-165bef0412d7 | note | QA complete ready for Inspection
1dcd7007-6dd6-5547-ae30-dc2ec1a5d09f | tickbox | Trades QA received & attached as applicable
| checklist | QA - Internal Plumbing |  | QA - Internal Plumbing | d9cfa967-5725-40f0-a7c8-cf7d9ec78178
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
| checkpoint | All setouts (walls and floor)
| checkpoint | Correct material used (Copper/Pex)
| checkpoint | Wing backs secured/pipes silicon for vibration/insulation
| checkpoint | Pressure test water and stacks holding and flushed of debris
8a344ece-147a-594d-a735-c8dec2b7afde | note | QA complete ready for Inspection
2737d573-e923-5e82-ba18-4a7bdce8c58d | tickbox | Trades QA received & attached as applicable
| checklist | QA - Painting |  | QA - Painting | f4907ea2-c799-40db-820c-1b2a5e87434c
| section | Details
| checkpoint | Check surface is clean, ready for seal coat
| checkpoint | Light check by Plasterers and hand over
| checkpoint | Painter light check on plasterer
| checkpoint | Final coats
9fc422bd-2e9e-5d0b-865a-51087cad15b2 | note | QA complete ready for Paint
| checklist | QA - Passive Fire |  | QA - Passive Fire | a354e922-2770-47eb-b7c9-445d34a9065e
| section | Details
| checkpoint | Review Fire report
| checkpoint | Passive fire specification
| checkpoint | Wall Types/Gib Manual
| checkpoint | Check sealant type/fire stopping/fixing of gib/collars/Fire dampers
| checkpoint | Check all penetrations and seal
7968335d-8857-5b98-bcfc-1968fab2e4a2 | note | QA complete ready for Inspection
8fcbffdf-4d23-528e-af92-ecd8b596b1bc | tickbox | Trades QA received & attached as applicable
| checklist | QA - Piling |  | QA - Piling | 2201e1f7-b7e9-495c-a440-8088b52fa508
| section | Prepour
| checkpoint | Pile diameter
d07b8dab-206d-5921-a3f5-275207599823 | textbox | Pile diameter
| checkpoint | Engineer Inspection reinforcing
| checkpoint | Geotech inspection
| checkpoint | Council inspection
| checkpoint | CLL QA received
| checkpoint | Any Issues with Pile
409b3ddd-32e8-5b53-8e15-a74f47a38569 | textbox | Any issues/ collapse?
459d666f-42f1-53e3-8e02-1476a2c064bb | textbox | Weather conditions
| section | Post pour
| checkpoint | Concrete poured to the correct height
a0456b24-1b48-4914-8ca0-12b6176fc593 | textbox | Date of Concrete Pour:
| checkpoint | Sand filled to clay height
| checkpoint | Cage centre of the hole
| checkpoint | No bars damaged
| checkpoint | Concrete cleaned from reinforcing
| checklist | QA - Piling Completion_Handover Checks |  | QA - Piling Completion/Handover Checks | 3bea8de2-aadb-475b-8d06-10e6fbb6e6b7
| checkpoint | Trades QA completed, received & reviewed
| checkpoint | General progress photos recorded
| checkpoint | All piles completed (locations and heights checked and correct within tolerance)
| signoff | Request signoff
| checklist | QA - Precast Walls |  | Precast for Area: | 173d5682-9e59-4b52-9e9c-d7294fcecf3c
| section | Pre installation
| checkpoint | Precast elements inspected, correct and damage free before placement
| checkpoint | All pre installation work completed
6279d689-eeea-5047-8125-f68bf6632e06 | tickbox | Site set-out completed
| signoff | Request Signoff
| section | Installation
| checkpoint | Alignment and levels of the panel checked/correct
| checkpoint | Panel propping checked
| checkpoint | Drypacking / grouting complete
| checkpoint | Any additional photos, comments and observations
| checkpoint | Panel installation completed within tolerance in respective area
e2594693-2ab9-5714-b7ae-0051cc7b56ec | tickbox | Trades QA received, reviewed, attached and approved
| signoff | Request Signoff
| checklist | QA - Structural Steel |  | Structural Steel for Area: | 3bb5e337-d000-4817-8aec-c4ff0e18ab05
| section | Pre installation
| checkpoint | Structural steel items checked
bca0ce93-507b-5f41-9ea4-9fb262643b58 | tickbox | Type/Size Checked
6603a5d4-47c2-5281-8dce-ecc448006cde | tickbox | Finishing checked (ie. Painted, Galvanised, etc)
| checkpoint | Cast in/anchor bolts and plates installed
| checkpoint | All pre installation work completed
| signoff | Request Signoff
| section | Installation
| checkpoint | Alignment and levels checked/correct
| checkpoint | All dry packing completed
| checkpoint | Any additional photos, comments and observations
| checkpoint | Structural steel work completed within tolerance in respective area
4c22c5cb-4c52-5160-acda-257757d2c746 | tickbox | Trades QA received, reviewed, attached and approved
| signoff | Request Signoff
| checklist | Roof Skylight |  | Roof Skylight | 0caee07f-1e24-4b92-8e66-1ce8935c1409
| checkpoint | Waterproofing QA done before start
| checkpoint | Slop of the nib to create 7 degree to glass skylight
| checkpoint | Powder coated aluminium flashing installed at the edge of the nib
| checkpoint | Under-flashing/Framing sealed to the roof membrane with Soudal Gorilla sealant on backing rod. Min 6mm gap
| checkpoint | Under-flashing/Framing powder coated with Duratek eternity range: Gun metallic kinetic matt
| checkpoint | Cover flashing fixed with 2x6mm EPDM compressed washers to form 6mm gap at fixing.
| checkpoint | Fixing as per specification
| checkpoint | Glass type in accordance to the specification
| checkpoint | Glass clean, and free from scratch, chips or any damage
| signoff | Request Signoff
| checklist | Seismic Gap DM Series with Vapour Barrier |  | Seismic Gap DM Series with Vapour Barrier | d7329d22-c474-49d6-bcc0-3bdc85856fc5
| checkpoint | Concrete haunching done on the floor slab with slop to outside slab
| checkpoint | Vapour barrier fixed from top to bottom without damage
| checkpoint | DMS framing fixed to concrete wall straight and plumb and in good condition
| checkpoint | Conc-conc joint +/- 150mm
| checkpoint | Frame-frame gap +/- 127mm centred to the concrete gap fix with screw at 450mm c/c, 150mm start and end
| checkpoint | Center plate/ cover plate surface finish as per specification (PC Dulux Gunmetal Kinetic Matt)
| checkpoint | Center plate/ cover plate resting firmly against the gasket of the framing
| checkpoint | Center plate screw tight and secured to centering bar: Cover against the concrete structure
| signoff | Request Signoff
| checklist | Seismic Gap IBS Series |  | Seismic Gap IBS Series | 1754d090-ed25-421f-8460-0a67646b2164
| checkpoint | Joint is clean, uniform gap 100mm, dry and undamaged
| checkpoint | Silicon adhesive is applied both sides
| checkpoint | Correct type of precompressed sealant used. (IBS 100) check depth and width
| checkpoint | Precompressed sealant run through without gap and enough offset to avoid clashes to DM Series framing
| checkpoint | Joint cut square/mitered, no gap and applied with silicon adhesive
| checkpoint | Sealant applied continuously and tooled properly
| signoff | Request Signoff
| checklist | Sika 740W Spray on Paint |  | Sika 740W Spray on Paint | a25c556a-8b93-4009-b643-5eba1b43f100
| checkpoint | Surface free of dust, oil, efflorescence and paint coatings
| checkpoint | Damage of concrete if any, have been patched
f64073cd-1c33-59cf-8447-dbb854de7119 | dropdown | Consultant/Client Inspection | Pass, Fail, Partial Pass, N/A
| checkpoint | Surface is dry and no damp patches
| checkpoint | Windows and curtain wall installed and well protected especially along the sealant area
| checkpoint | 2-3 coats applied wet-wet bottom-up without letting the product run into the surface
| checkpoint | Area is protected from rain for at least 6 hours
| signoff | Request Signoff
| checklist | Site Wide QA - Drainage |  | Drainage for Area: | 566e9290-d8c7-46d9-9094-4aa576ab84d4
| section | Manhole
| checkpoint | Diameter confirmed
| checkpoint | IL confirmed
| checkpoint | Base haunched
| checkpoint | Lid plastered
| checkpoint | Ladder condition acceptable
| section | Drainage line
| checkpoint | Upstream RL confirmed
| checkpoint | Downstream RL confirm
| checkpoint | Fall acceptable
| checkpoint | Pipe diameter correct
| checkpoint | Pipe material correct
| checkpoint | Connections complete
| checkpoint | Fines placed
| checklist | Staircase Glass Balustrade |  | Staircase Glass Balustrade | d76fe13c-069e-40d7-85f8-5e673a2ded0c
| checkpoint | 125x100x75 10tk Bottom plate rebated into precast concrete
| checkpoint | 50x25mm metal post balustade plumb and straight
| checkpoint | 50mm metal handrail installed at 900mm ht
| checkpoint | Spider fixing secured and no damage
| checkpoint | 10mm balustrade glass installed as per layout and with 1100mm ht
| checkpoint | Handrail and glass gap at 50mm
| checkpoint | Glass free from scratch, chips or any damages
| checkpoint | Glass protection installed
| signoff | Request Signoff
| checklist | Steel Frame Balustrade with Mesh Infill |  | Steel Frame Balustrade with Mesh Infill | 41eadf9b-6238-4629-9c55-9e325f5a528a
| checkpoint | Balustrade using 50x25x3mm HD galv powder coated steel
| checkpoint | Balustrade spacing as per specification
| checkpoint | SS mesh as per specified
| checkpoint | Height correct
| checkpoint | Fixing done in accordance to drawing
| checkpoint | Balustrade straight and plumb
| signoff | Request Signoff
| checklist | Terrace Canopy |  | Terrace Canopy | 7736b53f-b9db-4604-a09c-512c83ece6b1
| section | Stainless Steel Gutter at L1 Canopy
| checkpoint | Steel structure is painted and handed over before start work
| checkpoint | SS gutter weld continues and without hole, dent or crack
| checkpoint | SS gutter and sump fall about 1:100
| checkpoint | SS bracket at 600 C/C. Fixed to cladding with neoprene compressed washer with 12mm gap to cladding
| checkpoint | Diverter flashing over terrace column installed as per drawing
| section | Glazed Roof
| checkpoint | Spider fixing installed per shop drawing and without damage
| checkpoint | Glass using 21.52 toughened laminated safety glass with 115 clearance at structure
| checkpoint | Glass with anti-reflective frit as per drawing
| checkpoint | Glass overhung about 200mm from the spider fixing
| checkpoint | Glass edge as per drawing
| checkpoint | Joint sealant done with the correct type and properly tooled
| checkpoint | Drip angle installed at the the lower edge
| section | Aluminium Battened Soffit
| checkpoint | 50x50 aluminium box powder coated with Dulux Eternity Metro Silver Pearl Kinetic
| checkpoint | Spacing as per drawing
| checkpoint | Alignment as per drawing
| checkpoint | Batten adequately fixed and no damage
| signoff | Request Signoff
| checklist | Terrace Glass Balustrade |  | Terrace Glass Balustrade | 5b181474-7c17-43ed-baf7-08c6c18ebf4f
| checkpoint | Concrete nib straight with no damage
| checkpoint | Hilti HIT-HY200 + HIT V-R M10 Grade 316 SS anchor fixing @ 200 c/c and 160 embedment
| checkpoint | 1st Anchor placed at 120mm from edge of the concrete
| checkpoint | Continuous solid aluminium packer installed before between con structure and glass bottom support
| checkpoint | 2mm Powdercoated capping to concrete nib done as per drawing
| checkpoint | Base powder coating dulux eternity metro silver pearl kinetic
| checkpoint | Glass using 21.52mm safety sentry glass by Metroglass
| checkpoint | Glass ht 1100-1150mm to the top of the nib
| checkpoint | Glass is straigth and plumb
| checkpoint | Glass protection installed
| signoff | Request Signoff
| checklist | Terrace Tiled Flooring |  | Terrace Tiled Flooring | b9f96958-926d-435d-81f9-1c495e5d4ae7
| section | Nuraply waterproofing membrane
| checkpoint | All surface is clean, dry, free from sharp edges, oil, grease or other materials that my affect adhesion
| checkpoint | Surface screed slop to drain as per drawing
| checkpoint | Worker is approved applicator to do the job
| checkpoint | Nuralite Nuraply 3PM double layer torch on system installed continuously
| checkpoint | No visible cracks, holes, damages into the membrane
| checkpoint | Joint overlapping fully welded
| checkpoint | Sheets fully adhered to surface
| checkpoint | Double thickness application at all internal and external corner
| checkpoint | Pipe penetration done with ring clamp
| checkpoint | Termination bar mechanically fixed as per manufacturers manual
| section | Tiled Flooring
| checkpoint | Nurajack start T installed as per manufacturers manual
| checkpoint | Nurajck levellers installed as per manufacturers manual
| checkpoint | Nurapoxy tg applied at raised concrete when necessary
| checkpoint | Outdure Qwickbuild aluminium support frame system installed on top of nurajack
| checkpoint | Selected R11 non-slip 302x604x20 think porcelain tile installed, level and without damage
| signoff | Request Signoff
| checklist | Villaboard Soffit Lining |  | Villaboard Soffit Lining | 9746d6d6-570f-4002-aae8-1516b77aa700
| checkpoint | Correct timber framing installed with 600 c/c stud spacing and max 1200 frame
| checkpoint | Correct type of fixing used and not overdriving
| checkpoint | Correct spacing for fixings. 70mm at corners, 200mm C/C at edge, 300mm C/C at internal studs, 12mm edge distance
| checkpoint | Sheets rebated at joints with 1-2mm gap each joint
| checkpoint | Minimum 6mm gap to soffit edge structure
| checkpoint | Inseal tape along the edge
| checkpoint | All site cut and recessed must to sealed as specified
| checkpoint | Perforated paper tape applied at joint rebate as necessary during plaster
| checkpoint | Control joints if specified, has been done as per specification
| checkpoint | Edge of the soffit straight
| checkpoint | Paint done properly with correct colour as specified
| signoff | Request Signoff
| checklist | Warehouse Roof |  | Warehouse Roof | 9c833457-32b0-47bd-94dc-32e9e3e5c9c4
| section | Metal Roofing
| checkpoint | Metal roof type and colour as per specification. ST963 Gull Grey both sides
| checkpoint | Galvanized fixing screw neoprene washer with epdm seals rip fixed
| checkpoint | Metal roof free from scratches, dents and holes
| checkpoint | Fixings not over or underdriven to roof sheet and with enough embedment to structure
| checkpoint | Thermakraft Thermabar 397 FRR roofing underlay installed without damange
| checkpoint | Thermakraft Ausmesh mesh installed as per specification fixed at 600 c/c
| checkpoint | Sika expansion tape 600 installed at the top of precast
| checkpoint | Colorsteel eaves flashing installed as per drawing fixed at 600
| checkpoint | Vermin flashing insalled hard up the the gap
| checkpoint | Apron flashing as per detail and sufficient amount of fixing. Screws oversealed and birdproof. 200mm width
| checkpoint | Apron flashing minimum upstand 110mm. Continues sealed and with compressible foam seal
| checkpoint | Secondary apron flashing with continuous compressible foam and seal
| checkpoint | Secondary apron flashing fixing at 600mm c/c oversealed
| section | Roof penetration
| checkpoint | Conduit penetration to roof with Dektite EPDM boot in diamond layout
| checkpoint | Dektite screwed and sealed properly as per manufactorers detail
| section | Gutter and downpipe
| checkpoint | Gutter straight and with enough slop towards downpipe
| checkpoint | Gutter secure, undamaged and free from any debris
| checkpoint | Downpipe location as per drawing
| checkpoint | Downpipe free from dents, leaks and damages
| checkpoint | Downpipe plumb with clips and fixing spacing as per specification
| signoff | Request Signoff