## Sheet1
Homi Train Station - Inspection and Test Plan
Project Area |  | Homai Train Station |  |  |  | Rev | 5 |  | Inspection and Test Codes:
Activity Title |  | Piling Works |  |  |  | Date | 2024-10-25 |  | [R] Review | Review of reports, records or other evidence of compliance.
Location | [5 empty] | Lot No. |  |  | [I] Inspection | In process check, work proceeds. Record the check if required.
Ref # |  | DN1212-ITP-002 | [6 empty] | [W] Witness | Inspection to be witnessed on site and recorded. Record to be filed.
DNZ Project Manager: |  | Dan Trotman | [6 empty] | [H] Hold | No work to proceed past Hold Point until this is completed, recorded and released
AT Project Manager: |  | Mike Robertson
DNZ Project Engineer: |  | Grant Wallace
Drawings/Reference Documents: |  | Proposed Access Ramp General Notes: 3235599-SP03-ST-3001-1 Proposed Access Ramp General Notes Reinforcing Concrete: 3235599-SP03-ST-3002-1, 3235599-SP03-ST-3003-1 Proposed Access Ramp General Notes Structural Steel Work: 3235599-SP03-ST-3004-1 Proposed Access Ramp General Arrangement Plan and Elevation: 3235599-SP03-ST-3100-1 Proposed Access Ramp Setout: 3235599-SP03-ST-3150-1 Proposed Access Pile Reinforcement Details: 3235599-SP03-ST-3151-1
Specifications: |  | NZS3910:2013 746-24-874-AC 746-22-052-PS NZS3112 - SESOC/ NZGS Construction Specification Bored and Driven Piles June 2022 NZS 3104:2021 Specification for Concrete Production
ITP Item # | Construction Activity or Material Element |  | Standard, Drawing or Specification Reference | Construction Activity Description, Test Type and Acceptance Criteria |  | Test Frequency |  | QA Record | Verification Method and On Site Responsibilities |  |  | DNZ Rep Sign and Date
[9 empty] | DNZ Engineer | Engineer's Rep | Designer Rep
1 | PRELIMINARY AND GENERAL
1.1 | IFC Drawings and Specification |  | ACC | A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction Works done in accordance with Project specification |  | Once |  | N/A | R |  | H | #VALUE! | 2024-10-24
1.2 | Method Statement & JSEA Development |  | The Downer Standards (TDS) | Prior to construction: document review. |  | Once |  | Method Statement & JSEA Completed & signed by relevant authority | H | R | R | #VALUE! | 2024-10-24
1.3 | Permit to Dig |  | DN-ZH-ST043 Ground Disturbance SP03-ST-3150 | Prior to construction, all services shall be located ahead of construction. Permit in the work package. |  | Permit issued each week |  | Permit number ....................... | H |  |  | #VALUE! | 2024-10-24
1.4 | Survey Model |  | N/A | Model Review. |  | Once |  | Visual Inspection & measurement Survey Check set out as per design | H |  |  | #VALUE! | 2024-10-24
1.5 | Lift Plan |  | DG-ZH-ST047 Cranes and Lifting Equipment Standard | Prior to construction. For lifting of casing, reinforcing cages, tremmie pipes etc shall be in place ahead of construction, a Complex lift plan for the Crane and lift card for lifting with Excavators. Lift plan included in the work package. |  | Prior to Construction when required |  | Permit number …................ | H |  |  | #VALUE! | 2024-10-24
1.6 | Hot Works |  | DG-ZH-ST041 Hot Work Standard | Prior to construction,for welding, gas cutting, grinding etc a Hot work permit shall be in place ahead of construction. Permit in the work package.. |  | Prior to Construction when required |  | Permit number …................ | H |  |  | #VALUE! | 2024-10-24
1.7 | Working at Heights |  | DG-ZH-ST042 Working at Heights Standard | Prior to construction, permit in work package. |  | Prior to Construction when required |  | Permit number …................ | H |  |  | #VALUE! | 2024-10-24
1.8 | Permit to Pump Concrete |  | NZ Concrete Contractors Association | Prior to construction, permit in work package. |  | Prior to Construction when required |  | Permit number …................ | H |  |  | #VALUE! | 2024-10-27
1.9 | Permit to Enter (Rail Corridor) |  | DG-ZH-ST010-NZ Working in the Rail Corridor | Prior to construction, permit in work package. |  | Prior to Construction when required |  | Permit number …................ | H |  |  | #VALUE! | 2024-10-26
2 | MATERIAL APPROVALS
2.1 | Concrete Mix Design |  | 746-24-874-AC Table 4 C0601.4.4 C0610.2 | 40 Mpa, 11mm Aggregate size. Self Compacting. Target Slump 550mm ±50mm |  | Once |  | Approved Mix InEight Reference ................. | R |  | H | #VALUE! | 2024-10-25
2.2 | Steel Casing |  | 3235599-SP03-ST-3150-1 Note 4.0 | Details of the proposed casings shall be submitted to the Engineer for review and approval. 1219 OD permanent steel casing grade API 5L X52, thickness 16mm. |  | Each Casing |  | Mill Certifcates QA Report | R |  | H | #VALUE! | 2024-10-24
2.3 | Reinforcing Steel |  | AS/NZS 4671 746-24-874-AC C0600.17 | Grade 500E MA Reid Bars to Column Starter Cage Reid Bars for hanging pile cage Sonic Tubes for CSL Shop drawing and shop drawing check form to be provided to the Engineer for review. |  | Each Cage |  | Shop Drawing Approval Pile Cage inspection | R |  | H | #VALUE! | 2024-10-24
3 | Construction Activities
3.1 | Pile Set-Out |  | 3235599-SP03-ST-3150-1 | Before commencing pile drilling operations, survey set out pile position based on model. Set out to include; pile centre, height and offset. |  | Each Pile |  | As-Built | W |  |  | #VALUE! | 2024-10-26
3.2 | Pile Casing Installation |  | 3235599-SP03-ST-3150-1 | Pile casing to be installed into a shallow pre drilled hole. Pile casing to be as per submitted methodology and correspondence. Pile casing verticality to be checked using a spirit level. |  | Each Pile |  | As-Built | I |  |  | #VALUE! | 2024-10-26
3.3 | Welding of pile cages |  | C0602.5.6 C0602.5.7 | All welding of reinforcement shall be carried out in accordance with AS/NZS 1554.3. The welding procedure shall be made available to the Engineer upon request. All welds shall be category SP in accordance with AS/NZS 1554.3 100% visual examination by independent welding inspector. |  | As required |  | Welder Qualification Weld Procudure NDE Report | R |  | H | Sign | Date
3.4 | Pile Auger / Excavation |  | 3235599-SP03-ST-3150-1 Note 3.9 | Depth to be checked and recorded after auger/excavation. Diameter of pile shall not be less than the specified diameter. ±75mm positional tolerance, Max 1:75 (H:V) verticality tolerance. |  | Each Pile |  | Survey Checks Pile Card Photos | I |  | W | #VALUE! | 2024-10-27
3.5 | Geotechnical Engineer Pile Inspection |  | 3235599-SP03-ST-3150-1 Note 2.3, 3.2, 3.8 C0500 A3.0.5 | Geotechnical Engineer to confirm top of rock during the pile boring operation. And to inspect the material at the base and side of the rock socket complies with the design requirements (Bearing) at least equal to or greater than that nominated on the drawings. The pile card shall be signed by the inspecting Engineer confirming inspection has taken place and the founding stratum meets the relevant design requirements. Tolerance on Top of Rock level variance of ±2m from anticipated level is acceptable. |  | Each Pile |  | MSQ SVR Pile Card | I |  | H | #VALUE! | 2024-10-26
3.6 | Geotechnical Engineer Pile Toe Inspection |  | C0500 A6.0.2 Table 2 | Geotechnical Engineer to inspection base cleanliness prior to reinforcing cage placement. |  | Each Pile |  | MSQ SVR Pile Card | I |  | H | #VALUE! | 2024-10-27
3.7 | Structural Engineer Reinforcing Cage Inspection |  | C0700 | Structural Engineer to inspect the reinforcing cages that it comply with the design requirements. |  | Each Cage |  | MSQA SVR | I |  | H | #VALUE! | 2024-10-24
3.8 | Pile Reinforcing Installation |  | 3235599-SP03-ST-3151-1 Note 2.4 & 2.7, 3.3 746-24-874-AC C0601.8 | Once the Geotechnical Engineer has accepted the founding conditions, and the Structural Engineer has inspected the reinforcing cage, placement of the cage shall occur as soon as possible. Minimum concrete cover 75mm at any location. Tolerance on Spiral Spacing +10mm for 150mm Spiral. |  | Each Pile |  | Survey Checks before and after pour. As-Built Pile Card | I |  | W | #VALUE! | 2024-10-27
3.9 | Steel Tube Installation |  | 3235599-SP03-ST-3151-1 Note 1.7 | 4 x 40mm ID Integrity testing steel tube shall be installed at equal distance around the inside of the reinforcing cage for the full length of the pile. |  | Each Pile |  | Photos Structural Eng. Inspection As-Built Pile Card | H |  | W | #VALUE! | 2024-10-27
3.1 | Pre-Pour Inspection |  | 3235599-SP03-ST-3150-1 Consent Inspection Schedule | 2 Days notice to the Design Engineer. Pre-Pour inspection to be completed by DNZ Engineer, Auckland Council Inspector and Design Engineer. |  | Each Pile |  | MSQA SVR Pile Card Building Consent Booklet | I |  | H | #VALUE! | 2024-10-24
3.11 | Pile Concrete Pour |  | 746-24-874-AC C0601.4.6 C0601.10.4 3235599-SP03-ST-3151-1 Note 3.6 | 40Mpa Concrete. 3 Specimens tested 1 x 7 Days & 2 x 28 Days. Spead test shall be completed on each sample taken from the chute. Column and pile cage to be suspended for a minimum of 8 hours after placement of concrete. Pile concrete is to be over-poured. |  | Each Pile |  | Concrete Dockets Compressive Test Results Slump Test Results Photos | I |  | H | #VALUE! | 2024-10-27
3.12 | Pile Surface Finish / Construction Joint |  | 746-24-874-AC C0602.6 3235599-SP03-ST-3151-1 Note 3.6 NZS 3109 | Over-Poured concrete shall be removed carefully without damaging the reinforcing cage to form a Type B Construction Joint at the top of pile. |  | Each Pile |  | Photos | I |  | W | Sign | Date
3.13 | Post-Pour Inspection Cross Hole Sonic Loggging |  | 746-24-874-AC C0500.2 A5.0 | Testing to be undertaken at 8 days Preliminary results shall be submitted to the Engineer within 1 day of completion of the test results. The Final results and findings shall be submitted to the Engineer within 3 days of completion to the test. Once the Engineer has reviewed the results of the tested piles, and are satisfactory the tubes shall be grouted with a 40Mpa Cementitious grout. |  | Once |  | Test Reports | H |  | R | Sign | Date
4 | FINAL RECORDS
4.1 | Survey Records |  | N/A | Ensure all items have been surveyed and records are assembled for asbuilting |  | Once |  | As-Built | H |  | R | Sign | Date
4.2 | Redline Drawings |  | IFC Drawings | Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen. |  | Once |  | IFC Mark-Up | H |  | R
4.3 | Defect, Snag and Punch List |  | DN1212-DOW-PLA-PM-0005 QMP | Update the project Defect, Snag and Punch List Register |  | If required |  | Snag Register | H |  | R | Sign | Date
4.4 | Non-conformances |  | DN1212-DOW-PLA-PM-0005 QMP | Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report. NCR Reference ….................. |  | When Required |  | NCR Forms on InEight | H |  | R | Sign | Date
Comments:
ITP APPROVAL PROCESS
Prepared By: Quality Engineer |  |  | Nas Matar |  | Signed: |  | Date:
Reviewed By: Project Manager |  |  | Dan Trotman |  | Signed: |  | Date:
Reviewed By: QA Manager |  |  | Cordelia Gridler-Brown |  | Signed: |  | Date:
Reviewed By: Design Engineer |  |  | TBC |  | Signed: |  | Date:
Reviewed By: AT Project Manager |  |  | Mike Robertson |  | Signed: |  | Date:
FINAL ITP CLOSE-OUT
Downer Project/Site Engineer |  |  |  |  | Signed: |  | Date:
QA Mgr./Engineer |  |  |  |  | Signed: |  | Date:
Designers Rep(Assistant) |  |  |  |  | Signed: |  | Date:
Note on A52: Kelsey Wong: ITP Revision to be signed and approved the Project Lead prior to construction. Final version issued to Quality Engineer / Engineer's Rep for Comment and Acceptance of ITP.