## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-002 Pilling | itp |  |  |  |  | DN1212-ITP-002 Pilling Rev5
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with Project specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Method Statement & JSEA Development
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
label | Test Frequency - Once
label | QA Record - Method Statement & JSEA Completed & signed by relevant authority
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Permit to Dig
label | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance SP03-ST-3150
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, all services shall be located ahead of construction.
label | ○ Permit in the work package.
label | Test Frequency - Permit issued each week
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Model
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
label | Test Frequency - Once
label | QA Record - Visual Inspection & measurement Survey Check set out as per design
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Lift Plan
label | Standard, Drawing or Specification Reference - DG-ZH-ST047 Cranes and Lifting Equipment Standard
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. For lifting of casing, reinforcing cages, tremmie pipes etc shall be in place ahead of construction, a Complex lift plan for the Crane and lift card for lifting with Excavators.
label | ○ Lift plan included in the work package.
label | Test Frequency - Prior to Construction when required
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Hot Works
label | Standard, Drawing or Specification Reference - DG-ZH-ST041 Hot Work Standard
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction,for welding, gas cutting, grinding etc a Hot work permit shall be in place ahead of construction.
label | ○ Permit in the work package.
label | Test Frequency - Prior to Construction when required
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.7 - Working at Heights
label | Standard, Drawing or Specification Reference - DG-ZH-ST042 Working at Heights Standard
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
label | Test Frequency - Prior to Construction when required
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.8 - Permit to Pump Concrete
label | Standard, Drawing or Specification Reference - NZ Concrete Contractors Association
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
label | Test Frequency - Prior to Construction when required
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.9 - Permit to Enter (Rail Corridor)
label | Standard, Drawing or Specification Reference - DG-ZH-ST010-NZ Working in the Rail Corridor
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction, permit in work package.
label | Test Frequency - Prior to Construction when required
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Concrete Mix Design
label | Standard, Drawing or Specification Reference - 746-24-874-AC Table 4 C0601.4.4, C0610.2
label | Construction Activity Description, Test Type and Acceptance Criteria - 40 Mpa, 11mm Aggregate size. Self Compacting.
label | ○ Target Slump 550mm ±50mm
label | Test Frequency - Once
label | QA Record - Approved Mix
textbox | InEight Reference
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Steel Casing
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 4.0
label | Construction Activity Description, Test Type and Acceptance Criteria - Details of the proposed casings shall be submitted to the Engineer for review and approval.
label | ○ 1219 OD permanent steel casing grade API 5L X52, thickness 16mm.
label | Test Frequency - Each Casing
label | QA Record - Mill Certifcates, QA Report
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Reinforcing Steel
label | Standard, Drawing or Specification Reference - AS/NZS 4671, 746-24-874-AC C0600.17
label | Construction Activity Description, Test Type and Acceptance Criteria - Grade 500E MA
label | ○ Reid Bars to Column Starter Cage
label | ○ Reid Bars for hanging pile cage
label | ○ Sonic Tubes for CSL
label | ○ Shop drawing and shop drawing check form to be provided to the Engineer for review.
label | Test Frequency - Each Cage
label | QA Record - Shop Drawing Approval, Pile Cage inspection
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Construction Activities
checkpoint | 3.1 - Pile Set-Out
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1
label | Construction Activity Description, Test Type and Acceptance Criteria - Before commencing pile drilling operations, survey set out pile position based on model. Set out to include; pile centre, height and offset.
label | Test Frequency - Each Pile
label | QA Record - As-Built
label | DNZ Engineer - W
checkpoint | 3.2 - Pile Casing Installation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1
label | Construction Activity Description, Test Type and Acceptance Criteria - Pile casing to be installed into a shallow pre drilled hole. Pile casing to be as per submitted methodology and correspondence. Pile casing verticality to be checked using a spirit level.
label | Test Frequency - Each Pile
label | QA Record - As-Built
label | DNZ Engineer - I
checkpoint | 3.3 - Welding of pile cages
label | Standard, Drawing or Specification Reference - C0602.5.6, C0602.5.7
label | Construction Activity Description, Test Type and Acceptance Criteria - All welding of reinforcement shall be carried out in accordance with AS/NZS 1554.3.
label | ○ The welding procedure shall be made available to the Engineer upon request.
label | ○ All welds shall be category SP in accordance with AS/NZS 1554.3
label | ○ 100% visual examination by independent welding inspector.
label | Test Frequency - As required
label | QA Record - Welder Qualification, Weld Procudure, NDE Report
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Pile Auger / Excavation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 3.9
label | Construction Activity Description, Test Type and Acceptance Criteria - Depth to be checked and recorded after auger/excavation.
label | ○ Diameter of pile shall not be less than the specified diameter.
label | ○ ±75mm positional tolerance, Max 1:75 (H:V) verticality tolerance.
label | Test Frequency - Each Pile
label | QA Record - Survey Checks, Pile Card, Photos
label | DNZ Engineer - I
label | Designer Rep - W
checkpoint | 3.5 - Geotechnical Engineer Pile Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Note 2.3, 3.2, 3.8, C0500 A3.0.5
label | Construction Activity Description, Test Type and Acceptance Criteria - Geotechnical Engineer to confirm top of rock during the pile boring operation. And to inspect the material at the base and side of the rock socket complies with the design requirements (Bearing) at least equal to or greater than that nominated on the drawings.
label | ○ The pile card shall be signed by the inspecting Engineer confirming inspection has taken place and the founding stratum meets the relevant design requirements.
label | ○ Tolerance on Top of Rock level variance of ±2m from anticipated level is acceptable.
label | Test Frequency - Each Pile
label | QA Record - MSQ SVR Pile Card
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.6 - Geotechnical Engineer Pile Toe Inspection
label | Standard, Drawing or Specification Reference - C0500 A6.0.2 Table 2
label | Construction Activity Description, Test Type and Acceptance Criteria - Geotechnical Engineer to inspection base cleanliness prior to reinforcing cage placement.
label | Test Frequency - Each Pile
label | QA Record - MSQ SVR Pile Card
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.7 - Structural Engineer Reinforcing Cage Inspection
label | Standard, Drawing or Specification Reference - C0700
label | Construction Activity Description, Test Type and Acceptance Criteria - Structural Engineer to inspect the reinforcing cages that it comply with the design requirements.
label | Test Frequency - Each Cage
label | QA Record - MSQA SVR
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.8 - Pile Reinforcing Installation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3151-1 Note 2.4 & 2.7, 3.3, 746-24-874-AC C0601.8
label | Construction Activity Description, Test Type and Acceptance Criteria - Once the Geotechnical Engineer has accepted the founding conditions, and the Structural Engineer has inspected the reinforcing cage, placement of the cage shall occur as soon as possible.
label | ○ Minimum concrete cover 75mm at any location.
label | ○ Tolerance on Spiral Spacing +10mm for 150mm Spiral.
label | Test Frequency - Each Pile
label | QA Record - Survey Checks before and after pour. As-Built, Pile Card
label | DNZ Engineer - I
label | Designer Rep - W
checkpoint | 3.9 - Steel Tube Installation
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3151-1 Note 1.7
label | Construction Activity Description, Test Type and Acceptance Criteria - 4 x 40mm ID Integrity testing steel tube shall be installed at equal distance around the inside of the reinforcing cage for the full length of the pile.
label | Test Frequency - Each Pile
label | QA Record - Photos, Structural Eng. Inspection, As-Built, Pile Card
label | DNZ Engineer - H
label | Designer Rep - W
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - Pre-Pour Inspection
label | Standard, Drawing or Specification Reference - 3235599-SP03-ST-3150-1 Consent Inspection Schedule
label | Construction Activity Description, Test Type and Acceptance Criteria - 2 Days notice to the Design Engineer. Pre-Pour inspection to be completed by DNZ Engineer, Auckland Council Inspector and Design Engineer.
label | Test Frequency - Each Pile
label | QA Record - MSQA SVR, Pile Card, Building Consent Booklet
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.11 - Pile Concrete Pour
label | Standard, Drawing or Specification Reference - 746-24-874-AC C0601.4.6, C0601.10.4, 3235599-SP03-ST-3151-1 Note 3.6
label | Construction Activity Description, Test Type and Acceptance Criteria - 40Mpa Concrete.
label | ○ 3 Specimens tested 1 x 7 Days & 2 x 28 Days.
label | ○ Spead test shall be completed on each sample taken from the chute.
label | ○ Column and pile cage to be suspended for a minimum of 8 hours after placement of concrete.
label | ○ Pile concrete is to be over-poured.
label | Test Frequency - Each Pile
label | QA Record - Concrete Dockets, Compressive Test Results, Slump Test Results, Photos
label | DNZ Engineer - I
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.12 - Pile Surface Finish / Construction Joint
label | Standard, Drawing or Specification Reference - 746-24-874-AC C0602.6, 3235599-SP03-ST-3151-1 Note 3.6 NZS 3109
label | Construction Activity Description, Test Type and Acceptance Criteria - Over-Poured concrete shall be removed carefully without damaging the reinforcing cage to form a Type B Construction Joint at the top of pile.
label | Test Frequency - Each Pile
label | QA Record - Photos
label | DNZ Engineer - I
label | Designer Rep - W
checkpoint | 3.13 - Post-Pour Inspection Cross Hole Sonic Loggging
label | Standard, Drawing or Specification Reference - 746-24-874-AC C0500.2 A5.0
label | Construction Activity Description, Test Type and Acceptance Criteria - Testing to be undertaken at 8 days
label | ○ Preliminary results shall be submitted to the Engineer within 1 day of completion of the test results. The Final results and findings shall be submitted to the Engineer within 3 days of completion to the test. Once the Engineer has reviewed the results of the tested piles, and are satisfactory the tubes shall be grouted with a 40Mpa Cementitious grout.
label | Test Frequency - Once
label | QA Record - Test Reports
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | 4 - FINAL RECORDS
checkpoint | 4.1 - Survey Records
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed and records are assembled for asbuilting
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Redline Drawings
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Test Frequency - Once
label | QA Record - IFC Mark-Up
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Defect, Snag and Punch List
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Update the project Defect, Snag and Punch List Register
label | Test Frequency - If required
label | QA Record - Snag Register
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - When Required
label | QA Record - NCR Forms on InEight
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Quality Engineer - Nas Matar
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed By: QA Manager - Cordelia Gridler-Brown
label | Reviewed By: Design Engineer - TBC
label | Reviewed By: AT Project Manager - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature