## 026 MATV Cabling
MATV Cabling
Nominate Equipment or Works associated with this ITC | [14 empty] | Page 1 of 1
ITP No : |  | 001 |  | ITP Item No: |  | 3.22 |  | Job No: |  |  | Area:
Dwg No:
Function | [12 empty] | OK | NA | NCR raised
No | Confirm following items comply with requirements | [13 empty] | Major | Minor
1 | Check that cable to be installed matches Job Spec Requirement ie. Brand and Class
2 | Check that all cable pathways comply with ACA and Vendor requirements.
3 | Install cables, making sure of all strain and bend radius requirements, label cables correctly.
4 | Bundle sizes to be checked to Specification and number of cables not exceeded.
5 | Cables to be tied in with Cable Ties as per specified distance between ties.
6 | All Clearances between power and other services to be maintained as per requirements.
7 | Corro to be extended to outlet position if segregation is required from power in same cavity.
8 | Install Components (splitters, Taps Amps etc) onto Backboards as per design.
9 | Install all cable links and Terminators as required to backboard components
10 | Install Back boards in riser or designated position.
11 | Loom cables neatlt to back board, make sure that the cables are loomed to the correct component.
12 | Terminate cables in Riser or nominated backboard location.
13 | Check position of outlets on Architectural plans if available.
14 | Terminate cables in the field as per regulations and Vendor requirements
15 | Label all field outlets correctly
16 | Set up Head End as per Design and terminate cables.
17 | Check Signal with aerial and meter on roof to determine the best location for mounting.
18 | Install aerials in the designated location and connect cables.
19 | Test all outlets to the relevant standards and Vendor requirements.
20 | Supply test results and Asbuilt plans to Office.
Comments
Minor NCR's raised |  |  |  |  | YES | NO | N/A |  | Have all NCR's been finalised ?
[9 empty] | YES |  |  | NO |  |  | N/A
Major NCR's raised |  |  |  |  | YES | NO | N/A
Accepted By |  |  | Name (Print) |  |  | Signature |  |  |  | Position |  |  | Date
Q Electrical
PM Review
Client (If Applicable)