## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | RR-SEPD-BESS-FIC-004-01 - Proof roll | itp |  |  |  |  | RR-SEPD-BESS-FIC-004-01 - Proof roll
section | Part 1 – Proof roll (photos where applicable)
checkpoint | 1.1 - Smooth Drum Roller – 12t
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-006
checkpoint | 1.2 - Plate compactor – 0.75t
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-006
checkpoint | 1.3 - Single pass with smooth drum roller to cover the area for the proof roll. If any doubts remain after a single pass, any subsequent passes, yet no greater than four, further compaction works shall be carried out till SEPD supervisor and PE are satisfied that there are no visual subgrade defects.
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-006
checkpoint | 1.4 - The speed of the pass shall be constant and sufficient and no greater than walking speed.
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-006
checkpoint | 1.5 - No proof rolling to be conducted within 2m of footings, foundations or retaining walls. Subject to a visual assessment and the principal’s approval, any compaction within this proximity of civil infrastructure shall be only achieved using hand compaction methods.
label | Specifications/Drawings Reference - WBS-SS-CI-SPC-006
section | Part 2 – Comments
checkpoint-no-status | Comments:
section | Document Sign-off
checkpoint | Prepared by:
textbox | SEPD (Engineer) - Name:
date | SEPD (Engineer) - Date:
holdpoint | Add Signature
checklist | RR-SEPD-BESS-ITP-001-01 - Earthworks | itp |  |  |  |  | RR-SEPD-BESS-ITP-001-01 - Earthworks
section | Section 1: Preliminaries & Permits
checkpoint | 1.1 - Collect and verify information (Site boundary, utilities, survey map, design drawings)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Results included in work pack
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 1.2 - Permit approval (GDA/GDP)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Approved excavation permit (GDP) prior to commencing works
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - RR-SEPD-CI-SOW-002-01
holdpoint | HOLD POINT
checkpoint | 1.3 - Site set-out
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Verify levels, site boundaries, and physical bounds per IFC drawings
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 1.4 - Sediment control plan
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-PM-PLN-0024, WAE230103-03-003 TM Rev0
label | Conformance Criteria Summary - Sediment control measures in place
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - SEPD environment-al plan
checkpoint | 1.5 - Dust control plan
label | Responsibility - SE/PE
label | Specification Reference - PP3 section 1.5 and section 4.1
label | Conformance Criteria Summary - Dust control measures in place
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - NA
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - SEPD environment-al plan
section | Section 2: Materials
checkpoint | 2.1 - Import fill material inspection
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Material certificate and test report for particle size distribution, moisture content, MMDD
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Material certificates
checkpoint | 2.2 - Verify suitable foundation material (compaction >95% MMDD)
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Geotechnical test results showing compliance
label | Method - R
label | Frequency - PW
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Test results
holdpoint | HOLD POINT
section | Section 3: Earthworks
checkpoint | 3.1 - Excavation to subgrade – verify lines, depth and dimensions
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Compliance with design drawings and subgrade preparation
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - IFC Drawings
checkpoint | 3.2 - Stockpiling of excavated material – manage and segregate by type
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-0006
label | Conformance Criteria Summary - Material stockpiled appropriately, no cross contamination
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - SEPD environment-al plan
checkpoint | 3.3 - Subgrade proof roll
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Subgrade meets stability requirements
label | ○ Subgrade proof roll shall be inspected by the Principal
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - WBS-SS-CI-ITP-910049
holdpoint | HOLD POINT
checkpoint | 3.4 - Backfill under slabs and compaction of lifts
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-0006
label | Conformance Criteria Summary - Backfill material compacted in layers to required thickness
label | Method - I
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - WBS-SS-CI-ITP-920049
checkpoint | 3.5 - Compaction density ratio for backfill
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Compaction test report showing >95% MMDD
label | ○ WBS-SS-CI-ITP-920049
label | Method - T
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - HP
label | Hold/Witness Point Requirements: SEPD - HP
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - Test results
holdpoint | HOLD POINT
checkpoint | 3.6 - As-built survey pick-up
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006 PPR
label | Conformance Criteria Summary - Survey records and as-built drawings
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - As-built drawings
section | Section 4: Final Inspection
checkpoint | 4.1 - Finish level compliance with design drawings
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - As-built drawings
label | Method - S
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - WBS-SS-CI-ITP-920049
checkpoint | 4.2 - Final Inspection Checklist (FIC) completion
label | Responsibility - SE/PE
label | Specification Reference - WBS-SS-CI-SPC-0006
label | Conformance Criteria Summary - Signed FIC
label | Method - R
label | Frequency - PL
label | Hold/Witness Point Requirements: ROBAR - V
label | Hold/Witness Point Requirements: SEPD - V
label | Hold/Witness Point Requirements: Client - NA
label | Records or Checklist Document Number - WBS-SS-CI-ITP-920049
section | Document Sign-off
checkpoint | Close-out
textbox | SEPD - Name:
textbox | SEPD - Position:
date | SEPD - Date:
holdpoint | Add Signature