## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | 66833050-fec8-4492-b959-2917a48a84d6 |  | checklist | QA - Second fix |  |  |  |  | Yes | QA - Second fix | 1743c71c-4963-4635-be73-089ee14bd670
checkpoint-group | d38766d6-e161-4537-a142-2e16ea8ae752 |  | section | Power Outlets
checkpoint-status | 763300c0-7242-4501-8135-03d214557b0d |  | checkpoint | Correct type installed
checkpoint-status | d7a240a8-82ca-41ce-aeb8-a7b753b783af |  | checkpoint | Correctly installed with terminations all secured properly
checkpoint-status | a35f1da9-e28e-4577-b0fc-4a8a5441b5c8 |  | checkpoint | Outlet Installed level
checkpoint-status | 1df1b4f8-ad24-4460-9f3c-ed71d6e012cf |  | checkpoint | Circuit Tested and results recorded
checkpoint-status | 970e3d9d-8771-4ad7-96c7-c17c80c66599 |  | checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
checkpoint-group | 4198c9bf-d687-410f-bc02-8be51ce82f58 |  | section | Light Switches
checkpoint-status | 0eb9b68f-6444-48f7-bf69-2e323360fef8 |  | checkpoint | Correct type installed
checkpoint-status | 0966b762-8c87-490e-872e-83b13951b6b6 |  | checkpoint | Correctly installed with terminations all secured properly
checkpoint-status | 60523051-3ab0-45d0-9c47-7d54b2fec347 |  | checkpoint | Light switch Installed level
checkpoint-status | 4d0593c3-ad59-41e9-82b9-e3c5f8713226 |  | checkpoint | Circuit Tested and results recorded
checkpoint-status | e65b9fad-7a7a-440d-b830-f4bfb9d35176 |  | checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
checkpoint-group | e4823999-280a-431c-bd0a-588651eb292f |  | section | Light Fixtures
checkpoint-status | a34ae0da-eb29-4345-89f9-0d527d247fe3 |  | checkpoint | Correct type installed
checkpoint-status | 09a7c17f-89a2-4708-990e-485aba8b6f57 |  | checkpoint | Correctly installed with terminations all secured properly
checkpoint-status | d57d55f5-b275-445d-9446-2dd36efd54f3 |  | checkpoint | Tested for operation
checkpoint-status | df17f7a5-efae-4836-b25d-454791dfd626 |  | checkpoint | Correctly installed with stainless screws & 90 / 45 angle
checkpoint-group | d7c808d7-e513-4d51-ae24-8913aca682f5 |  | section | Photos
checklist-sectioned | 691d9bdd-bb3c-4ecb-851e-03c7cbbf4ef7 |  | checklist | QA - First Fix |  |  |  |  | Yes | QA - First Fix | 9bcd7b3f-102d-439a-a70d-4907f7fb1abb
checkpoint-group | fa9d2a49-bf04-4b79-a2c5-25f7e8bda202 |  | section | Flush Boxes
checkpoint-status | 3eae09d8-49e2-48ca-bc3d-6f5807c2c52e |  | checkpoint | Fire Rated or Acoustic
checkpoint-status | a3f8e95d-7e4a-42d1-91ca-db4088023727 |  | checkpoint | Height as per plan
checkpoint-status | fec3bcb7-9150-4556-a07d-92eb558f21c5 |  | checkpoint | Location as per plan
checkpoint-status | f6d0ccad-e7a5-46ec-be05-852cfcc251ce |  | checkpoint | Intumescent Pad In Place
checkpoint-group | 8d94d6b1-d871-4664-bc5b-99f4ae20c606 |  | section | Cabling
checkpoint-status | f6ae990d-e38f-4c2a-aef3-8a9418e2944c |  | checkpoint | Power cables installed correctly
checkpoint-status | 742cf1b9-029a-4807-8d20-160e02412626 |  | checkpoint | Lighting cables installed correctly
checkpoint-status | 1ee1a44d-878a-4886-af19-19d15e97e335 |  | checkpoint | Equipment cables installed correctly
checkpoint-status | 8709c2b2-973d-4072-9353-6c250cc1d6f4 |  | checkpoint | Circuits clearly labelled
checkpoint-status | 0ddfb8e4-c8ad-44de-b8bb-62af570491ee |  | checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint-status | b74d9959-7bde-4c0d-9cf6-4cb48f17f556 |  | checkpoint | All cables secured via cable ties with ends cut
checkpoint-group | 572a24a4-b0e9-43c7-9a97-72daa45723f9 |  | section | Cable Ladder
checkpoint-status | 0b103d8c-4deb-4b0d-94dc-79dc37ff0c32 |  | checkpoint | Minimum 25% spare capacity left on cable tray
checkpoint-group | 2fe4fb6f-d19c-4455-afe2-bdf96e54b3f5 |  | section | QA - Lights
checkpoint-status | bdeeb454-7027-4bd7-b3aa-279d3e28bf15 |  | checkpoint | Setout Correct
checkpoint-status | 2829c3ae-73f8-4ca6-bb9e-83ebfcdc55f1 |  | checkpoint | Cabling in correct location
checkpoint-status | 452fa8f6-bab7-4f73-87e5-511f52a607ed |  | checkpoint | Emergency/ Exit Lighting
checkpoint-status | cd790a03-d4ca-4e87-95e7-d729aea84783 |  | checkpoint | Nogging installed for Electrical Services
checkpoint-group | d73a0b25-b0ab-44ae-a768-59243487d279 |  | section | Seismic Bracing
checkpoint-status | fd80f3f8-bed4-4df7-a62c-c67367ab5c78 |  | checkpoint | For Lighting
checkpoint-status | b3cbdf2e-bab8-4c9a-b748-474dd12dbf96 |  | checkpoint | Cable Tray
checkpoint-status | 828350cc-54dc-4675-a0bb-401ff97b6c9c |  | checkpoint | Switchboard
checkpoint-group | da03a5a8-bd4c-480e-964f-058f4db4cdc8 |  | section | Conduits
checkpoint-status | 7276ea28-4fa6-4947-a17d-6e82315063e3 |  | checkpoint | Correct size installed
checkpoint-status | dd6f52f4-98ce-4235-bfc6-afad823a9868 |  | checkpoint | Location as per plan
checkpoint-status | 97ad909e-8860-4544-9aba-f2d6d7586e13 |  | checkpoint | All conduits glued & watertight
checkpoint-status | a18df952-2380-42f6-986f-cdefc030c549 |  | checkpoint | Clean inside and in good condition
checkpoint-status | ea59af99-36c3-4d79-85d4-4e667380ad61 |  | checkpoint | Stainless screws used
checkpoint-group | 35752903-8fba-4670-b326-33281588a951 |  | section | Photos
checklist-flat | 2c9fd240-02d9-40fb-a42e-d614a784aab0 |  | checklist | Switchboard |  |  |  |  | Yes | Switchboard | bf47dfe4-7d11-4f7b-b117-de1468770a8f
checkpoint-status | 8d61e640-b670-4712-980e-2f0d177dd386 |  | checkpoint | Spatial certificate signed if required
checkpoint-status | ac29ccf5-5131-4b4c-bb3c-1c57a0efbcc0 |  | checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint-status | f6f39a15-2db8-4fa2-80f9-3802e7ba1ff5 |  | checkpoint | All clearances sighted to ensure location is compliant
checkpoint-status | a41406fa-aa7c-44f1-8331-7ecc94eabcff |  | checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint-status | d88954fe-beaf-4beb-8bfc-27235c03c66d |  | checkpoint | Cables neatly dressed
checkpoint-status | 40f03103-73d2-4910-806e-04b3ad0ecc1a |  | checkpoint | Phase tabs on chassy covered
checkpoint-status | 842f5dcf-80ee-493e-86c7-68ac1b6687e9 |  | checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint-status | 05de488d-8724-483d-8ac0-3e3212359c75 |  | checkpoint | Switchboard is clean on the inside and outside
checkpoint-status | 0ae91450-9b1e-4ad6-8d71-6feb63c9e55c |  | checkpoint | Masking blanks installed
checkpoint-status | bc93d21e-2a7e-4c54-aa88-ba0132b9849a |  | checkpoint | DB legend installed
checkpoint-status | da0b168f-3d62-497a-b6f4-e9562eab1ab8 |  | checkpoint | Feisst label on the door installed
checkpoint-status | ce43f214-bb37-4757-91c7-e90dab09f7f2 |  | checkpoint | Photos
checklist-flat | 12cbe54a-f6ac-4660-a60f-96cb2e15664f |  | checklist | Cable Ladder |  |  |  |  | Yes | Cable Ladder | c3ebe95d-e635-45d6-b482-9777a547ced1
checkpoint-status | 01c86da9-b24e-4b6c-9422-74641dbd70c6 |  | checkpoint | Unistrut Field & Painted
checkpoint-status | b9212531-adc5-40e1-8415-6ac761abfea3 |  | checkpoint | Hangers Spaced as Specified
checkpoint-status | 7e4cf596-ded3-4b16-a33c-409bc915497c |  | checkpoint | Correct Size Ladder Installed
checkpoint-status | 48c9666d-937d-4f70-bf84-19c04d01a74c |  | checkpoint | Ladder Joined Correctly
checkpoint-status | be726d8f-ab67-4a0d-8391-7d1a4d706ab4 |  | checkpoint | Hangers Seismically Restrained as per Design
checkpoint-status | d763ac4e-7787-4708-ab13-c531f422b3ab |  | checkpoint | Ladder Fastened to Hangers
checkpoint-status | fc6f3f2a-0c5a-497b-b695-1062173f002d |  | checkpoint | Correct Anchors used fixing to Ceiling / Walls
checkpoint-status | d33c86da-b08b-4c59-9a0e-d38e7bb1afe4 |  | checkpoint | Cable Ladder Bonded
checkpoint-status | e31aba93-be35-43f4-8f66-5834c467de95 |  | checkpoint | Photos
checklist-sectioned | 475d0b0b-c402-4da4-b3c2-84186c8d39b0 |  | checklist | FEL SM Weekly Site Checklist |  |  |  |  | Yes | FEL SM Weekly Site Checklist | cd5b5406-3b7b-4a77-ab9c-974b72158798
checkpoint-group | 6f36fb38-c787-415b-b125-1a4b56941174 |  | section | Monday
checkpoint-status | 50572691-febf-4331-b341-f90e03f93e3d |  | checkpoint | Pre Start Meeting with Team
checkpoint-status | 966296b3-dfda-4808-b191-c2275eb4c67d |  | checkpoint | Health Check
checkpoint-status | 606060fc-1f53-4a3a-8aa0-0f953f2eb096 |  | checkpoint | Review Tasks for the week
checkpoint-status | 160d44f7-851f-4188-8755-a9755f8426c4 |  | checkpoint | Identify Targets Including Hours
checkpoint-status | 3b063654-914c-4c6f-b70d-677469dbbdcf |  | checkpoint | Approve hours by 9AM for previous week
checkpoint-status | d513296b-6610-4cd1-8ef2-19ebce0e6082 |  | checkpoint | Sign off Subcontractor Hours & Submit
checkpoint-status | 156b931f-8b0d-4a19-8139-c19efe34c8b1 |  | checkpoint | Review SWMS
checkpoint-status | 6298e4f8-4dfe-47d1-90ec-5a7dc4620da0 |  | checkpoint | Site Toolbox Meeting
checkpoint-status | 46a3059f-9bc6-4ae6-90a3-a98949161631 |  | checkpoint | SSSP in Order
checkpoint-group | 0d5c088d-bb41-4d25-bcb9-2c63381d1cef |  | section | Tuesday
checkpoint-status | a914e83c-289e-4eb3-8dd1-f25cd4b9a770 |  | checkpoint | Follow up outstanding RFI's with PM
checkpoint-group | ebad7f64-fc9f-456f-aba2-0fbd2fe11e51 |  | section | Wednesday
checkpoint-status | 5504fe4a-ae9f-4e80-9845-b95c7b439181 |  | checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint-status | b226a162-89bf-410e-b74c-a5181e264b48 |  | checkpoint | QAs up to date
checkpoint-group | d20435b2-2a1d-434a-a969-02c58fdfe5c1 |  | section | Thursday
checkpoint-status | 20d033a1-89ac-4357-a21f-3a2ce0b389be |  | checkpoint | Weekly planner filled out for week ahead
checkpoint-status | e803bbf4-6ccc-474e-9d5b-d99b8fef2f0c |  | checkpoint | Roadblocks identified and actioned
checkpoint-status | 2ed9008f-29c1-43c0-83f5-41da3f16a2c9 |  | checkpoint | Materials organized for week ahead
checkpoint-status | a8a49443-b171-493c-9b58-8167a0dd703b |  | checkpoint | Plans printed with any relevant notes added
checkpoint-group | 9a39836f-5576-4b9f-af60-c7f9c1056c0d |  | section | Friday
checkpoint-status | 190b935b-5a13-4ea5-a269-5b1ccf06eceb |  | checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint-status | 884ed978-11cf-4ef7-bf03-b8fa1390b7d7 |  | checkpoint | Job Cards up to date and submitted
checkpoint-status | 073db379-5757-4ee1-ae4e-60260bff127b |  | checkpoint | Team tasks for week ahead filled out on whiteboard
checklist-sectioned | 8bb54341-baaa-41d8-86d3-4205ecf6766f |  | checklist | Inground Services |  |  |  |  | Yes | Inground Services | eafbd17c-10aa-4975-9573-1f87fc9c7539
checkpoint-group | 522b0c0b-ed7e-44ee-8f80-b2cdd4d477a5 |  | section | Ducts and Conduits
checkpoint-status | 49c0bb4e-d003-4782-9a2b-aacceb9bd3ea |  | checkpoint | Correct size installed
checkpoint-status | 42091936-3d32-443f-b1d3-6881921923f8 |  | checkpoint | Start and finish locations correct as per plan
checkpoint-status | c9dbec8d-0379-448c-ac87-fce2f556845c |  | checkpoint | separation from other services
checkpoint-status | 48a500ed-1145-49cd-b2a0-f16dbfb4d834 |  | checkpoint | Clean inside and in good condition
checkpoint-group | 97f0b626-ccce-4f58-96b1-ca5fee65de75 |  | section | Electrical Pits
checkpoint-status | 7668d727-ded3-4aec-a0c2-7b341db30860 |  | checkpoint | Set out correct
checkpoint-status | 1444d6fa-0e70-4363-82e5-12740872101e |  | checkpoint | Correct size installed
checkpoint-status | 9d3c5106-96e1-4b03-b439-b00fe1181aab |  | checkpoint | Duct entry holes sealed / water proofed
checkpoint-status | 969f39d4-ad14-4df1-83e9-a4e2a08a366d |  | checkpoint | Pits installed to correct height and level
checkpoint-status | 4c916f93-63da-4ba7-9987-5866ef9478ad |  | checkpoint | Clean inside and in good condition
checkpoint-group | b60c8b17-12bb-46bb-a741-a5f0dd1944ff |  | section | Light Pole Foundations
checkpoint-status | 8028a191-9657-411a-9961-88219d371659 |  | checkpoint | Set out correct
checkpoint-status | bb09c15b-ce98-42be-8db7-98c83e0ba4b1 |  | checkpoint | Ducting in correct position - centre of cage
checkpoint-status | 995205b6-7037-4800-9848-c47b5c843553 |  | checkpoint | Correct Cage Installed
checkpoint-status | 0bd5e106-65ac-44a2-a7e0-d7de1b3c79ba |  | checkpoint | Cage installed to correct height / level
checkpoint-status | 100b5d76-2e9a-476a-a104-d8793bb7cf47 |  | checkpoint | Ground Plant pole installed to correct height / level
checkpoint-group | 9e185004-68c1-46d0-8fc8-332d4537010d |  | section | Photos