## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Drainage - | [5 empty] | QA - 05. Drainage
section | Details
checkpoint | Construction drawings and specification sent to subcontractor.
checkpoint | Site set out by surveyor.
checkpoint | Site RL installed by surveyor.
checkpoint | Confirm backfill requirements (hardfill/compaction)
checkpoint | Sleeves at correct locations through site concrete/footings
checkpoint | Lines cleaned out CCTV if required
checkpoint | Subs QA, photos and As-built supplied
checkpoint | Council inspection.
checklist | Tanking/Waterproofing - | [5 empty] | QA - 07. Tanking_Waterproofing
section | Details
checkpoint | Construction drawings and specification sent to subcontractor.
checkpoint | Correct product confirmed
checkpoint | Correct backing for tanking to be installed
checkpoint | Pile cap waterproofing completed
checkpoint | Laps correct to join on to
checkpoint | Swell seal install in the correct locations
checkpoint | Independent membrane inspection
checkpoint | Independent inspection report completed
checkpoint | Council inspection.
checklist | Foundations - | [5 empty] | QA - 08. Foundations
section | Details
checkpoint | Construction drawings and specification sent to subcontractor.
checkpoint | Site set out by surveyor.
checkpoint | Site RL installed by surveyor.
checkpoint | Confirm foundation RL's bottom off footing
checkpoint | Geotech engineer inspection or confirmation received to proceed
checkpoint | Confirm foundation RL's top off footing
checkpoint | Foundation dimensions confirmed
checkpoint | Waterproofing DPC / Membrane installed inspected
checkpoint | Reinforcing complete
checkpoint | Starters installed and position confirmed
checkpoint | Drossbach starters install and positioned confirmed
checkpoint | Steps & stopends in place
checkpoint | Correct MPA concrete
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint | Rugasol exposed surfaces ready for keying in for next pours
checklist | Concrete Slab on Grade - | [5 empty] | QA - 09. Concrete Slab on Grade
section | Details
checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint | Slab on grade – top of metal RL.
checkpoint | Formwork in place.
checkpoint | Reinforcing steel – mesh size and lap.
checkpoint | Starter bars in correct position and size.
checkpoint | Holding bolts in place.
checkpoint | Floor thickness in place (random slab check areas).
checkpoint | Cover to reinforcing correct.
checkpoint | Construction joints / control joints installed.
checkpoint | Correct MPA / slump.
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint | Levels of finish confirmed.
checkpoint | Curing – water spray / membrane ordered.
checkpoint | Check overspray / clean.
checkpoint | Control joints / saw-cuts and depth.
checklist | Blockwork - | [5 empty] | QA - 10. Blockwork
section | Details
checkpoint | Construction drawings and specification to subcontractor.
checkpoint | Reinforcing ordered for blockwork.
checkpoint | Set out completed – pins in footings profiles installed and plumb
checkpoint | RL check for foundations.
checkpoint | Blockwork sizes correct.
checkpoint | Control joint locations and type agreed.
checkpoint | Openings framed out.
checkpoint | Reinforcing placed as per drawings.
checkpoint | Bond beams installed.
checkpoint | Control joints placed.
checkpoint | Washouts installed and cleaned
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint | Grout MPA & slump confirmed.
checklist | Structural Steel - | [5 empty] | QA - 11. Structural Steel
section | Details
checkpoint | Construction drawings and specification to subcontractor.
checkpoint | CI's/SIR's items of note communicated to subcontractor and actioned
checkpoint | Coordination with services complete on penetrations
checkpoint | Hold downs in the correct location
checkpoint | RL confirmed
checkpoint | Connections to PCP / Shotcrete correct / façade connections