## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Structural Steel - | [5 empty] | QA - 11. Structural Steel
section | Details
checkpoint | Construction drawings and specification to subcontractor.
checkpoint | CI's/SIR's items of note communicated to subcontractor and actioned
checkpoint | Coordination with services complete on penetrations
checkpoint | Hold downs in the correct location
checkpoint | RL confirmed
checkpoint | Connections to PCP / Shotcrete correct / façade connections
checkpoint | Site welding complete and checked
checkpoint | Shear studs installed
checkpoint | All bracing installed
checkpoint | Steel checked for plumb & level
checkpoint | All temporary bracing / shoring installed
checkpoint | All bolts checked, marked and torqued up
checkpoint | Engineer inspection received and remedials (if any) closed out
checkpoint | Subs QA provided
checklist | Concrete Beams/Stitches/Columns - | [5 empty] | QA - 14. Concrete Beams_Stitches_Columns
section | Details
checkpoint | Plans detailing set-out, RLs, sizes and relation to grid.
checkpoint | Formwork drawings for shutters and bracing.
checkpoint | Hire / order formwork if required.
checkpoint | Reinforcing and chairs ordered
checkpoint | Form tube and cones ordered.
checkpoint | Reinforcing in place – correct cover, size and stirrup centres correct.
checkpoint | Level of finish determined to match shutters finish required.
checkpoint | Set any castins that may be required
checkpoint | Correct MPA & slump.
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Structural engineer inspection or confirmation received to proceed
checklist | Suspended Floor (Comfloor) - | [5 empty] | QA - 15. Suspended Floor (Flatslabs)
section | Details
checkpoint | Construction drawings and specification to subcontractor.
checkpoint | Structural steel shop drawings sent for coordination
checkpoint | Install/lifting plan agreed into TA and signed onto by all involved
checkpoint | Flatslabs placed and secured
checkpoint | Propping plan supplied and approved
checkpoint | Propping installed as per approved design
checkpoint | Perimeter boxing installed
checkpoint | Set downs / rebates installed
checkpoint | Reinforcing installed correct bars and covers
checkpoint | Construction joints / control joints installed.
checkpoint | Correct MPA / slump.
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint | Curing – water spray / membrane ordered.
checkpoint | Check overspray / clean.
checklist | Suspended Floor (Rib & Tile) - | [5 empty] | QA - 16. Suspended Floor (Rib & Tile)
section | Details
checkpoint | Construction drawings and specification to subcontractor.
checkpoint | Site dimensions checked
checkpoint | Install/lifting plan agreed into TA and signed onto by all involved
checkpoint | Brackets correctly bolted to required specification
checkpoint | Correct seating allowed
checkpoint | Shoring system designed / required
checkpoint | Shoring installed
checkpoint | Timber infill's correct
checkpoint | Crane ordered, correct size and reach
checkpoint | Reinforcing in place, correct steel and clearances
checkpoint | Perimeter boxing installed
checkpoint | Construction joints / control joints installed.
checkpoint | Correct MPA / slump.
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint | Curing – water spray / membrane ordered.
checkpoint | Check overspray / clean.
checklist | Roofing Membrane - | [5 empty] | QA - 20. Roofing Membrane
section | Details
checkpoint | Sub structure signed off
checkpoint | IDL system confirmed if required
checkpoint | Connection / hold downs installed
checkpoint | Plywood substrate installed
checkpoint | Penetration / plinths / parapets brought through the roof to correct height
checkpoint | Nibs and upstands installed
checkpoint | Angle fillets installed
checkpoint | Gutter / sumps / overflows installed correct falls
checkpoint | Pre start inspection from membrane contractor / manufacture
checkpoint | Membrane inspection undertaken by manufacture
checkpoint | Membrane inspection report completed
checkpoint | Roofing installed
checkpoint | Cap / Parapet flashings installed
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Subs QA supplied
checklist | Insitu slab infill - | [5 empty] | QA - 34. Insitu slab infill
section | Details
checkpoint | Plans showing RLs / set downs / nibs / rebates / slab thickness.
checkpoint | Formwork in place.
checkpoint | Reinforcing steel – mesh size and lap.
checkpoint | Starter bars in correct position and size.
checkpoint | Floor thickness in place (random slab check areas).
checkpoint | Cover to reinforcing correct.
checkpoint | Construction joints / control joints installed.
checkpoint | Correct MPA / slump.
checkpoint | Council inspection or confirmation received to proceed
checkpoint | Structural engineer inspection or confirmation received to proceed
checkpoint | Levels of finish confirmed.