## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | GT4-ITP-014 - Electrical Works | itp | GT4-ITP-014 - Electrical Works |  | cca7e9be-f7b7-4ee3-8d09-046b4de3e61e
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Define physical bounds of a lot
2013e2f3-bbef-50f2-be67-92f6d2567401 | note | Frequency: Prior to Commencing Work
748d43b6-5e44-500f-a42a-45cf942c27d4 | note | Acceptance Criteria: Maximum lot size = Single run to the location of field equipoment. Multiple cables can be included in the lot
a0e85c32-8b8c-5011-aa9a-405d043fdbb2 | note | Reference Documents: Lot Map
724fe329-fd7e-5c45-ba01-379a6d9333b5 | note | Record of conformity: Lot map
cec3ddc2-ff59-5266-a14a-b7a44023b5f5 | note | HP*
d5b2ea8c-0023-5826-8b14-408741c623a1 | note | Responsibility: Site Engineer
c9476cf8-2ada-5911-8107-927d2262a786 | date | Date Completed:
| checkpoint | 1.2 - Site Access available
7efb809b-d0d0-5064-b301-9a762847ebca | note | Frequency: Prior to Commencing Work
96b9e722-32af-56df-9e5c-39adc33c2772 | note | Acceptance Criteria: Confirm Site access to area with Supervisors. Confirm all safety procedures including car and pedestrian barriers are in place - as required.
9d396dc8-3fa2-5ff5-a532-a7886719b86f | note | Reference Documents: Current safety requirements of the site
2a7f83fb-1046-557d-96c3-2e5c0f982822 | note | Inspection / Test Method: Site inspection
036bc5f7-7ada-5d10-a329-b07f729f9b82 | note | Record of conformity: Photos
65cbc08d-5e26-5710-938a-802bd00e223a | note | HP*
4d41ac6f-81a4-5146-9085-b41654aaed83 | note | Responsibility: Site Engineer
8b7ff225-4ff6-5b25-aa15-8b5cd790bdfc | date | Date Completed:
| checkpoint | 1.3 - Underlying lot(s) conform
d784f2ef-34c8-5ee3-8091-155f8e374d5b | note | Frequency: Prior to Commencing Work
d1eab0ea-c582-5e8a-959a-ed920e618ad4 | note | Acceptance Criteria: Contractor to verify all underlying lots are closed, or lots open but acceptable to proceed with work. Confirm "Service Trenching & Install CTN-ITP-003" has been completed and signed off.
50f4621d-ac83-5dd4-b7d9-a579fce709d6 | note | Reference Documents: "Service Trenching & Install CTN-ITP-003"
cfecc6b9-f13e-51b6-83be-61d0746210b0 | note | Inspection / Test Method: Site inspection
7bf61edb-ec88-5506-b348-0790383f0e73 | note | Record of conformity: Previous related ITP completed and signed off
b96a172b-de70-5e59-91ea-da99120e0a41 | note | HP*
2506b68f-d3c1-5f3d-be8e-2acee88fb7d3 | note | Responsibility: Site Engineer
dad6c3c9-feba-5e6e-820c-d17301551867 | date | Date Completed:
| checkpoint | 1.4 - Ensure current Termination drawing revisions and cable schedules are available
d6c648f4-cf1f-5226-9c71-458dccab805b | note | Frequency: Prior to Commencing Work
961b9140-25eb-5aff-b10a-162074ebf5ce | note | Acceptance Criteria: Identify and use latest drawing revisions.
8d71e1ee-13d4-51f2-8979-1eae12c47e67 | note | Reference Documents: latest relevent drawings
299b8542-ba69-5337-a4d0-eff74573a17a | note | Inspection / Test Method: Document review & Site inspection
7669a0d9-1087-500a-8172-22297ca08686 | note | Record of conformity: List drawings and version
21ccce91-5541-5d76-ace3-01e2ad36f549 | note | HP*
c14f3774-f4f4-5179-90f5-75d1fbf11d2b | note | Responsibility: Site Engineer
5e80bed5-2911-5a6d-a0c1-2ef4e4765238 | date | Date Completed:
| section | 2 - Subcontractor ITP
| checkpoint | 2.1 - Receive completed FLE ITP SS107 - Fence and gate installation
3edbf162-f9ab-5926-99bb-dbcca59d2dfe | note | Frequency: Per ITP
39f8ab71-0c16-5676-9aee-74b626c3c00b | note | Acceptance Criteria: ITP per lot package satisfactorily completed
665ec274-54c1-51e8-8ac1-b249d182d7e8 | note | Reference Documents: Signed and completed ITP
3d8df007-81da-52b9-98da-11119fd6e773 | note | Inspection / Test Method: AS/NZS 3000
735a7ab7-f19b-5c30-8751-cd8868416afe | note | Record of conformity: Signed ITP
2030c765-6366-503f-9abb-371f345ed1c5 | note | HP*
b2a46b22-f6a0-5e9e-b720-b87924bd5dde | note | Responsibility: Site Engineer
52340157-9941-5dac-8309-fd6c03007acf | date | Date Completed:
| checkpoint | 2.2 - Receive completed FLE ITP SS108 - Internal road
393b8d37-2cc9-537f-bbf4-46bcd16bee07 | note | Frequency: Per ITP
6967a878-fd24-5713-be3d-0ab8118ed0f1 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
a215ae1c-03c6-5faa-959f-59dce8f1c2b5 | note | Reference Documents: Signed and completed ITP
68230d56-e1ac-5e78-93d1-0e526eac523a | note | Inspection / Test Method: AS/NZS 3000
3c85acf4-fcf4-54d0-9fc2-c5b987d6678b | note | Record of conformity: Signed ITP
ce117278-458b-57cf-a68c-44a3437c55cb | note | HP*
94ac1357-8bbf-59cf-bf0d-e14bbe05d8f9 | note | Responsibility: Site Engineer
f184202b-602f-5ebf-9a27-880aecf9ccdd | date | Date Completed:
| checkpoint | 2.3 - Receive completed FLE ITP SS109 - Switchyard Surfacing
c53c41df-3363-58c3-b301-b0855ec9a97a | note | Frequency: Per ITP
d00121a5-54e8-55fb-925b-9274450a6fa3 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
9d1646ee-1741-5a29-8517-01eaacf29c2b | note | Reference Documents: Signed and completed ITP
52f09c96-f4bb-5e39-85e1-0d0a4e2245b2 | note | Inspection / Test Method: AS/NZS 3000
cb79c5fa-e087-5de2-a965-2444de374fdf | note | Record of conformity: Signed ITP
1de0d2ac-da55-51bd-9abb-03a3e6b9dd27 | note | HP*
3b4aabbb-765d-5d97-8515-1850653bcf2b | note | Responsibility: Site Engineer
1b3e998b-7862-531d-82d6-ad6075178eba | date | Date Completed:
| checkpoint | 2.4 - Receive completed FLE ITP SS110 - Stormwater Pipe Installation
b190e8af-088a-55df-ac95-ee677d1b8c99 | note | Frequency: Per ITP
7bd7724f-b0f5-5def-96d8-394363f4c0aa | note | Acceptance Criteria: ITP per lot package satisfactorily completed
b069abf9-4b16-566a-a421-62907ff87e66 | note | Reference Documents: Signed and completed ITP
78ba56f6-127d-563b-9c50-29d11b6657f6 | note | Inspection / Test Method: AS/NZS 3000
2346005f-21a4-50ea-8235-a4e1345a0fc4 | note | Record of conformity: Signed ITP
a152ed43-ffa3-5742-929b-8582d76634bc | note | HP*
7f5ff26a-0d04-5246-b261-544241e28b98 | note | Responsibility: Site Engineer
094c2a3c-81b4-52a3-a5c2-da6bc22caa79 | date | Date Completed:
| checkpoint | 2.5 - Receive completed FLE ITP SS200 - Structural Steel Installation
86c3db10-e271-567f-9375-92f2755f01c8 | note | Frequency: Per ITP
5e89c2b4-9ec5-5a49-b7bd-2fc56e4c66cd | note | Acceptance Criteria: ITP per lot package satisfactorily completed
cb6ed715-bbe6-51aa-96e9-4bc1f221bcd1 | note | Reference Documents: Signed and completed ITP
f724d845-90f0-5350-a574-cc0faebef848 | note | Inspection / Test Method: AS/NZS 3000
3e6bb671-afd4-5171-bb41-5b2c4d899d9c | note | Record of conformity: Signed ITP
54bde4fd-4db5-5af9-8096-7a5c108b2bcc | note | HP*
5b3263a3-4365-59da-bed3-7435cd59d04b | note | Responsibility: Site Engineer
edd9d119-8992-549f-ada5-a437539924f9 | date | Date Completed:
| checkpoint | 2.6 - Receive completed FLE ITP SS301- Substation Earth Grid Inspection Checklist
6ab9cd62-c13d-528c-a432-67ce5542245f | note | Frequency: Per ITP
44c64ae0-4dc8-5a12-9cdf-515eab325928 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
05646d8e-2a19-5782-8e23-3c832f513358 | note | Reference Documents: Signed and completed ITP
a41b1dcc-fbf9-5c84-bfca-fda7622a1440 | note | Inspection / Test Method: AS/NZS 3000
10c9c098-e537-5631-8ca4-4eaae21217ba | note | Record of conformity: Signed ITP
27c99dae-e31d-5c38-87e8-30bb2351a3ca | note | HP*
5c47bbea-ef0c-5e68-ac7a-305659901382 | note | Responsibility: Site Engineer
d1855bcb-de94-5bdb-bbb6-7d7df17bb02b | date | Date Completed:
| checkpoint | 2.7 - Receive completed FLE ITP SS302 - Current and Voltage Transformer Installation Checklist
f31c36b0-67e4-5bc3-adc2-da34d05a0fee | note | Frequency: Per ITP
6d201c41-96de-5148-9466-2eadd990a45b | note | Acceptance Criteria: ITP per lot package satisfactorily completed
4dde1f37-0584-59fc-9ba3-afc182c64379 | note | Reference Documents: Signed and completed ITP
7688600e-71f6-5df6-aa06-3af05e5c8160 | note | Inspection / Test Method: AS/NZS 3000
2ecc9617-888a-573e-81a2-ff844634acaa | note | Record of conformity: Signed ITP
2a67f1b7-dcfa-5148-8d76-0a38ddc70697 | note | HP*
1beb2030-970e-5989-8ff7-15cd856446aa | note | Responsibility: Site Engineer
91c217f3-bf2b-5b82-bf8c-7ceabdb90413 | date | Date Completed:
| checkpoint | 2.8 - Receive completed FLE ITP SS303 - Isolator and Earth Switch Installation Checklist
4328a9e8-9843-5484-b262-3068aafa30df | note | Frequency: Per ITP
b943c5c7-1338-567a-bdbe-3e7d8e8fda2f | note | Acceptance Criteria: ITP per lot package satisfactorily completed
dea7810f-b6bd-5ea8-9878-e305f9f83833 | note | Reference Documents: Signed and completed ITP
c06cab17-75de-5199-9360-9c837b964564 | note | Inspection / Test Method: AS/NZS 3000
71c2a502-1d93-5659-9d89-a4211ccae918 | note | Record of conformity: Signed ITP
da9d64e1-8a47-5e67-8c58-ffa6f3c62a2e | note | HP*
902b46ef-a017-5105-ab3e-4aab69abe5a7 | note | Responsibility: Site Engineer
1b227f69-f2e1-57a9-935b-0cc2f4aea9fd | date | Date Completed:
| checkpoint | 2.9 - Receive completed FLE ITP SS304 - Circuit Breaker Installation Checklist
e4382413-78b6-5051-8ffd-6df6344ebfe7 | note | Frequency: Per ITP
ff25a0d0-2d28-5874-8413-fa3b93a85c74 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
f554dc23-bf63-5c4a-a278-bd164f6dd47e | note | Reference Documents: Signed and completed ITP
ec6bb70c-57f5-59ce-8660-2d41b6d27e41 | note | Inspection / Test Method: AS/NZS 3000
f388f587-e88f-511e-ae10-5f5d3832cbec | note | Record of conformity: Signed ITP
dec847f1-9925-5158-b00c-bf2a18938147 | note | HP*
44b04694-8072-5d6a-beab-62c54367069b | note | Responsibility: Site Engineer
d1101fac-d9bb-52d7-b280-f5983b7dece0 | date | Date Completed:
| checkpoint | 2.10 - Receive completed FLE ITP SS305 - Post Insulator Checklist
e5dd62a0-ef3b-514f-b24e-f8f7bf18fbc4 | note | Frequency: Per ITP
d3122ff2-af1b-5cd8-8544-8bda731fa6d0 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
526632b2-0bb1-5535-a54c-e1c845fb430d | note | Reference Documents: Signed and completed ITP
01d05049-8ee4-5252-a11d-91f3bd26ba76 | note | Inspection / Test Method: AS/NZS 3000
19c2808d-f9da-5b1a-b5b3-bb1c288c1819 | note | Record of conformity: Signed ITP
a73d2557-b7e5-525e-aa30-68d1b4d2938a | note | HP*
2c734f20-5ffb-5aba-acdf-9530ffb89f6e | note | Responsibility: Site Engineer
ffe47701-2e1f-5815-b75a-57d0879ae472 | date | Date Completed:
| checkpoint | 2.11 - Receive completed FLE ITP SS306 - Bus Bar and Clamps Installation Checklist
4f7c4a8e-23ca-5193-963f-a55ec72860b9 | note | Frequency: Per ITP
509db4fc-314b-59f6-8b56-3b7b87d7eb4e | note | Acceptance Criteria: ITP per lot package satisfactorily completed
77ddc562-7716-5250-9726-a36214c961ed | note | Reference Documents: Signed and completed ITP
5747d405-83aa-5536-b2ae-7218b47b4a45 | note | Inspection / Test Method: AS/NZS 3000
aa91afbf-78f2-5009-9f51-f713de9e0c4c | note | Record of conformity: Signed ITP
fa47f8b2-8b8a-5c74-8d63-6157e0eff216 | note | HP*
fa3069fb-4a06-54fa-b7f4-f8bc36e96053 | note | Responsibility: Site Engineer
275a3bde-1296-5ed9-a9d0-b356b145bc68 | date | Date Completed:
| checkpoint | 2.12 - Receive completed FLE ITP SS307 - Control Panel Installation Checklist
12e06f97-1982-544e-a79d-e2986a5d7d66 | note | Frequency: Per ITP
f410e722-2a4f-5c64-aaf3-30f29c0ef1a8 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
faa16c15-e881-532f-984d-1a7d7e4ec2bf | note | Reference Documents: Signed and completed ITP
15aadd74-deb9-5021-9399-343d48bbc063 | note | Inspection / Test Method: AS/NZS 3000
d2df3914-3248-5a16-b509-942b76ce7982 | note | Record of conformity: Signed ITP
b61348a8-dac2-55c5-abf2-6b4f5e1593f4 | note | HP*
faa2f9bb-e87f-5ea2-8fbf-74a64165fff6 | note | Responsibility: Site Engineer
53c937cc-c61e-5393-a1dc-bea1ab3328fc | date | Date Completed:
| checkpoint | 2.13 - Receive completed FLE ITP SS308 - Lighting Mast Installation Checklist
4fc3386d-ac7e-540b-b676-dcafec03f519 | note | Frequency: Per ITP
7949a3e0-bc43-5bea-b13d-4d2193d15788 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
80da7b19-9061-55cc-a850-c21bda9da95e | note | Reference Documents: Signed and completed ITP
220bf728-3eee-5ed0-ac7d-8a1052e6fcf0 | note | Inspection / Test Method: AS/NZS 3000
57fd093f-c09e-5901-a526-336b3f88f54f | note | Record of conformity: Signed ITP
af27e2f2-50e1-5c83-b24b-249d8ed3fabf | note | HP*
fa83c492-0fd2-53a2-a050-a055c71ab848 | note | Responsibility: Site Engineer
137717a2-911b-5fd3-872d-2b7c61897c26 | date | Date Completed:
| checkpoint | 2.14 - Receive completed FLE ITP SS309 - Low Voltage Cable Termination Checklist
34ff7a40-afff-5a59-bfba-9989ead2c3f0 | note | Frequency: Per ITP
e01b78ef-3414-5010-bfab-6d64bc66ca99 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
2ead78e1-4688-5c15-a0d0-bd86c8ba6448 | note | Reference Documents: Signed and completed ITP
23b81137-69b8-53c5-9e7f-21eafd7018e1 | note | Inspection / Test Method: AS/NZS 3000
b4193d9a-296d-536c-bd76-87d4cffbdf36 | note | Record of conformity: Signed ITP
7c912d8e-7b2d-5ea2-ae94-9cce2e251b07 | note | HP*
41f4dbf0-9b21-59c0-a562-a12c50a3630e | note | Responsibility: Site Engineer
67b03e41-861c-5c45-b429-9e432ef77289 | date | Date Completed:
| checkpoint | 2.15 - Receive completed FLE ITP SS310 - Ductor Test Results (Insulation resistance DLA/DDF)
e914c482-305b-575e-b891-ac9c6cb58f21 | note | Frequency: Per ITP
81305a37-26e4-586a-988a-9cea02cf6465 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
6bfeb68f-709a-58d2-91c5-1bf5b2483016 | note | Reference Documents: Signed and completed ITP
3a850046-094f-52e2-8e92-0003c4b7c5af | note | Inspection / Test Method: AS/NZS 3000
ad7af829-8bad-5ba1-b2ef-1e51681461fb | note | Record of conformity: Signed ITP
51dafac2-ef29-512e-ab22-706843ba6c89 | note | HP*
4cad94c0-aac6-5bb7-8451-55f6b0126399 | note | Responsibility: Site Engineer
3b9701af-8fae-5392-a42f-c9b197248b22 | date | Date Completed:
| checkpoint | 2.16 - Receive completed FLE ITP SS311 - Marshalling Box Installation Checklist
54457018-03d3-569f-aefe-45c0c6c56209 | note | Frequency: Per ITP
17094e0f-f9f2-5123-b923-09a5e394f723 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
fa04ef50-532a-53f9-906c-63a5acde5ba4 | note | Reference Documents: Signed and completed ITP
7df36cd2-64c8-5e99-bf5d-fce6c9b09035 | note | Inspection / Test Method: AS/NZS 3000
204c31be-eaee-5b29-9a02-77dcb7e3fe56 | note | Record of conformity: Signed ITP
eaa816af-c9cf-531e-b991-61f6bc4f9490 | note | HP*
a4eb368f-8f70-50a3-aa4d-4a7147261d33 | note | Responsibility: Site Engineer
eee55797-822f-507a-a0fd-0aed3e9344ee | date | Date Completed:
| checkpoint | 2.17 - Receive completed FLE ITP SS312 - HV Cable termination
e9c1b1b0-ca22-573a-865c-ef82b7ef1591 | note | Frequency: Per ITP
f2cb88aa-44ce-56a9-acc2-e51e8a8f3bc4 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
d30c7852-99d0-5967-a331-6471ae3e9f4e | note | Reference Documents: Signed and completed ITP
1314cd95-e43b-5452-8f20-301c79cab5a4 | note | Inspection / Test Method: AS/NZS 3000
6a37c35d-ff80-5627-8c89-328645657a18 | note | Record of conformity: Signed ITP
190c46b5-031f-5435-b4b9-5956c6e3105e | note | HP*
0a5ef813-4297-57ba-820e-2538ec8a8fc9 | note | Responsibility: Site Engineer
92178d88-77ad-5a8f-943e-caf305d1df88 | date | Date Completed:
| checkpoint | 2.18 - Receive completed FLE ITP SS313 - Light and Power in Substation Building
f5b93aba-9d25-539a-91d8-1d58f08bdd5f | note | Frequency: Per ITP
a26e0431-7e47-5c42-94fa-5e819ea37e27 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
3380a5b3-99f8-5779-b464-65cd87f5ae63 | note | Reference Documents: Signed and completed ITP
f6d0be86-6293-5be0-b747-725ebdad0c48 | note | Inspection / Test Method: AS/NZS 3000
839a762f-bc35-53fa-8475-24992e8f008f | note | Record of conformity: Signed ITP
1048d948-83e6-5694-a303-1e80223b0788 | note | HP*
7323686b-da43-5b37-8e98-548814905aaa | note | Responsibility: Site Engineer
6d53d406-12f8-591d-b366-7ef5c97b7ab7 | date | Date Completed:
| checkpoint | 2.19 - Receive completed FLE ITP SS314 - Field Cable Installation
21881c0d-bf93-575d-bb26-1599816b58f9 | note | Frequency: Per ITP
4dae6fcf-9c94-506a-99fe-00467a062b18 | note | Acceptance Criteria: ITP per lot package satisfactorily completed
44df8283-fb87-5059-89ce-fd91b0359761 | note | Reference Documents: Signed and completed ITP
080e9573-be59-5092-a1fa-1e60ea14312f | note | Inspection / Test Method: AS/NZS 3000
09351a5d-1073-5835-acbd-16fe74fd1f15 | note | Record of conformity: Signed ITP
47d000ea-bbe5-51d1-84aa-ab9be92b9a45 | note | HP*
cbd2164e-981d-5316-8188-2d441803703c | note | Responsibility: Site Engineer
b48c413a-3ca1-5c1f-be0a-d8548af34cd1 | date | Date Completed:
| section | 3 - Final Inspection
| checkpoint | Final Inspection
95942443-6527-56a2-b5ea-a4842155354c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e429ccfd-dac4-56fe-98e5-c732c36bfacf | textbox | Print Name:
34591ab1-ca50-5d59-bbbf-8840503e32e9 | textbox | Position:
ff7e91c2-5747-5459-8d8c-d06032683757 | date | Date:
| signoff | Sign ITP