## Checklist Templates
Type | Name | Values | Prompting Name
checklist | ITPS-025 Ewis Fit Off AS 1670.4 | itp | ITPS-025 Ewis Fit Off AS 1670.4
checkpoint | 1. WIP
note | CIBSE C6.2.8 Warden Intercom Phones
note | Are the Warden Intercom Phones mounted at a height of not less than 1200mm & not more than 1800mm?
button | Is there one WIP per EWIS zone installed within 4m of the exit? | Yes, No
note | Add Photo
checkpoint | 2. SPEAKERS
note | CIBSE C5.2.2 Set Points
textbox | Drawing Reference and Revision Number:
button | Have all speakers been installed to the latest RCP? | Yes, No
note | Add Photo
checkpoint | 3. STROBES
note | CIBSE C5.2.2 Set Points
note | Have all strobes been installed to the latest RCP?
button | Have all strobes been labelled "EVACUATE" with 25mm lettering? | Yes, No
note | Add Photo
checkpoint | 4. HOLD POINT DETAILS
button | Hold Point Required:
checkpoint-no-status | GM Fire Sign Off
signoff | GM Fire Sign Off
checkpoint-no-status | Principal Contractor Sign Off
signoff | Principal Contractor Sign Off
checkpoint-no-status | Consultant Sign Off
signoff | Consultant Sign Off