## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Penetration checklist
section | Penetration
checkpoint-no-status | Subcontractor: PREMIER FIRE
checkpoint | Service material
button | Material: | Pipe,Cable
textbox | Size of the Service
textbox | FRL Required
checkpoint | Penetrating Substrate
button | Penetrating Substrate: | Wall,Floor
textbox | Wall / Floor Type
checkpoint | Manufacturer providing the Passive Fire System
button | Manufacturer: | PROMAT,HILTI,BOSS
checkpoint | Passive Fire Product
tickbox | SEALANT
tickbox | BATT
tickbox | PENO PATCH
tickbox | COLLAR
checkpoint | Test Data / Opinion
checkpoint | Attach relevant drawings and photos of penetration
checklist | Sprinkler System Installation ITP
section | First Fix
checkpoint | Area clear, tidy and accessible
textbox | Drawing Document number and revision:
checkpoint | Delivery inspection
checkpoint | Pipework to spec and approved sample
checkpoint | Fittings to spec and approved sample, piping & weld quality reviewed
checkpoint | Cut sheets and plans align with pipe delivered to sit
label | Installation of only approved sample equipment
label | Installed to approved drawing
label | Compliance with AS2118
checkpoint | Operating temperature (fast response, colour of liquid in bulb)
checkpoint | Joints, connections, supports, position & spacing / obstruction correct
checkpoint | Shields/guards provided (where specified)
label | Fixings and supports in accordance with AS2118
checkpoint | Valves Set Installed as per approved sample
checkpoint | Joints, connections, supports and position correct - any accessories installed if required
checkpoint | Controls and electrical services
checkpoint | Signage, Labelling, Locks and straps
checkpoint | Seismic Restraint Installed as per the design
checkpoint | Painting of exposed Pipework
section | Second Fix
checkpoint | Check Sprinkler Heads
textbox | Type and material
textbox | Operating temperature (fast response, colour of liquid in bulb)
checkpoint | Joints, connections, supports, position & spacing / obstruction correct
checkpoint | Shields/guards provided (where specified)
checkpoint | Escutcheon plates added
checkpoint | Sprinkler Support Systems are installed to not impede other services installed
label | Installed to approved drawing
label | Compliance with AS2118
checkpoint | Seismic Restraint Installed as per the design
checkpoint | Fire Rating completed prior to ceiling sheeting
checkpoint | Sprinkler heads have been installed straight prior to ceiling sheeting PFS advise any heads found not straight will not be at our expense to rectify - please take photos
section | Final Fit Off
checkpoint | Check Sprinkler Heads
textbox | Type and material
checkpoint | Operating temperature (fast response, colour of liquid in bulb)
checkpoint | Joints, connections, supports, position & spacing / obstruction correct
checkpoint | Shields/guards provided (where specified)
checkpoint | Escutcheon plates added
label | Installed to approved drawing
label | Compliance with AS2118
section | Hydraulic Pressure Test
checkpoint | 1600 kPa or 400 kPa in excess of the maximum static working pressure, whichever is greater, for a period of not less than 2 hours
textbox | Start Time:
textbox | Pressure:
checkpoint | Attach picture of pressure test gauge:
textbox | Finish Time:
textbox | Pressure:
checkpoint | Final Client Sign Off - All work completed as per ITP
checklist | Dry Fire System Installation ITP
section | Installation Inspection
checkpoint | Area clear, tidy and accessible
checkpoint | Installed to approved drawing
label | Compliance with AS1670, AS1668, BCA 2015
textbox | Drawing Document number and revision:
checkpoint | Check Cabling
checkpoint | Conduits installed
section | Cabling Rough In
checkpoint | Cabling roughed into RCP and interface locations and Cable continuity checks have been conducted prior to ceiling sheeting.
checkpoint | Fire Rating completed prior to ceiling sheeting
checkpoint | Are wires clearly drawn and submitted for AS BUILTS/AS CONSTRUCTED drawings
checkpoint | Riser Cable Tray Installation & cables fed
button | Fire rated cabling to floor LOOP, WIP, SPEAKER | Yes,No,N/A
button | Cable supported to tray | Yes,No,N/A
button | Cable connections | Yes,No,N/A
checkpoint | Fire rating of penetrations in riser
section | Final Fit Off
checkpoint | Thermal and Smoke Detectors
checkpoint | Check Thermal and Smoke Detectors installed in accordance with AS1670, AS1668, BCA
button | Spacing, no paints / marks & fit for purpose | Yes,No,N/A
checkpoint | Check Speakers installed in accordance with AS1670, BCA
button | Spacing, no paints / marks & fit for purpose | Yes,No,N/A
checkpoint | WIP & ECP installed in accordance with AS1670, BCA
button | Spacing, no paints / marks & fit for purpose | Yes,No,N/A
checkpoint | Check Interfaces as noted above are installed in accordance with AS1670, AS1668, BCA
button | Fit for purpose | Yes,No,N/A
checkpoint | Cabling Test to be conducted after fit off to confirm end of line resistance and/or loop continuity
checkpoint | Final Client Sign Off - All work completed as per ITP
checklist | Fire Detection System Commissioning
section | Fire Detection System Commissioning
checkpoint | Area accessible & ready
textbox | Drawing Document number and revision:
checkpoint | Floor inspect to confirm all system works are complete
checkpoint | All faults and isolations cleared for area
checkpoint | Installation of only approved sample equipment which is fit for purpose
label | Installed to approved drawing
label | Compliance with AS1670, AS1668, BCA 2015
checkpoint | Joints, connections, terminations, separation of cables, Fixing, supports, position & spacing / obstruction correct
checkpoint | Signage & Labelling installed, block plans reviewed
checkpoint | Test Thermal and Smoke Detectors in accordance with AS1670, AS1668, BCA
checkpoint | Test Speakers/ Visual in accordance with AS1670, BCA
checkpoint | Test WIP & ECP in accordance with AS1670, BCA
checkpoint | Test all interfaces in accordance with AS1670, AS1668, BCA
label | Interfaces to be tested: Sprinkler system, hydrant system, fire graphics, mech (fans/dampers/boards/MSSB), security, background music, prohibitive signage, vacuum waste, boom gates, BMS, IBAMS
textbox | Number of devices tested
textbox | Number of Interface tested
checkpoint | Emergency warning System.
textbox | Max reading
textbox | Min Reading
textbox | WIP Reading
checkpoint | ASE Commissioning
checkpoint | Final Client Sign Off - All work completed as per ITP
checklist | Sprinkler System Commissioning
section | Sprinkler System Commissioning
checkpoint | Floor inspect to confirm all system works are complete
checkpoint | Installation of only approved sample equipment
label | Installed to approved drawing
label | Compliance with AS2118
textbox | Operating temperature (fast response, colour of liquid in bulb)
checkpoint | Escutcheon plates installed
checkpoint | Joints, connections,position & spacing / obstruction correct
checkpoint | Shields/guards provided (where specified)
checkpoint | Fixings and supports in accordance with AS2118
checkpoint | Sprinkler Support Systems are installed to not impede other services installed
checkpoint | Controls and electrical services
checkpoint | Signage & Labelling, Locks & Straps installed, block plans reviewed
checkpoint | Seismic Restraint & paint assessed
checkpoint | Check operation of isolation valve & FIP interface
checkpoint | Inspect and test gauge operation
checkpoint | Check operation of drain for sprinkler system
checkpoint | Check operation of manual test drain confirm FSW activation to FIP
checkpoint | Check operation of solenoid test drain confirm FSW activation to FIP
checkpoint | Final Client Sign Off - All work completed as per ITP
checklist | Hydrant Commissioning
section | First Fix - Floor Hydrant
checkpoint | Area clear, tidy and accessible
textbox | Drawing Document number and revision:
checkpoint | Delivery inspection
checkpoint | Pipework to spec and approved sample
checkpoint | Fittings to spec and approved sample, piping & weld quality reviewed
checkpoint | Cut sheets and plans align with pipe delivered to site
label | Installation of only approved sample equipment
label | Installed to approved drawing
label | Compliance with AS2419
checkpoint | Check Hydrant Landing Valves
tickbox | Type and material
tickbox | Joints and connections
tickbox | Position and spacing / obstruction
tickbox | Fixing and supports in accordance with AS2419
tickbox | Note number of units per floor and attach photos
checkpoint | Check Hose Reel
tickbox | Type and material
tickbox | Joints and connections
tickbox | Position and spacing / obstruction
tickbox | Fixing and supports in accordance with AS2419
tickbox | Note number of units per floor and attach photos
checkpoint | Isolation Valve installation
tickbox | Type and material
tickbox | Joints and connections
tickbox | Position and spacing / obstruction
tickbox | Fixing and supports in accordance with AS2419
tickbox | Note number of units per floor and attach photos
tickbox | Valve numbering
checkpoint | Valve Set installation
tickbox | Type and material
tickbox | Finish
tickbox | Make and model no.
tickbox | Capacity/output
tickbox | Joints and connections
tickbox | Supports
tickbox | Position
tickbox | Accessories
tickbox | Control and electrical services
tickbox | Signage, labeling, locks and straps
checkpoint | Compliance Check - 100mm around valve Handle
checkpoint | Compliance Check - Hydrant on 45 degree
checkpoint | Compliance Check - Couplin Bolts not impeding operation
checkpoint | Council Inspection Rough In
section | Second Fix - ZONE PRESSURE TEST AT TOP OF ZONE
checkpoint | Hydraulic Pressure Test
label | Hydrostatic pressure testing of 1700KPA for a 2 hour period as required in AS2419, S10.2.2. Onsite testing installation @ 1700KPA
label | Attach Photos
section | Third Fix - Final Sign Off
checkpoint | Signage, Locks and Straps
checkpoint | Asset register and Test Tag NO.
checkpoint | Block Plan Installation
checkpoint | Commissioning
checkpoint | As Built Complete
checkpoint | Escutcheon plates added
checkpoint | Installed to approved drawing