## ITP Master Body
Project: Peacocke Whatukooruru Drive
Number and Revision: DN1205 - 139 - Rev B
Item No. | Inspection and Test Point | Acceptance / Conformance Criteria | Standard / Specification | Verifying Document | Frequency | Verification Activity
[6 empty] | Activity | By
SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
3.01 | Site Requirements
3.01.01 | Approved Shop Drawings | Shop drawings have been approved by designer. | BBO | Shop Drawings and Approval | Prior to fabrication | HP | ENG
SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
4.01 | Materials
4.01.01 | Balustrades | Balustrades to be manufactured as per shop drawings. |  | Shop drawings Dockets Galv Records | Prior to Order | H | PE
4.01.02 | Fixings | All fixings to be M16 galvanised fixed into concrete with chemset epoxy. | Shop Drawings | Dockets | Prior to Order | H | PE
4.01.03 | Grout | Cemix repair & patching grout for levelling pad or similar. |  | Dockets | Prior to Order | H | PE
SECTION 5 – CONSTRUCTION ACTIVITY
5.01 | Installation | Balustrades installed as per shop drawings. | Shop Drawings | Photos | Each area | H | PE
5.02 | Fixings | Minimum 50mm edge distance to centre of bolt to edge of concrete island. Set in place using chemset epoxy. Minimum 75mm embedment into concrete. | BBO | Photos | Each area | H | PE
5.03 | Grout Pad | Max 40mm height levelling mortar pad. Minimum thickness 1mm. | Shop Drawings | Photos | Each area | H | PE
5.04 | Reflective Tape | Install reflective stripe on entrance poles. | RITS D3.8.8 | Photos | Each area | H | PE
SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
6.01 | General
6.01.01 | Red-Line Markups | Red-line markups of any design changes. |  | Red-line markup | Upon completion | H | PE