## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - 139 - Balustrades | itp |  |  |  |  | ITP - 139 - Balustrades Rev B
section | SECTION 3 – PRE-CONSTRUCTION (P&G / ESTABLISHMENT)
checkpoint | 3.01.01 - Approved Shop Drawings
label | Acceptance / Conformance Criteria - Shop drawings have been approved by designer.
label | Standard / Specification - BBO
label | Verifying Document - Shop Drawings and Approval
label | Frequency - Prior to fabrication
label | Verification Activity: Activity - HP
label | Verification Activity: By - ENG
holdpoint | AUTHORITY HOLDPOINT
section | SECTION 4 – MATERIAL, PERSONNEL & THIRD PARTY APPROVAL
checkpoint | 4.01.01 - Balustrades
label | Acceptance / Conformance Criteria - Balustrades to be manufactured as per shop drawings.
label | Verifying Document - Shop drawings, Dockets, Galv Records
label | Frequency - Prior to Order
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.02 - Fixings
label | Acceptance / Conformance Criteria - All fixings to be M16 galvanised fixed into concrete with chemset epoxy.
label | Standard / Specification - Shop Drawings
label | Verifying Document - Dockets
label | Frequency - Prior to Order
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 4.01.03 - Grout
label | Acceptance / Conformance Criteria - Cemix repair & patching grout for levelling pad or similar.
label | Verifying Document - Dockets
label | Frequency - Prior to Order
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 5 – CONSTRUCTION ACTIVITY
checkpoint | 5.01 - Installation
label | Acceptance / Conformance Criteria - Balustrades installed as per shop drawings.
label | Standard / Specification - Shop Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 5.02 - Fixings
label | Acceptance / Conformance Criteria - Minimum 50mm edge distance to centre of bolt to edge of concrete island.
label | ○ Set in place using chemset epoxy.
label | ○ Minimum 75mm embedment into concrete.
label | Standard / Specification - BBO
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 5.03 - Grout Pad
label | Acceptance / Conformance Criteria - Max 40mm height levelling mortar pad. Minimum thickness 1mm.
label | Standard / Specification - Shop Drawings
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | 5.04 - Reflective Tape
label | Acceptance / Conformance Criteria - Install reflective stripe on entrance poles.
label | Standard / Specification - RITS D3.8.8
label | Verifying Document - Photos
label | Frequency - Each area
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
section | SECTION 6 – POST CONSTRUCTION (FINAL INSPECTION AND HANDOVER)
checkpoint | 6.01.01 - Red-Line Markups
label | Acceptance / Conformance Criteria - Red-line markups of any design changes.
label | Verifying Document - Red-line markup
label | Frequency - Upon completion
label | Verification Activity: Activity - H
label | Verification Activity: By - PE
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature