## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Overall Progress
Scope
Rows
|  | BASEMENT - DUCTWORK | grouping | BASEMENT - DUCTWORK
|  | Ductwork |  | BASEMENT | DUCTWORK:
|  | BASEMENT - FANS | dynamic | BASEMENT | FANS:
|  | BASEMENT - SITE QA | grouping | BASEMENT - SITE QA
|  | Site QA |  | BASEMENT | SITE QA
|  | GROUND FLOOR - DUCTWORK | grouping | GROUND FLOOR - DUCTWORK
|  | Ductwork |  | GROUND FLOOR | DUCTWORK:
|  | GROUND FLOOR - PIPEWORK | grouping | GROUND FLOOR - PIPEWORK
|  | Pipework |  | GROUND FLOOR | PIPEWORK:
|  | GROUND FLOOR - FCU UNITS | dynamic | GROUND FLOOR | FCU UNITS:
|  | GROUND FLOOR - FANS | dynamic | GROUND FLOOR | FANS:
|  | GROUND FLOOR - SITE QA | grouping | GROUND FLOOR - SITE QA
|  | Site QA |  | GROUND FLOOR | SITE QA
|  | LEVEL 1 - DUCTWORK | grouping | LEVEL 1 - DUCTWORK
|  | Ductwork |  | LEVEL 1 | DUCTWORK:
|  | LEVEL 1 - PIPEWORK | grouping | LEVEL 1 - PIPEWORK
|  | Pipework |  | LEVEL 1 | PIPEWORK:
|  | LEVEL 1 - FCU UNITS | dynamic | LEVEL 1 | FCU UNITS:
|  | LEVEL 1 - FANS | dynamic | LEVEL 1 | FANS:
|  | LEVEL 1 - VAVs | dynamic | LEVEL 1 | VAVs:
|  | LEVEL 1 - SITE QA | grouping | LEVEL 1 - SITE QA
|  | Site QA |  | LEVEL 1 | SITE QA
|  | ROOF | grouping | ROOF
|  | Roof |  | ROOF | ROOF:
Columns
|  | All Subbie Fit off & Testing Progression |  | All Subbie Fit off & Testing Progression
|  | All Subbie Rough-in Progression |  | All Subbie Rough-in Progression
|  | As Builts |  | As Builts
|  | Drains |  | Drains
|  | Ductwork |  | Ductwork
|  | Fan Coil Unit |  | Fan Coil Unit
|  | FANS: |  | FANS:
|  | Grille Fit-Off |  | Grille Fit-Off
|  | Indoor Equipment |  | Indoor Equipment
|  | Pipework |  | Pipework
|  | Pipework Testing |  | Pipework Testing
|  | Plantroom / Outdoor Equipment |  | Plantroom / Outdoor Equipment
|  | Pump |  | Pump
|  | VAV |  | VAV
Detailed Progress
Scope
Rows
|  | BASEMENT - DUCTWORK | grouping | BASEMENT - DUCTWORK
|  | Ductwork |  | BASEMENT | DUCTWORK:
|  | BASEMENT - FANS | dynamic | BASEMENT | FANS:
|  | BASEMENT - SITE QA | grouping | BASEMENT - SITE QA
|  | Site QA |  | BASEMENT | SITE QA
|  | GROUND FLOOR - DUCTWORK | grouping | GROUND FLOOR - DUCTWORK
|  | Ductwork |  | GROUND FLOOR | DUCTWORK:
|  | GROUND FLOOR - PIPEWORK | grouping | GROUND FLOOR - PIPEWORK
|  | Pipework |  | GROUND FLOOR | PIPEWORK:
|  | GROUND FLOOR - FCU UNITS | dynamic | GROUND FLOOR | FCU UNITS:
|  | GROUND FLOOR - FANS | dynamic | GROUND FLOOR | FANS:
|  | GROUND FLOOR - SITE QA | grouping | GROUND FLOOR - SITE QA
|  | Site QA |  | GROUND FLOOR | SITE QA
|  | LEVEL 1 - DUCTWORK | grouping | LEVEL 1 - DUCTWORK
|  | Ductwork |  | LEVEL 1 | DUCTWORK:
|  | LEVEL 1 - PIPEWORK | grouping | LEVEL 1 - PIPEWORK
|  | Pipework |  | LEVEL 1 | PIPEWORK:
|  | LEVEL 1 - FCU UNITS | dynamic | LEVEL 1 | FCU UNITS:
|  | LEVEL 1 - FANS | dynamic | LEVEL 1 | FANS:
|  | LEVEL 1 - VAVs | dynamic | LEVEL 1 | VAVs:
|  | LEVEL 1 - SITE QA | grouping | LEVEL 1 - SITE QA
|  | Site QA |  | LEVEL 1 | SITE QA
|  | ROOF | grouping | ROOF
|  | Roof |  | ROOF | ROOF:
Columns
|  | 24hr pipe pressure test |  | 24hr pipe pressure test (attach photo)
|  | Access to all relevant controls & isolators |  | Access to all relevant controls and isolators
|  | Access to all relevant controls, isolators & maintenance items |  | Access to all relevant controls, isolators and maintenance items
|  | Access to all valves & fittings is achievable |  | Access to all valves and fittings is achievable
|  | Access to fan & isolator |  | Access to fan and isolator
|  | Access to filter bank/filters installed |  | Access to filter bank / filters installed
|  | Access to VAV & controls |  | Access to VAV and controls
|  | Additional taping/sealing to medium/high pressure spiral |  | Additional taping/sealing to medium/high pressure spiral
|  | Adequate maintenance clearance maintained |  | Adequate maintenance clearance maintained
|  | Air bleeds installed in pipework where req. |  | Air bleeds installed in pipework where required
|  | Air filters installed |  | Air filters installed
|  | All joins welded/crimped as per manufacturer's instr. |  | All joins welded / crimped as per manufacturer's instructions
|  | All manufacturer specific reqs. have been provided in addition to project reqs. |  | All manufacturer specific requirements have been provided in addition to project requirements
|  | All work in zone completed & appear compliant |  | All work in zone completed and appear compliant
|  | Any req. ductwork leakage testing |  | Any required ductwork leakage testing
|  | Are all grilles installed correctly? Air leaks, vibration or failure |  | Are all grilles installed correctly? Air leaks, vibration or failure
|  | Balancing dampers installed as documented & left in the open position |  | Balancing dampers installed as documented and left in the open position
|  | BD pop access panel coordinated & marked |  | BD pop access panel coordinated and marked
|  | Blade dampers installed as documented & left in the open position |  | Blade dampers installed as documented and left in the open position
|  | Cleats installed as req. |  | Cleats installed as required
|  | Coil valves accessible & not blocking any service points |  | Coil valves accessible and not blocking any service points
|  | Coil valveset access panel coordinated & marked |  | Coil valveset access panel coordinated and marked
|  | Confirm correct CDW pipe work installed as per latest drawing |  | Confirm correct CDW pipe work installed as per latest drawing (e.g. Valves, binder points, air vents)
|  | Confirm correct electrical connections to the fan |  | Confirm correct electrical connections to the fan
|  | Confirm drain pipe taken to appriorate drain point |  | Confirm drain pipe taken to appriorate drain point
|  | Confirm ductwork connections to the fans are correct & include flexible connections |  | Confirm ductwork connections to the fans are correct and include flexible connections
|  | Confirm ductwork connections to the unit are correct |  | Confirm ductwork connections to the unit are correct
|  | Confirm electrical connection to pump |  | Confirm electrical connection to pump
|  | Confirm electrical connection to unit |  | Confirm electrical connection to unit
|  | Confirm installation of any dampers on the units |  | Confirm installation of any dampers on the units
|  | Confirm pipework connections to the pump are correct & include all fittings, valves & accessories as documented |  | Confirm pipework connections to the pump are correct and include all fittings, valves and accessories as documented
|  | Confirm safety tray and/or condensate drain provided to the units & is piped to adjacent waste point |  | Confirm safety tray and/ or condensate drain provided to the units and is piped to adjacent waste point
|  | Confirm safety tray provided with fall to drain point |  | Confirm safety tray provided with fall to drain point
|  | Confirm seismic bracing to reqs. |  | Confirm seismic bracing to requirements
|  | Confirm test points, sensors & gauges have been provided & installed as documented |  | Confirm test points, sensors and gauges have been provided and installed as documented
|  | Confirm test points, sensors & pressure points have been provided & installed as documented |  | Confirm test points, sensors and pressure points have been provided and installed as documented
|  | Confirm VSD is installed |  | Confirm VSD is installed
|  | Correct coil valves installed as per schedule |  | Correct coil valves installed as per schedule
|  | Correct fan installed as per latest drawing |  | Correct fan installed as per latest drawing
|  | Correct grille type installed |  | Correct grille type installed
|  | Correct hanger spacing/fall |  | Correct hanger spacing / fall
|  | Correct hanger spacing/supports installed |  | Correct hanger spacing / supports installed
|  | Correct hanger spacing/supports installed for flex |  | Correct hanger spacing / supports installed for flex
|  | Correct hanger spacing/supports installed for pipe runs |  | Correct hanger spacing / supports installed for pipe runs
|  | Correct hanger spacing/supports installed for spiral |  | Correct hanger spacing / supports installed for spiral
|  | Correct IDU installed as per latest drawing |  | Correct IDU installed as per latest drawing
|  | Correct VAV installed as per latest drawing |  | Correct VAV installed as per latest drawing
|  | Cushion boxes installed as per latest drawing |  | Cushion boxes installed as per latest drawing
|  | Damper access panels coordinated & marked |  | Damper access panels coordinated and marked
|  | Drain pipe insulated where req. |  | Drain pipe insulated where required
|  | Drain pipe is labelled clearly |  | Drain pipe is labelled clearly
|  | Drain pump installed level & tested |  | Drain pump installed level and tested
|  | Drain pump installed on a gradient/ level |  | Drain pump installed on a gradient/ level
|  | Drain terminates at a tundish |  | Drain terminates at a tundish
|  | Drain tested |  | Drain tested
|  | Drain trapped where req. |  | Drain trapped where required
|  | Drains, pump & tundish access for maintenance |  | Drains, pump and tundish access for maintenance
|  | Drains, pump & tundish access for maintenance. |  | Drains, pump and tundish access for maintenance.
|  | Duct flanges firmly bolted & sealed where req. |  | Duct flanges firmly bolted and sealed where required
|  | Ductwork restrained for wind/seismic where req. |  | Ductwork restrained for wind/seismic where required
|  | DW insulated where req. & damage free |  | DW insulated where required and damage free
|  | Fan connections secured & sealed |  | Fan connections secured and sealed
|  | Fan installed as per latest drawing |  | Fan installed as per latest drawing
|  | Fan is labelled clearly |  | Fan is labelled clearly
|  | FCU installed as per latest drawing |  | FCU installed as per latest drawing
|  | Fire dampers installed as per latest drawing/access panel in DW where req. |  | Fire dampers installed as per latest drawing / access panel in DW where required
|  | Flexible connections installed |  | Flexible connections installed
|  | Flexible connections installed & sealed |  | Flexible connections installed and sealed
|  | Flexible duct connections completed correctly |  | Flexible duct connections completed correctly
|  | Floor or Platform Mounted Thermal Plant correctly supported as per project engineering reqs. |  | Floor or Platform Mounted Thermal Plant correctly supported as per project engineering requirements
|  | Free from support off other services |  | Free from support off other services
|  | Grille color as per schedule |  | Grille color as per schedule
|  | Grille fit-Off completed to drawings/specification & Area left clean/tidy |  | Grille fit-Off completed to drawings/specification & Area left clean/tidy (Any Issues comment below)
|  | Grille installed flush & square |  | Grille installed flush and square
|  | Grille left clean of fingerprints & caps installed where req. |  | Grille left clean of fingerprints and caps installed where required
|  | Grilles installed in correct location as per latest duct layout/RCP |  | Grilles installed in correct location as per latest duct layout / RCP
|  | HHW Flushed - plan, photos of flow readings & water quality attached |  | HHW Flushed - plan, photos of flow readings and water quality attached
|  | HHW Pressure Test – ITR attached |  | HHW Pressure Test – ITR attached
|  | IDU access panel coordinated & marked |  | IDU access panel coordinated and marked
|  | Indoor Unit (IDU) correctly supported as per project engineering reqs. |  | Indoor Unit (IDU) correctly supported as per project engineering requirements
|  | Inertia base installed |  | Inertia base installed
|  | Initial pipe pressure test |  | Initial pipe pressure test (attach photo)
|  | Inspect the fan. Record & report for any issues |  | Inspect the fan. Record and report for any issues
|  | Inspect the unit casing is not damaged. Record & report for any issues |  | Inspect the unit casing is not damaged. Record and report for any issues
|  | Installed as per manufacturer's reqs. Refer to specific equipment schedule for detail |  | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail
|  | Installed as per manufacturer's reqs. Refer to specific equipment schedule for detail. |  | Installed as per manufacturer's requirements. Refer to specific equipment schedule for detail.
|  | Location of register coordinted with other services & marked on plan or floor |  | Location of register coordinted with other services and marked on plan or floor
|  | Maintenance & ventilation clearance maintained as per manufacturer's specs |  | Maintenance and ventilation clearance maintained as per manufacturer's specs
|  | Motorised dampers installed as per latest drawing/actuator fit off |  | Motorised dampers installed as per latest drawing / actuator fit off
|  | No other services suspended from pipework |  | No other services suspended from pipework
|  | Photos of ductwork correctly sealed through smoke wall & smoke damper |  | Photos of ductwork correctly sealed through smoke wall & smoke damper
|  | Pipe tested & recorded as per Pipe Testing ITP |  | Pipe tested and recorded as per Pipe Testing ITP
|  | Pipework installed as per latest drawings |  | Pipework installed as per latest drawings
|  | Pipework installed level & free of damage |  | Pipework installed level and free of damage
|  | Piping cleaned & flushed |  | Piping cleaned and flushed
|  | Pops & flex installed as per latest drawing |  | Pops & flex installed as per latest drawing
|  | Pump & pipe are indenpendently supported |  | Pump and pipe are indenpendently supported
|  | Pump base plate is grouted & bolted |  | Pump base plate is grouted and bolted
|  | Pump installed as per latest drawing |  | Pump installed as per latest drawing
|  | Pump is labelled clearly |  | Pump is labelled clearly
|  | Rectangular duct installed as per latest drawing |  | Rectangular duct installed as per latest drawing
|  | Riser or area branch valve access panel coordinated & marked |  | Riser or area branch valve access panel coordinated and marked
|  | Smoke dampers installed as per latest drawing/actuator fit off |  | Smoke dampers installed as per latest drawing / actuator fit off
|  | Spiral installed as per latest drawing |  | Spiral installed as per latest drawing
|  | Spiral insulated where req. & damage free |  | Spiral insulated where required and damage free
|  | Spiral joins sealed correctly |  | Spiral joins sealed correctly
|  | Test points, drains & bleeders installed where req. |  | Test points, drains and bleeders installed where required
|  | Unit complete with acoustic wrapping as per documented |  | Unit complete with acoustic wrapping as per documented
|  | Unit correctly supported as per documented |  | Unit correctly supported as per documented
|  | Unit installed as per latest drawing |  | Unit installed as per latest drawing
|  | Unit is labelled clearly |  | Unit is labelled clearly
|  | Update As-Built's of any known changes |  | Update As-Built's of any known changes
|  | VAV access panel coordinated & marked |  | VAV access panel coordinated and marked
|  | Ventilation fan access panel coordinated & marked |  | Ventilation fan access panel coordinated and marked
|  | Ventilation fan correctly supported as per project engineering reqs. |  | Ventilation fan correctly supported as per project engineering requirements
|  | Volume Control Dampers installed as per latest drawing |  | Volume Control Dampers installed as per latest drawing