## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-272-CIV-ADL-Site Clearing and Grubbing
ITP Description: |  | ADL-Site Clearing and Grubbing
Discipline (e.g. CIV/STR/RAIL: |  | 272-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-05-20
ITP created by: |  | Abhi Patel
ITP approved for use by: |  | Aldrin Guinchoma
Special Notes to ConQA Team :
Inspection & Test Plan - Site Clearing & Grubbing
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-05-20
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section 201 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 204 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
3 | Preliminaries - Documentations
3.1 | Environmental Controls | MRPA Environmental Management Plan | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified. | Visual | Where applicable, prior to starting Works | WP | Supervisor SE/PE/SPE | This ITP Signed-off
3.2 | Vegetation Removal Permit | MRPA Environmental Management Plan | Prior to removing any vegetation or habitat: i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits. A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works. ii. fence and sign all sites nominated as No-Go Zones. | Document Review Visual | Where applicable, prior to starting Works | HP* | Supervisor SE/PE/SPE | This ITP Signed-off Ecologist's Report Vegetation Removal Permit
4 | Pre-Construction Activities
4.1 | Survey Set-out / Limits of Work | IFC Drawings Section 201.03 | The limits of clearing and grubbing shall be: a. the limits defined on the IFC drawings b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains c. no more than the width required for completion of the Work under the Contract. | Measure Visual | Once, prior to starting Works | IP | Surveyor SE/PE/SPE | This ITP Signed-off
4.2 | Cultural Heritage and Areas of Significance | MRPA Environmental Management Plan Section 201.10 | Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing. Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended. Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage. | Document Review Visual | Where applicable, prior to starting Works | HP* | Surveyor SE/PE/SPE | This ITP Signed-off Cultural Heritage Report
5 | Construction Activities
5.1 | Stripping of Topsoil | IFC Drawings Section 204.05 | Topsoil shall be stripped for the full width of the formation. Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site. Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable. | Visual | Each Site | IP | Supervisor SE/PE/SPE | This ITP Signed-off
5.2 | Stockpiling | MRPA Environmental Management Plan Section 204.05 | Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways. If this clearance is not possible,additional protection shall be provided. Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable. | Visual | Where applicable, each Site | IP | Supervisor SE/PE/SPE | This ITP Signed-off
5.3 | Abandoned Services | IFC Drawings Excavation Permit Section 201.05 | Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done. Verify service is not likely to contain a hazardous material (sewage, asbestos pipe) Decommissioned services to be disposed of in a suitable manner. Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete. | Visual | Where applicable, each Site | IP | Supervisor SE/PE/SPE | This ITP Signed-off
5.4 | Clearing of Trees and Vegetation | IFC Drawings Section 201.04 | Clearing work shall not be undertaken outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used. | Visual | Where applicable, each Site | IP | Supervisor SE/PE/SPE | This ITP Signed-off
5.5 | Grubbing of Vegetation | IFC Drawings Section 201.05 Section 201.06 | In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment. Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort). Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed. | Visual | Where applicable, each Site | IP | Supervisor SE/PE/SPE | This ITP Signed-off
6 | Post-construction Activities
6.1 | Disposal of Materials & Vegetation | Section 201.07 | Salvagable material to be used wherever possible, the remainder is to be remove from site. Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments. Tree trunks and large branches shall be removed from the site. Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch. Attach: Delivery Dockets (for Items sent off Site) | Visual | Where applicable, each Site | IP | Supervisor SE/PE/SPE | This ITP Signed-off
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /