## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-274-CIV-ADL-Type A Fill - Road
ITP Description: |  | ADL-Type A Fill - Road
Discipline (e.g. CIV/STR/RAIL: |  | 274-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-05-21
ITP created by: |  | Abhi Patel
ITP approved for use by: |  | Aldrin Guinchoma
Special Notes to ConQA Team :
Inspection & Test Plan - Type A Fill - Road
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-05-21
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | IFC Drawings VicRoads Standard Section 176 VicRoads Section 204 Code of Practice RC500.20 Code of Practice RC500.5 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries-Materials
2.1 | Material Conformance | Section 204.04 b) Table 204.041 | Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter. Type A Material shall meet the followingPOST FIELD COMPACTION requirements as follows: Assigned CBR≥ 6% Swell ≤ 1.5% Permeability ≤ 5X10-9 m/s Grading: 75.0mm 100% 4.75mm 40-80% 0.075mm 10-40% PI Range: 6 to 25 PI x %passing o.425 mm: 1000 max Reference: Material approval in Teambinder: | Document Review | Once, for each material type | HP* | SE/Nominated Authority | Teambinder Material Approval
3 | Preliminaries-Documentations
3.1 | Pre-Commencement of Fill Works | Section 204.10 (b) | Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority. No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority Reference: Subgrade Preparation Lot Number: | Visual Inspection | Prior to commencement of fill works | HP | Nominated Authority | This ITP
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set Out | Design Drawings | Set out pegs in place and clearly mark out limits of works. ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP) | Visual Inspection | Each lot prior to commencement | HP* | PE | Signed ITP Lot Map
5 | Type A Fill/Verge Activities
5.1 | Placing of Fill | Section 204.10 | Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm. | Visual | Each Lot | WP | SE/Site Supervisor | Sign ITP
5.2 | Test Roll | Section 173.03 Section 204.12 | Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion. | Test Roll as per 173.03 | Each Lot/Layer | HP | Nominated Authority | Sign ITP
5.3 | Compaction Testing | Table 204.131 Section 204.14 c) Table 204.142 | Testing as per 204. Ensure testing is tracked and reports available. Standard Compactive Effort For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three. Compaction and Moisture content Scale A: Characteristic Density Ratio 99%. Scale B: Characteristic Density Ratio 98%. Scale C: Mean Value of Density Ratio: 100% Lot size - the leser of one day's production or 5,000sqm ATTACH: COMPACTION TEST RESULTS | Review Document | Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work | IP | SE/Site Supervisor | Sign ITP Attach Compaction Test Report
5.4 | Preparation of final surface | Section 204.15, 204.03 (g) | The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water). | Measure | Top layer | IP | SE/Site Supervisor | Signed ITP
6 | Post-construction Activities
6.2 | Survey Conformance | VicRoads 204.03f,g and h | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level. | Document Review | Top of Type A/Verge | IP | Surveyor SE/PE/SPE | This ITP Survey Conformance Report
6.3 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /