## res_ITP-217-CIV-HOP-Subgrade Pr
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-272-CIV-ADL-Site Clearing and Grubbing | itp |  |  |  |  | ITP-272-CIV-ADL-Site Clearing and Grubbing Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-272-CIV-ADL-Site Clearing and Grubbing
label | ITP Description: ADL-Site Clearing and Grubbing
label | Discipline (e.g. CIV/STR/RAIL): 272-CIV
label | Revision Number: 0
label | Revision Date: 20/05/2025
label | ITP created by: Abhi Patel
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 201
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 204
label | 1.3 - Non Dependent
label | Reference - IFC Drawings
section | 3. Preliminaries - Documentations
checkpoint | 3.1 - Environmental Controls
label | Reference - MRPA Environmental Management Plan
label | Acceptance Criteria - All environmental measures to be implemented as per current EMP and local authorities.
label | ○ Sediment control measures to be installed and protected vegetation to be clearly identified.
label | Method - Visual
label | Frequency - Where applicable, prior to starting Works
label | Category - WP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
checkpoint | 3.2 - Vegetation Removal Permit
label | Reference - MRPA Environmental Management Plan
label | Acceptance Criteria - Prior to removing any vegetation or habitat:
label | i. arrange an on-site inspection with the Nominated Authority and relevant authorities to confirm and clearly identify and mark trees, vegetation or habitat to be removed, consistent with the Design Documents and any relevant permits.
label | ○ A qualified ecologist with appropriate permits/licenses shall be present on site during removal of vegetation to identify possible locations of fauna, discovery of significant flora or fauna and to examine any habitats likely to be affected by Works.
label | ii. fence and sign all sites nominated as No-Go Zones.
label | Method - Document Review, Visual
label | Frequency - Where applicable, prior to starting Works
label | Category - HP*
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off, Ecologist's Report, Vegetation Removal Permit
date | Date Completed:
section | 4. Pre-Construction Activities
checkpoint | 4.1 - Survey Set-out / Limits of Work
label | Reference - IFC Drawings Section 201.03
label | Acceptance Criteria - The limits of clearing and grubbing shall be:
label | a. the limits defined on the IFC drawings
label | b. the whole width between the outside edges of any batters, including any roundings, together with a further horizontal distance of 1m beyond the outside edges of batters but not beyond the road reserve boundary or, where catch drains are required, to the outside edges of catch drains
label | c. no more than the width required for completion of the Work under the Contract.
label | Method - Measure, Visual
label | Frequency - Once, prior to starting Works
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
checkpoint | 4.2 - Cultural Heritage and Areas of Significance
label | Reference - MRPA Environmental Management Plan Section 201.10
label | Acceptance Criteria - Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | ○ Immediately notify the Nominated Authority if any Cultural Heritage is discovered or identified during construction and work to be suspended.
label | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | Method - Document Review, Visual
label | Frequency - Where applicable, prior to starting Works
label | Category - HP*
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off, Cultural Heritage Report
date | Date Completed:
section | 5. Construction Activities
checkpoint | 5.1 - Stripping of Topsoil
label | Reference - IFC Drawings Section 204.05
label | Acceptance Criteria - Topsoil shall be stripped for the full width of the formation.
label | ○ Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | Method - Visual
label | Frequency - Each Site
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
checkpoint | 5.2 - Stockpiling
label | Reference - MRPA Environmental Management Plan Section 204.05
label | Acceptance Criteria - Where soil is stock piled on Site, such stockpiles shall be located, where possible, to provide a clearance of not less than 10 metres from waterways.
label | ○ If this clearance is not possible,additional protection shall be provided.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water.
label | ○ Topsoil shall be re-spread as soon as practicable.
label | Method - Visual
label | Frequency - Where applicable, each Site
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
checkpoint | 5.3 - Abandoned Services
label | Reference - IFC Drawings Excavation Permit Section 201.05
label | Acceptance Criteria - Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works to be done.
label | ○ Verify service is not likely to contain a hazardous material (sewage, asbestos pipe)
label | ○ Decommissioned services to be disposed of in a suitable manner.
label | ○ Decommissioned pits have been broken back to 0.3m below subgrade level. Remaining pipe openings shall be sealed with concrete.
label | Method - Visual
label | Frequency - Where applicable, each Site
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
checkpoint | 5.4 - Clearing of Trees and Vegetation
label | Reference - IFC Drawings Section 201.04
label | Acceptance Criteria - Clearing work shall not be undertaken outside of the specified limits of work.
label | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | Method - Visual
label | Frequency - Where applicable, each Site
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
checkpoint | 5.5 - Grubbing of Vegetation
label | Reference - IFC Drawings Section 201.05, Section 201.06
label | Acceptance Criteria - In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3m below the subgrade and batters, whichever is the lesser treatment.
label | ○ In areas to be covered by embankments, grubbing to be a depth of not less than 0.3m below the stripped surface or not less than 0.6m below the finished surface of the subgrade, whichever is the lesser treatment.
label | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material and not less than density ratio of 95% (standard compactive effort).
label | ○ Unless otherwise shown on the drawings, trees and stumps within 10 m of any portion of a proposed bridge, or proposed culvert having a waterway area greater than 6 m2, shall be cleared and grubbed.
label | Method - Visual
label | Frequency - Where applicable, each Site
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.1 - Disposal of Materials & Vegetation
label | Reference - Section 201.07
label | Acceptance Criteria - Salvagable material to be used wherever possible, the remainder is to be remove from site.
label | ○ Salvagable concrete and bituminous materials greater than 50 mm shall be disposed of at approved recycling establishments.
label | ○ Tree trunks and large branches shall be removed from the site.
label | ○ Small tree branches,shrubs and leaves; excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch.
label | ○ Attach: Delivery Dockets (for Items sent off Site)
label | Method - Visual
label | Frequency - Where applicable, each Site
label | Category - IP
label | Responsibility - Supervisor, SE/PE/SPE
label | Verifying Documents - This ITP Signed-off
date | Date Completed:
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-273-CIV-ADL-Subgrade Preparation - Road | itp |  |  |  |  | ITP-273-CIV-ADL-Subgrade Preparation - Road Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-273-CIV-ADL-Subgrade Preparation - Road
label | ITP Description: ADL-Subgrade Preparation - Road
label | Discipline (e.g. CIV/STR/RAIL): 273-CIV
label | Revision Number: 0
label | Revision Date: 22/05/2025
label | ITP created by: Abhi Patel
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 - Non Dependent
label | Reference - VicRoads Section 204
label | 1.2 - Non Dependent
label | Reference - VicRoads Section 173
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Material Approval
label | Reference - VR 204.04 (C)
label | Acceptance Criteria - Type B material shall be totally free of organic content, topsoil, deleterious and/or perishable matter.
label | ○ Type B material shall have a minimum Assigned CBR of 2%, and Assigned Percent Swell less than 2.5% which has been determined in accordance with VicRoads Code of Practice RC 500.20.N/A
textbox | Enter: Teambinder Material Approval number
label | Method - Document Review
label | Frequency - Once, for each mix material
label | Category - HP*
label | Responsibility - Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
section | 3. Preliminaries-Documentations
checkpoint-no-value | 3.1 - Non Dependent
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set-Out
label | Reference - IFC Drawings
label | Acceptance Criteria - Area has been set out in accordance with the drawings
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP):
label | Method - Verify
label | Frequency - Prior to commencement of excavation
label | Category - IP
label | Responsibility - SE/Surveyor
label | Verifying Documents - This ITP
date | Date Completed:
section | 5. Construction / Installation Activities
checkpoint | 5.1 - Inspection of Subgrade Material-Subgrade Material Properties
label | Reference - Section 204.06 (C), Section 204.06 (e) IFC Drawings
label | Acceptance Criteria - Prior to commencing excavation in any area and during excavation work, the Nominated Authority and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
label | ○ In situ material within 400mm of cut floor level to be consistent with IFC Drawings
label | ○ Assigned CBR ≥ 2.5%
label | ○ If parameters are met, rip and re compact to a depth of 150mm.
label | ○ If assumed design parameters not met, remove 400mm of material and replace with conforming Type A fill.
label | ○ If existing material needs to be removed and replaced with Type A Fill, ITP-CIV Type A Fill - Road is to be utilised.
label | ○ Attach: Laboratory testing Verification:
textbox | Enter: Type A fill Lot Number:
label | Method - Verify-Document Review
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP/Test Report/Referenced Lot number
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.2 - Material classified as silt
label | Reference - Section 204.04 (b)
label | Acceptance Criteria - Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Nominated Authority
label | Method - Document Review
label | Frequency - Prior to commencing
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Superintendent satisfied with Stabilisation, Signed ITP/ records
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Acceptance of Rock Subgrade (where applicable)
label | Reference - Section 204.06 (f)
label | Acceptance Criteria - Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | Method - Site Inspection/ Document Review
label | Frequency - Prior construction of the regulating layer
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Unsuitable Material
label | Reference - Section 204.07 (d)
label | Acceptance Criteria - Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the Nominated Authority for review.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Groundwater
label | Reference - Section 204.06 h)
label | Acceptance Criteria - Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater.
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Cut to Fill Zones
label | Reference - Section 204.06 g)
label | Acceptance Criteria - All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type A material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type A material.
label | Method - Site Inspection
label | Frequency - Each lot
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.7 - Proof Roll
label | Reference - Section 173
label | Acceptance Criteria - Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | Method - Visual inspection
label | Frequency - Each lot
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.8 - Compaction Testing
label | Reference - Table 204.131
label | Acceptance Criteria - All Type A Material, Type B Material placed within 400 mm of top of Type B Material and
label | ○ Ripped and re-compacted material below Cut Floor Level
label | ○ Scale A: Characteristic Density Ratio 99%.
label | ○ Scale B: Characteristic Density Ratio 98%.
label | ○ Scale C: Mean Value of Density Ratio: 100%
label | ○ Attach: Compaction Test Result:
label | Method - Document Review
label | Frequency - Each lot
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Sign ITP, Attach Test Report
date | Date Completed:
checkpoint | 5.9 - Post Compaction Material Property Testing
label | Reference - Section 204.04 (C), Section 204.14 (a) and Table 204.141 For Scal A, Section 204.14 (b) for Scale B IFC Drawings
label | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
label | Scale A:
label | — CBR and Swell as per IFC for design packge:
label | — MRP-DPK-087-00-CDR-0002-0
label | — as per table VR 204.141
label | Scale B:
label | — CBR and Swell as per IFC for design packge:
label | — MRP-DPK-087-00-CDR-0002-0
label | First Lot for Max Particle Dimension:
label | — After compaction Type B material shall have a maximum particle dimension of not more than:
label | — 150 mm within 400 mm of the top of Type B material and 400 mm at depths greater than 400 mm below the top of Type B material.
label | ○ Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
label | ○ Attach: Post compaction test results:
label | Method - Review Document
label | Frequency - Refer to Section 204
label | Category - IP
label | Responsibility - PE/SE
label | Verifying Documents - Sign ITP, Attach Material Property Test Report
date | Date Completed:
section | 6. Post Construction Activities
checkpoint | 6.1 - Survey Conformance
label | Reference - VicRoads 204.03f,g and h
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | Level tolerances (Scale A):
label | — Range x = +5, -15mm
label | — Max S = 12 mm
label | — 80 measurements per lot
label | Level tolerances (Scale B):
label | — Range x = +5, -25mm
label | — Max S = 15 mm
label | — 40 measurements per lot
label | Level tolerances (Scale C):
label | — Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | Method - Review Document
label | Frequency - Each lot
label | Category - SCP
label | Responsibility - SE/Surveyor
label | Verifying Documents - Sign ITP, Attach Survey Report
date | Date Completed:
checkpoint | 6.2 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP
checklist | ITP-274-CIV-ADL-Type A Fill - Road | itp |  |  |  |  | ITP-274-CIV-ADL-Type A Fill - Road Rev 0
section | 1. Referenced Documentation
checkpoint-no-value | Referenced Documentation
label | Document Title: ITP-274-CIV-ADL-Type A Fill - Road
label | ITP Description: ADL-Type A Fill - Road
label | Discipline (e.g. CIV/STR/RAIL): 274-CIV
label | Revision Number: 0
label | Revision Date: 22/05/2025
label | ITP created by: Abhi Patel
label | ITP approved for use by: Aldrin Guinchoma
label | 1.1 - Non Dependent
label | Reference - IFC Drawings
label | ○ VicRoads Standard Section 176
label | ○ VicRoads Section 204
label | ○ Code of Practice RC500.20
label | ○ Code of Practice RC500.5
section | 2. Preliminaries-Materials
checkpoint | 2.1 - Material Conformance
label | Reference - Section 204.04 b) Table 204.041
label | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
label | Type A Material shall meet the followingPOST FIELD COMPACTION requirements as follows:
label | ○ Assigned CBR≥ 6%
label | ○ Swell ≤ 1.5%
label | ○ Permeability ≤ 5X10-9 m/s
label | ○ Grading:
label | — 75.0mm 100%
label | — 4.75mm 40-80%
label | — 0.075mm 10-40%
label | ○ PI Range: 6 to 25
label | ○ PI x %passing o.425 mm: 1000 max
textbox | Reference: Material approval in Teambinder:
label | Method - Document Review
label | Frequency - Once, for each material type
label | Category - HP*
label | Responsibility - SE/Nominated Authority
label | Verifying Documents - Teambinder Material Approval
date | Date Completed:
section | 3. Preliminaries-Documentations
checkpoint | 3.1 - Pre-Commencement of Fill Works
label | Reference - Section 204.10 (b)
label | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
label | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
label | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
textbox | Reference: Subgrade Preparation Lot Number:
label | Method - Visual Inspection
label | Frequency - Prior to commencement of fill works
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - This ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 4. Pre-construction / Pre-installation Activities
checkpoint | 4.1 - Survey Set Out
label | Reference - Design Drawings
label | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
label | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
label | Method - Visual Inspection
label | Frequency - Each lot prior to commencement
label | Category - HP*
label | Responsibility - PE
label | Verifying Documents - Signed ITP, Lot Map
date | Date Completed:
section | 5. Type A Fill/Verge Activities
checkpoint | 5.1 - Placing of Fill
label | Reference - Section 204.10
label | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
label | Method - Visual
label | Frequency - Each Lot
label | Category - WP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP
date | Date Completed:
checkpoint | 5.2 - Test Roll
label | Reference - Section 173.03, Section 204.12
label | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
label | Method - Test Roll as per 173.03
label | Frequency - Each Lot/Layer
label | Category - HP
label | Responsibility - Nominated Authority
label | Verifying Documents - Sign ITP
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.3 - Compaction Testing
label | Reference - Table 204.131, Section 204.14 c) Table 204.142
label | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
label | ○ Standard Compactive Effort
label | — For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
label | ○ Compaction and Moisture content
label | — Scale A: Characteristic Density Ratio 99%.
label | — Scale B: Characteristic Density Ratio 98%.
label | — Scale C: Mean Value of Density Ratio: 100%
label | ○ Lot size - the leser of one day's production or 5,000sqm
label | ○ ATTACH: COMPACTION TEST RESULTS
label | Method - Review Document
label | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Sign ITP, Attach Compaction Test Report
date | Date Completed:
checkpoint | 5.4 - Preparation of final surface
label | Reference - Section 204.15, 204.03 (g)
label | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
label | Method - Measure
label | Frequency - Top layer
label | Category - IP
label | Responsibility - SE/Site Supervisor
label | Verifying Documents - Signed ITP
date | Date Completed:
section | 6. Post-construction Activities
checkpoint | 6.2 - Survey Conformance
label | Reference - VicRoads 204.03f,g and h
label | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
label | ○ Level tolerances Scale C: Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
label | Method - Document Review
label | Frequency - Top of Type A/Verge
label | Category - IP
label | Responsibility - Surveyor, SE/PE/SPE
label | Verifying Documents - This ITP, Survey Conformance Report
date | Date Completed:
checkpoint | 6.3 - Non-conformance Report (NCR) Closure
label | Reference - MRPA Quality Management Plan
label | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | Method - Document Review
label | Frequency - Once, prior to closure of this lot / element / Work area
label | Category - HP*
label | Responsibility - SE/PE/SPE
label | Verifying Documents - This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP