## Sheet1
First Click/Main area | Second click/Sub area | Checklist Required
Prestart Inspections
| Floor and Lift Lobby | QA-Wall/floor prep
QA- Waterproofing
QA- Tiling Installation
QA- Other Information
QA - Final sign off for invoicing
| Amenities | QA-Wall/floor prep
QA- Waterproofing
QA- Tiling Installation
QA- Other Information
QA - Final sign off for invoicing
| Herringbone Timber | QA-Wall/floor prep
QA - Herringbone Installation
QA- Other Information
QA - Final sign off for invoicing
| TL01 | QA - Miscallaneous items
QA- Final Sign off for invoicing

## Sheet2
type | BNZ
checklist | Prestart Inspections
checkpoint | site has been cleaned in advance of our arrival on site
checkpoint | Walls are plumb and level
label | IMPORTANT
checkpoint | Tiling works running to programme - prior trades completed
checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
checkpoint | Data sheets, of products, are supplied on site with TA's
checkpoint | Inductions completed & Site Inspection checklist has been completed
checkpoint | All tools tagged and tested - (photo's required)
checkpoint | Tiler has current site safe - Input number and expiry
checkpoint | Tiler has correct PPE relevant to project.
checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
section | Wall/Floor Preparation
checkpoint | Is the area clean, and cleared, ready for necessary preparation
checkpoint | Are flanges installed at correct depth in accordance with specified wastes
checkpoint | Has screeding been completed to shower at correct height and falls with correct product
checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
Checklist | QA - Waterproofing
checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
checkpoint | Gaskets have been installed to floor flange and wall plumbing fittings
checkpoint | Correct waterproofing is supplied as per project specification.
checkpoint | Waterproofing coat # 1 applied to floors, upstand and walls (take photos)
checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
checkpoint | Flood tests, if required, undertaken and photos provided.
Checklist | QA - Tiling Installation - Floor & Lift Lobby
section | Tiling to floors/walls
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install 1200x600x20mm Panama Sonte Honed to floor
checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
checkpoint | Install Chinchilla Hones 70x300x20 to lift lobby walls upto 3M high
checkpoint | Install stone to stair threads, and risers as per details
checkpoint | Trim - Install approved trim to tile/matwell and tile/vinyl junctions
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Apply 6mm silicone movement joints for stone flooring 3.6-4.8 spacing
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Apply sealer to all floor stone and lift lobby walls stone
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
Checklist | QA - Tiling Installation - Amenities
section | Tiling to floors/walls
checkpoint | Tiles set out according to latest drawing - always check revisions on site
checkpoint | Specified product used with notched trowel or required product
checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Install 600x600 tiles to floors as per drawings
checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
checkpoint | Install 600x600 tiles to walls as per drawings
checkpoint | Grout nominated is the correct colour and applied evenly and correctly
checkpoint | Grout is consistent throughout and no missing grout.
checkpoint | Tiling completed, checked and Supervisor sign off
checkpoint | Silicone is completed to all tile junctions where required
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
Checkpoint | QA - Herringbone Timber
section | Timber Floor installation
checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
checkpoint | Installation of Herringbone Flooring as per drawing
checkpoint | Install trim to perimeter of herringbone floor
checkpoint | Area left clean & tidy
checkpoint | Builders clean completed
Checklist | QA-Other Information
section | Other Information
checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
checkpoint | change of details and or instructions
checkpoint | Site specific details to be added
checkpoint | Material Details - Notes to be added of materials used on site
Checklist | Final Sign Off for Invoicing
checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
Checklist | Miscellaneous Items
Sections | Miscellaneous Items
checkpoint | Supply & installation of all floor tactiles (TI01 x 4 areas) and trim thread insert to stone
checkpoint | Install Fantima Stone to demo'd wall as per mark up