## Project Structure
Folder Structure | Bosform | Project: Imperial Square | Checklist
Site QA
| Level / Area | Scope of Works
| SOG B-1 | Lift Over Run | Walls Checklist
|  | SOG Edge Boards | SOG Checklist
| B-1 | Columns | Columns Checklist
|  | Walls | Walls Checklist
|  | System | Climb Track Checklist
|  | Slab | Suspended Slab Checklist
|  | Stairs | Stairs Checklist
| Ground | Columns | Columns Checklist
|  | Walls | Walls Checklist
|  | System | Climb Track Checklist
|  | Slab | Suspended Slab Checklist
|  | Stairs | Stairs Checklist
|  | Hoist | Hoist Checklist
| Mezz Level | Columns | Columns Checklist
|  | Walls | Walls Checklist
|  | System | Climb Track Checklist
|  | Slab | Suspended Slab Checklist
|  | Stairs | Stairs Checklist
|  | Hoist | Hoist Checklist
| Level 1 | Columns | Columns Checklist
|  | Walls | Walls Checklist
|  | System | Climb Track Checklist
|  | Slab | Suspended Slab Checklist
|  | Stairs | Stairs Checklist
|  | Hoist | Hoist Checklist
| Level 2 | Columns | Columns Checklist
|  | Walls | Walls Checklist
|  | System | Climb Track Checklist
|  | Slab | Suspended Slab Checklist
|  | Stairs | Stairs Checklist
|  | Hoist | Hoist Checklist
| Level 3 | Columns | Columns Checklist
|  | Walls | Walls Checklist
|  | System | Climb Track Checklist
|  | Slab | Suspended Slab Checklist
|  | Stairs | Stairs Checklist
|  | Hoist | Hoist Checklist
| Level 4 - 17 | Columns | Columns Checklist
|  | Walls | Walls Checklist
|  | System | Climb Track Checklist
|  | Slab | Suspended Slab Checklist
|  | Stairs | Stairs Checklist
|  | Hoist | Hoist Checklist
| Roof | Core Walls | Walls Checklist
|  | Core lids | Core Lids Checklist
Ability to Add
Ability to Add
Ability to Add
Site Diary
Toolbox
Pre Start
Incident Report
Variations / SI
Progress Claim
2023-01-01
2023-02-01
2023-03-01
2023-04-01
2023-05-01
2023-06-01
2023-07-01
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01
2024-02-01
2024-03-01
2024-04-01
2024-05-01
2024-06-01

## Checklists
type | name | values
checklist | Columns Checklist
checkpoint | Area accessible & ready
checkpoint | Drawing references entered
text | Architectural
text | Structural
text | Other
text | Column No
checkpoint | Current plans in use / Latest drawings checked and referenced
checkpoint | Survey points given for 2 points
checkpoint | Datum RL supplied by surveyor, pour height marked
checkpoint | Blockouts, couplers, cast-in elements installed
holdpoint | Inspection from site engineer
checkpoint | Column box cleaned & oiled
checkpoint | Placement of column box over cage
checkpoint | Bracing props secured
checkpoint | Column plumbed
checkpoint | Correct class of finish
checklist | Suspended Slab Checklist
checkpoint | Area accessible & ready
checkpoint | Drawing references entered
checkpoint | Materials used complies with design documentation
checkpoint | Datum point used & soffit RLs checked
checkpoint | Grids marked by builder
checkpoint | Surveyor points given for outside of building
checkpoint | Fillet & drip mould installed
checkpoint | Check set down position & RL
checkpoint | Check penetrations installed
checkpoint | Prop drop head wedges are secure
checkpoint | Column blockouts installed
holdpoint | Inspection by site engineer
checkpoint | check back propping as per design
checkpoint | Blow off deck
holdpoint | Do not commence concrete till all works agreed
checkpoint | Engage external consultant (engineer inspection)
checkpoint | Correct Class of Finish
checkpoint | Stripping, cleaning & materials removed
checklist | Walls Checklist
checkpoint | Area accessible & ready
checkpoint | Drawing references entered
text | Architectural
text | Structural
text | Other
checkpoint | Current plans in use
checkpoint | Survey points given for 2 points
checkpoint | Land shutter bracing props secured plumb shutter
checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint | Blockouts steps penetrations marked & installed
checkpoint | Steel tied & clear from Z bar holes
checkpoint | Couplers & rebate boards installed
checkpoint | Base of walls cleaned
holdpoint | Inspection by site engineer
checkpoint | Closing shutter installed
checkpoint | Z bars secured wall straight & plumbed
checkpoint | Correct Class of Finish
checklist | Stairs Checklist
section | Phase 1
checkpoint | Area accessible & ready
checkpoint | Drawing references entered
text | Architectural
text | Structural
text | Other
checkpoint | Current plans in use
checkpoint | Land stringers & backdrops secured
checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint | Couplers & rebate boards installed
checkpoint | Base of stairs cleaned
checkpoint | Riser heights confirmed
checkpoint | Going lengths confirmed
checkpoint | Correct Class of Finish
section | Phase 2
checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint | Couplers & rebate boards installed
checkpoint | Base of stairs cleaned
checkpoint | Riser heights confirmed
checkpoint | Going lengths confirmed
checkpoint | Correct Class of Finish
checklist | Stairs (in-situ) Checklist
section | Phase 1
checkpoint | Area accessible & ready
checkpoint | Drawing references entered
text | Architectural
text | Structural
text | Other
checkpoint | Current plans in use
checkpoint | Land stringers & backdrops secured
checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint | Couplers & rebate boards installed
checkpoint | Base of stairs cleaned
checkpoint | Riser heights confirmed
checkpoint | Going lengths confirmed
checkpoint | Correct Class of Finish
section | Phase 2
checkpoint | Datum RL supplied by surveyor pour height marked
checkpoint | Couplers & rebate boards installed
checkpoint | Base of stairs cleaned
checkpoint | Riser heights confirmed
checkpoint | Going lengths confirmed
checkpoint | Correct Class of Finish
checklist | Core Lids Checklist
section | Phase 1
checkpoint | Area accessible & ready
checkpoint | Drawing references entered
text | Architectural
text | Structural
text | Other
checkpoint | Materials used complies with design documentation
checkpoint | Datum point used & soffit RLs checked
checkpoint | Grids marked by builder
checkpoint | Surveyor points given for outside of building
checkpoint | Fillet & drip mould installed
checkpoint | Check set down position & RL
checkpoint | Check penetrations installed
checkpoint | Column blockouts installed
section | Phase 2
checkpoint | Check back propping as per design
checkpoint | Blow off deck
holdpoint | Do not commence concrete till all works agreed
checkpoint | Engage external consultant (engineer inspection)
checkpoint | Correct Class of Finish
checkpoint | Stripping, cleaning & materials removed
checklist | S.O.G Checklist
checkpoint | Area accessible & ready
checkpoint | Drawing references entered
text | Architectural
text | Structural
text | Other
checkpoint | Current plans in use
checkpoint | Survey points give for grids
checkpoint | Surveyors points given for edge boards
checkpoint | Datum RL supplied by surveyor
checkpoint | Edge boards plumb & straight
checkpoint | Step downs secure & correct RL
checkpoint | Dowels installed on pour joins
checkpoint | Column blockouts installed
checkpoint | Correct Class of Finish
checklist | Variation / Site Instruction
checkpoint | Variation / SI Details Entered
label | Please take before photos
radio | Work type: | Site Instruction, Variation Work
text | Attention:
text | Area/Location
text | Date
text | Scope of work
text | Normal Hours
text | Overtime Hours
text | Material to complete task
checkpoint | Reference/SI Number Entered
text | Reference/SI Number
checkpoint | Variation / SI Work Completed
checkpoint | Values added (Office use only)
text | Labour Value
text | Material Value
text | Measured Items
text | Total Variation Value
checklist | Site Diary
checkpoint | Areas of work accessible for the day
select | Day | Monday, Tuesday, Wednesday, Thursday, Friday, Saturday, Sunday
text | Date
text | Year
text | Number of workers on site
text | HSR on site today enter name
text | First Aider on site today enter name
text | Injury on site today enter name
checkpoint-no-status | Work area 1 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Comments
checkpoint-no-status | Work area 2 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Comments
checkpoint-no-status | Work area 3 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Comments
checkpoint-no-status | Work area 4 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Comments
checkpoint-no-status | Work area 5 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Comments
checkpoint-no-status | Work area 6 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Comments
checkpoint-no-status | Work area 7 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Other
checkpoint-no-status | Work area 8 details entered
text | Area
select | Task | Columns, Framing, Deck, Walls, Cores, Stripping, Setdown, Upstand, Footings G/Slab, Other
text | Comments
checkpoint-no-status | Weather conditions entered
select | Conditions: | Fine, Overcast, Showers, Rain, Windy, Hot
text | Min temp predicted
text | Max temp predicted
checkpoint-no-status | Delays from inclemency
text | Total Hours of delay
select | Conditions: | Rain, Windy, Heat, Other trades,
checkpoint-no-status | Delays from Builders or Others
text | Total Hours of delay
select | Conditions: | Builder, Union, Crane, Scaffold, Steel fixer, PT, Concreter, Earthworks, Safety, Other
checklist | Injury Form
checkpoint | Injury form completed
text | Date of incident
text | Time
text | Site location of the accident / incident
text | Detail of how the accident / incident happened
label | Details of injured person
text | First name
text | Last name
text | DOB
text | Contact No
text | Address
text | Company
text | Trade
text | Date Inducted
select | Location of injury | Amputation, Bruise, Burn, Concussion, Deafness, Dislocation, Foreign Body, Fracture, Hernia, Inflammation / Infection, Internal Injury, Laceration / Cut, Occupational Illness, Open Wound, Poisoning / Toxic Effect, Strain / Sprain Twist
select | Location on body | Front, Back, Head, Neck, Torso, Left Hand, Left Arm, Right Hand, Right Arm, Left Leg, Left Foot, Right Leg, Right Foot, Other
select | Treatment | No First Aid Treatment, First Aid Treatment, Medical Treatment , Lost Time Injury, Fatal Injury
text | Initial treatment given
text | Was follow up treatment provided
text | Medical centre / Doctor / Hospital attended
text | Date / time attended
button | Regulator notified | Yes, No
label | Witness details
text | Witness name & contact details
text | Witness name & contact details
select | Event details / cause | Falls from height, Fall from same level, Hitting objects with body part, Exposure to mechanical vibration, Being hit by moving objects, Exposure to sharp sudden noise / long term noise, Exposure to extreme temps, Exposure to radiation, Exposure to biological factors, Exposure to mental stress factors, Vehicle accident, Muscular single / repetitive movement, Contact with electricity, Contact with toxic chemicals / substance, Other & multiple mechanisms of injury
text | Other
label | Injured worker: I confirm the information recorded in this register is to the best of my knowledge true & correct & I give consent for this information to be provided to Bosform for my incident investigation & reporting purposes
checkpoint | Signature of injured worker
checkpoint | Person completing this form
checklist | Toolbox Meeting
checkpoint | Toolbox signed off - Attach an forms
text | Work area
text | Supervisor
text | Date
text | Time am / pm
text | Actions from last meeting
text | Injuries last week
text | Near misses last week
text | Safety Items discussed
text | Comments from the floor
text | New business
text | Attendees
checkpoint | Attendance verified
checklist | Daily Pre Start
checkpoint | Daily pre start meeting completed
text | Date
text | Time
text | Location
text | Supervisor / meeting leader
text | Project Manager & Construction Supervisor attending
select | Current weather | Rain, Wind
text | Temp
select | Forecast | Rain, Wind
text | Temp
button | Is everyone fit, well & healthy, not showing any flu like symptoms | Yes, No
button | Have any workers travelled interstate or been in close contact with anyone with a positive COVID 19 test | Yes, No
text | Any issues from the previous day
button | Do you need to change SWMS
text | First aiders on site today
text | Apprentice & who are they assigned to
text | Apprentice & who are they assigned to
text | Apprentice & who are they assigned to
text | Todays tasks / jobs
select | SWMS name & number | 02 Ground works, 03, Hand & power tools, 04 Operating generator, 05 Compressor, 06 Columns, 07 Walls, 09 EWP, 10 Loading / unloading trucks, 11 Manitou forklift, 12 Weld oxy, 13 Patching, 15 Stair / lift core, 17 Meva system, 18 Faresin system, 19 Conventional formwork, 21 Peri system, 23 Catch deck, 24 Pallet trolley
button | SWMS in place for all activities | Yes, No
button | Hot works | Yes, No
button | Excavation | Yes, No
button | Ladder | Yes, No
button | Core | Yes, No
button | Are any hazardous substances being used or will be brought to / or stored on site today | Yes, No
text | If yes, list the substances
text | Attendees
checklist | Jump System / Climb Track Checklist
section | Pre Lift
checkpoint | Confirm concrete strength MPA 15 has been reached at connection points (Builder to supply)
checkpoint | Signage in place (Stripping in progress/Jumping in progress/ No access)
checkpoint | Exclusion Zone in place
checkpoint | Spotters in place on slab below jump (outside exclusion zone)
checkpoint | All Platforms cleaned and clear from rubbish
checkpoint | All loose materials removed from edge
checkpoint | Clear communication between team leaders and Crane crew (toolbox talk)
checkpoint | Ladders available and secured
checkpoint | Flipper systems lubricated
checkpoint | Trailing Decks clean of debris
checkpoint | Trailing decks clear of protruding ferrals in walls above
checkpoint | Check exclusion zones in pit below are in place
checkpoint | Plumber to check pipes to water cooler
checkpoint | Transfer RL heights
section | Post Lift
checkpoint | Confirm connection points are secure and all engaged
checkpoint | Confirm mesh secured to doors and penetrations
checkpoint | Signage in place
checkpoint | Screens and mesh infills are in place and secure
checkpoint | Loose materials are stacked and secure each day
checkpoint | Platforms cleaned and clear from rubbish
checkpoint | All loose materials removed from edge
checkpoint | Loads on platforms not exceeded
checkpoint | Ladders available and secured
checkpoint | Access is clear and marked
checkpoint | Power Board connected
checkpoint | Confirm ready for lift with all involved - Team Leaders
checklist | Screens
section | Pre Lift
checkpoint | Area accessible & ready
text | Screen number
checkpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint | Signage in place
checkpoint | Exclusion Zone with name and number of supervisor– Ground level and Slab level
checkpoint | Spotters in place
checkpoint | WMS ready and signed on to
checkpoint | Platforms cleaned and clear from rubbish
checkpoint | All loose materials removed from edge
checkpoint | Edge protection installed on Level/s to be exposed once lifted
checkpoint | Deflector shields removed
checkpoint | Radio communication woking between screen crew
checkpoint | Hydraulic lifting Apparatus installed correctly if using lifter
checkpoint | Screen Free from Debris
checkpoint | All wire infills detached
checkpoint | Confirm ready for lift with all involved - Team Leader
checkpoint | Work at heights permit completed - attach or take photo of permit
section | Post Lift
checkpoint | Ensure all gaps are closed
checkpoint | Mesh to be install where required
checkpoint | Double check all needles are secure and double nuts in place
checkpoint | Clean and clear area
checkpoint | Remove exclusion zones and barricades
checkpoint | Bar caps for protruding z bars
checklist | Hoist
section | Install
checkpoint | Area accessible & ready to receive hoist
text | Hoist ID. Number
checkpoint | Adequate Crane or Franna to install (heaviest lift required 4.5 tonne)
button | Copy the Certificate of service and service history onsite
text | Name and Number of Rigger
checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
holdpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint | Scaffolder on site to assist in edge protection if required
checkpoint | Signage in place
button | 3 Phase power accessible and adequate circuit breaker 75 start Amps at power sorce
checkpoint | Exclusion Zone around required area
checkpoint | WMS ready and signed on to
checkpoint | Platforms cleaned and clear from rubbish
checkpoint | All loose materials removed from edge
checkpoint | Gates installed
holdpoint | Copy of Engineered Bracing plan for ties back to building on site and followed
checkpoint | Log book for hoist is onsite and in good condition
button | Copy of Bosform commissioning sheet on site and completed
section | Hoist Jump and Dismantle
checkpoint | Ensure exclusion zones are in place
checkpoint | Platforms cleaned and clear from rubbish
checkpoint | All loose materials removed from edge
text | Name and Number of Rigger
checkpoint | Work at heights permit completed - attach or take photo of permit if required for project
checkpoint | Scaffolder on site to assist in edge protection if required
text | Level Number to be Jumped to
checkpoint | Gates installed on Level/s to be exposed once lifted
holdpoint | Confirm concrete strength MPA 25 has been reached at supporting level
checkpoint | Signage in place
holdpoint | Copy of Engineered Bracing plan for ties back to building on site and followed
button | Hoist Screen installed if required
checkpoint | Remove exclusion zones and barricades
checklist | Deck Handover
checkpoint | Communication between all trades
checkpoint | Signage and barricades in place
checkpoint | Deck clean and clear of materials
checkpoint | Loose materials are stacked and secure
checkpoint | Any backpropping required to handle loads of reo and other equipment
checkpoint | Designated walkways established
checkpoint | All loose materials removed from edge
checkpoint | Are all penetrations covered and secured
checkpoint | Rubbish bin on Deck
checkpoint | Perimeter Screens / Edge protection installed
checkpoint | Correct spacing of frames, props and timbers
checkpoint | Correct joist and bearer sizes
checkpoint | Acceptable jack extensions
checkpoint | Quality of materials
checkpoint | Adequate bracing to ensure stability
signoff | Deck Handover signed off
type | name | values
checklist-flat | Weekly Labour Hire Control
checkpoint | Tuesday
text | Date
text | General Comments
Checkpoint | Wednesday
text | Date
text | General Comments
Checkpoint | Thursday
text | Date
text | General Comments
Checkpoint | Friday
text | Date
text | General Comments
Checkpoint | Saturday
text | Date
text | General Comments
Checkpoint | Monday
text | Date
text | General Comments
Checkpoint | Tuesday
text | Date
text | General Comments
checkpoint | Please Attach Time Sheet
signoff | Client Confirmation Signature
type | name | value
checklist-flat | Progress Claim Checklists
checkpoint | Please add Comments / Photos
select | General | Site Establishment / Prefab, Systems
select | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes
checkpoint | Please add Comments / Photos
select | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes
checkpoint | Please add Comments / Photos
select | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes
checkpoint | Please add Comments / Photos
select | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes
checkpoint | Please add Comments / Photos
select | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes
checkpoint | Please add Comments / Photos
select | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | Formed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Stripped | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Patched | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes
checkpoint | Please add Comments / Photos
select | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes
checkpoint | Please add Comments / Photos
select | Level | Below SOG, SOG, Basement 1,Ground, 1, 2, 3, 4 - 17, Roof Plant Deck
select | Description of Works | General, Submissions Site Establishment Design Off Site Fabrication including Design & Commissioning, Ground Works, Formwork to Lift Over Runs Pit Walls, Formwork to CJ'S, Spoon Drain & Step Downs, Formwork to Capping Beam, Formwork to Columns, Formwork to Vertical Walls, Formwork to Suspended Slab,Step-downs Rebates etc, Quick Stair System including Handrails and wreathing (Fire Stairs Only), Supply of Material Hoist & Maintenance , Install & Removal of Hoist, Supply of Climb Trac / Climb System , Install & Removal of Systems.
select | Completed | N/A, 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
text | General Notes

## Sheet3
type | name | values
checklist-flat | Progress Claim Checklists
checkpoint | Comments / Photo's
text | Description of Works
select | Formed | 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Stripped | 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%
select | Patched | 5%, 10%, 15%, 20%, 25%, 30%, 35%, 40%, 45%, 50%, 55%, 60%, 65%, 70%, 75%, 80%, 85%, 90%, 95%, 100%