## Table 1
| TASK | SPECIFICATION REFERENCE | TEST REQUIRED | TASK TIMING OR TASK FREQUNECY & MINIMUM REQUIREMENTS |  | TASK ASSIGNED TO | MEASURING DEVICES OR METHOD | ACCEPTANCE CRITERIA | QUALITY DOCUMENTATION | DOCUMENTATION RECEIVED |  | FREQUENCY ACHIEVED |  | ACCEPTANCE CRITERIA ACHIEVED
[10 empty] | DATE | SIGNATURE | DATE | SIGNATURE | DATE | SIGNATURE
1 | PRECONSTRUCTION HOLD POINTS
1.1 | Agree QA Requirements | ITP | Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing | Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
1.2 | Confirm Pricing for Additional Items | NTP | Pricing for additional items to be submitted to Design Project Manager and approved | Prior to construction handover meeting. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
1.3 | Construction Handover Meeting | NTP | Meeting | Minimum 2 weeks prior to commencement of physical works. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
1.4 | Physical works Programme | NTP | Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Bryan Crean and start and end dates to by updated in RAMM Contractor prior to physical works. | Minimum 10 working days prior to commencement of physical works. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
1.5 | Quantity Review | NTP | Confirm construction set-out and drawings align with quantities provided in schedule of quantities | After construction set-out, prior to commencement of physical works. |  | Construction Project Manager | - | Confirmation received by Delivery Manager by scheduled task timing
1.6 | Existing Pavement Walkover | NTP | Visual Inspection of existing pavement | Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength. |  | Construction Project Manager | Eye, spray paint, mark-up on drawings | Confirmation received by Delivery Manager by scheduled task timing | Mark-up on drawings
2 | SUBBASE MATERIAL TESTING
2.1 | Crushing Strength | Design | Crushing Resistance Test | 1 test per 10,000m3 (min 1 test) - 1 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.10 | <10% fines passing 2.36mm under 110 KN load | IANZ Test report
2.2 | Weathering Quality | Design | Weathering Quality Index Test | 1 test per 10,000m3 (min 1 test) - 1 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.11 | AA, AB, AC, BA, BB or CA | IANZ Test report
2.3 | Soaked CBR | Design | Remoulded soaked CBR | 1 sample per 500m3 - 1 tests |  | IANZ accredited laboratory | Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15 | ≥ 80% | IANZ Test report
2.4 | Sand equivalent | WBOPDC DC 2009 | String line or equivalent | 1 sample per 500m3 - 1 tests |  | IANZ accredited laboratory | NZS4407 : 1991, Test 3.6 | ≥ 40 (unless agreed otherwise with Paul Anderson) | IANZ Test report
2.5 | Particle size distribution | Design | Wet sieving test | 1 sample per 500m3 - 1 tests (1 test on same sample as MDD/OMC curve) |  | IANZ accredited laboratory | NZS4407 4407 : 1991, Test 3.8.1 | 100% passing 63mm 55 – 80% passing 37.5mm 35 – 65% passing 19mm 20 – 50% passing 9.5mm 10 – 35% passing 4.75mm 2 – 20% passing 1.18mm ≤6% passing 75micron | IANZ Test report
2.6 | Solid Density | TNZ B/2 7.5 | Solid Density | 1 test |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.7 | report value only | IANZ Test report
2.7 | Determination of MDD & OWC | TNZ B/2 7.5 | 5 point compaction curve | 1 test per 5000m2 - 1 tests |  | IANZ accredited laboratory | NZS 4402 : 1986, Test 4.1.3 | report value only | IANZ Test report
3 | SUBBASE LAYER CONSTRUCTION
3.1 | Formation | TNZ B/2 7.7 | 3m straight edge or approved equivalent | 20m centres each side - 38 Tests |  | Pavement subcontractor quality representative | 3m straight edge, tape measure | +/- 10mm | Inspection checklist
3.2 | Finished Level | TNZ B/2 5.1 | String line or equivalent | 20m centres each side - 38 Tests |  | Pavement subcontractor quality representative | Stringline, tape measure | +5mm / -25mm | Inspection checklist
3.3 | Compaction | TNZ B/2 7.6 | NDM | min 5 tests per lot (max lot size = 1,000m2) - 7 tests |  | IANZ accredited laboratory | NDM | Mean ≥ 95% MDD, Min ≥ 92%, Total voids ≤ 20% | IANZ Test report
4 | BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
4.1 | Crushing Strength | TNZ M/4 3.3.1 | Crushing Resistance Test | 1 test per 10,000m3 (min 1 per source) - 1 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.10 | <10% fines passing 2.36mm under 130 KN load | IANZ Report
4.2 | Weathering Quality | TNZ M/4 3.3.2 | Weathering Quality Index Test | 1 test per 10,000m3 (min 1 per source) - 1 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.11 | AA, AB, AC, BA, BB or CA | IANZ Report
4.3 | Soaked CBR | TNZ M/4 3.3.3 | Remoulded soaked CBR | 1 test per 10,000m3 (min 1 per source) - 1 tests |  | IANZ accredited laboratory | Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15 | ≥ 80% | IANZ Report
4.4 | Sand equivalent | TNZ M/4 4.2.1.1 | Sand equivalent | 0-400m3=2 tests; 400- 1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3 | 2 Tests | IANZ accredited laboratory | NZS4407 : 1991, Test 3.6 | ≥ 40 | IANZ Report
4.5 | Broken Faces Content | TNZ M/4 4.2.2 | Broken face content |  | 2 Tests. n.b. not required if sourced from 100% crushed rock quarry | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.14 | ≥ 70% | IANZ Report
4.6 | Particle size distribution | Design | Wet sieving test |  | 2 Tests (1 test must be from same sample as MDD/OMC test) | IANZ accredited laboratory | NZS4407 4407 : 1991, Test 3.8.1 | 100% passing 37.5mm 66 - 81% passing 19mm 43 - 57 passing 9.5mm 28 - 43 passing 4.75mm 19 - 33 passing 2.36mm 12 - 25 passing 1.18mm 7 - 19 passing 600µm 3 - 14 passing 300µm 0 - 10 passing 150µm 0 - 7 passing 75µm | IANZ Report
4.7 | Solid Density | TNZ B/2 7.5 | Solid Density | 1 test per 5000m2 - 1 tests |  | IANZ accredited laboratory | NZS 4407 : 1991, Test 3.7 | report value only | IANZ Report
4.8 | Determination of MDD & OWC | TNZ B/2 7.5 | 5 point compaction curve | 1 test per 5000m2 - 1 tests |  | IANZ accredited laboratory | NZS 4402 : 1986, Test 4.1.3 | report value only | IANZ Report
5 | BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
5.1 | Formation | TNZ B/2 7.7 | 3m straight edge or approved equivalent | 20m centres each side - 38 Tests |  | Pavement subcontractor quality representative | 3m straight edge, tape measure | +/- 10mm | Inspection checklist
5.2 | Finished Level | TNZ B/2 5.1 | String line or equivalent | 20m centres each side - 38 Tests |  | Pavement subcontractor quality representative | Stringline, tape measure | +15mm / -5mm | Inspection checklist
5.3 | Plateau Density Test | TNZ B/2 7.5 (b) | Plateau Density Test | 1 test minimum |  | IANZ accredited laboratory | NDM | report value only | IANZ Report
5.4 | Compaction | TNZ B/2 7.6 | NDM | min 5 tests per lot (max lot size = 1,000m2) - 7 tests |  | IANZ accredited laboratory | NDM | Mean ≥ 98% MDD or Plateau Density Test, Min ≥ 95%, Total voids ≤ 20% | IANZ Report
5.5 | Compaction - Feather Edge | TNZ B/2 8 | Visual Inspection | Inspect full length each side |  | Pavement subcontractor quality representative | truck with 4 tonne wheel load | the surface shall be able to withstand a moving wheel load of up to 4 tonnes without displacement | Inspection checklist
5.6 | Degree of Saturation | TNZ B/2 12 | NDM | min 5 tests per lot (max lot size = 1,000m2) - 7 tests |  | IANZ accredited laboratory | NDM | < 60% (or 80% on consultation with the pavement designer) | IANZ Report
5.7 | Surface Finish | TNZ B/2 7.8 | Visual Inspection | 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. |  | Pavement subcontractor quality representative | Stiff bristled broom, camera, eye | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which; • The large aggregate is • exposed to the surface; • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material; • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter. | Inspection checklist and photographs supplied electronically.
5.8 | Ride Quality | Internal measure | Ride quality test to AG:AM/T002 | Prior to sealing |  | WestLink will pay for NAASRA after sweeping before sealing. To be arranged by contractor. | inertial laser profiler or response-type roughness meter | no 100m moving average > 65 counts | Certified test report
6 | BITUMEN - TO GAIN APPROVAL
6.1 | Penetration | TNZ M/1 Table 1 | Penetration at 25°C, 100g, five seconds | 1 test |  | IANZ accredited laboratory | ASTM D5 | Complies with requirements for penetration grade as per TNZ M/01 Table 1 | Letter of compliance from NZTA
6.2 | Viscosity | TNZ M/1 Table 1 | Viscosity PaS at 60°C | 1 test |  | IANZ accredited laboratory | AS 2341.2 or ASM D2171 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
6.3 |  | TNZ M/1 Table 1 | Viscosity mm2/s at 135°C | 1 test |  | IANZ accredited laboratory | AS 2341.3 or ASM D2170 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
6.4 | Flash Point | TNZ M/1 Table 1 | Flash point (Cleveland open cup), °C | 1 test |  | IANZ accredited laboratory | ASTM D92 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
| TASK | SPECIFICATION | TEST REQUIRED | TASK TIMING OR TASK FREQUNECY & MINIMUM REQUIREMENTS |  | TASK ASSIGNED TO | MEASURING DEVICES OR | ACCEPTANCE CRITERIA | QUALITY DOCUMENTATION | DOCUMENTATION RECEIVED |  | FREQUENCY ACHIEVED |  | ACCEPTANCE CRITERIA ACHIEVED
6.5 | Solubility | REFERENCE TNZ M/1 Table 1 | Solubility in Trichloroethylene, % or Solubility in Toluene, % | 1 test |  | IANZ accredited laboratory | METHOD ASTM D2042, AS 2341.8 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
6.6 | Rolling Thin Film | TNZ M/1 Table 1 | Rolling Thin Film Oven Test | 1 test |  | IANZ accredited laboratory | ASTM D2872 or AS 2341.10
6.7 | Penetration | TNZ M/1 Table 1 | Penetration of residue, at 25°C, 100g, five seconds, % of original | 1 test |  | IANZ accredited laboratory | ASTM D5 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
6.8 | Ductility | TNZ M/1 Table 1 | Ductility of residue, at 25°C, (metres) | 1 test |  | IANZ accredited laboratory | ASTM D113 | Complies with requirements for penetration grade as per TNZ M/01 Table 1
7 | SEALING CHIP MATERIAL TESTING
7.1 | Crushing Strength | TNZ M/6 3.2 | Crushing Resistance Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.10 | <10% fines passing 2.36mm under 230 KN load | IANZ Test report
7.2 | Weathering Quality | TNZ M/6 3.3 | Weathering Quality Index Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.11 | AA or BA | IANZ Test report
7.3 | Weak Particles Test | TNZ M/6 3.4 | Australian Weak Particles Test | Only undertaken in cases of dispute |  | IANZ accredited laboratory | AS 1141.32-1995 | Maximum of 1% | IANZ Test report
7.4 | Polished Stone Value | TNZ M/6 3.5 | Polished Stone Value Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality |  | Accredited PSV Testing Agency | BS 812: Part 114 | PSV Required = 43 | IANZ Test report
7.5 | Cleanliness | TNZ M/6 4.1.1 | Cleanliness Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.9 | Grade 2 - 89 min Grade 3 - 87 min Grade 4 - 85 min | IANZ Test report
7.6 | Size & Shape | TNZ M/6 4.1.2 | Size & Shape | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.13 | Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD 1.1% passing 4.75mm | IANZ Test report
7.7 | Broken Faces | TNZ M/6 4.1.2 | Broken Faces Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.14 | 98% with minimum two broken faces | IANZ Test report
7.8 | Grading | TNZ M/6 4.2.2 | Grading | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805) |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.8 | Grade 5 100% passing 13.2mm 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm Grade 6 100% passing 9.5mm 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm | IANZ Test report
7.9 | Cleanliness | TNZ M/6 4.2.3 | Cleanliness Test | Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality |  | IANZ accredited laboratory | NZS 4407:1991, Test 3.9 | Report Value Only | IANZ Test report
8 | SEAL DESIGN
8.1 | Seal design | TNZ P/3 | Seal design | 2 weeks Prior to sealing |  | Contractor's Quality Manager | report only | report only | Seal design
8.2 | Seal design approval | Internal measure | Internal verification | 2 weeks Prior to sealing |  | Downer Surfacing Expert | report only | report only | Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
8.3 | Surface Finish | TNZ B/2 7.8 | Visual Inspection | 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale. |  | Sealing subcontractor quality representative | Stiff bristled broom, camera, eye | The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which; • The large aggregate is • exposed to the surface; • held in place with a matrix of smaller aggregates • The smaller aggregate is held firmly in place by fine material; • The matrix does not displace under normal trafficking or sweeping. The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter. | Inspection checklist and photographs supplied electronically.
9 | SEALING RECORDS
9.1 | Blend sheet | Client request |  | On day of seal |  | Bitumen blending facility |  | Report value only | Blend sheet
9.2 | Spray sheets | Client request |  | On day of seal |  | Sealing Manager |  | Report value only | Spray sheets