## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Arawa Rd Smoothings | [5 empty] | ITP - Arawa Rd Smoothings
section | 1.0 - PRECONSTRUCTION HOLD POINTS
checkpoint | 1.1 - Agree QA Requirements
label | SPECIFICATION REFERENCE - ITP
label | TEST REQUIRED - Check pricing and ITPs & notify Westlink of any difference in understanding of tender pricing
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Review ITP and confirm minimum quality requirements are understood prior to construction handover meeting.
label | TASK ASSIGNED TO - Construction Project Manager
label | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint | 1.2 - Confirm Pricing for Additional Items
label | SPECIFICATION REFERENCE - NTP
label | TEST REQUIRED - Pricing for additional items to be submitted to Design Project Manager and approved
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to construction handover meeting.
label | TASK ASSIGNED TO - Construction Project Manager
label | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint | 1.3 - Construction Handover Meeting
label | SPECIFICATION REFERENCE - NTP
label | TEST REQUIRED - Meeting
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 2 weeks prior to commencement of physical works.
label | TASK ASSIGNED TO - Construction Project Manager
label | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint | 1.4 - Physical works Programme
label | SPECIFICATION REFERENCE - NTP
label | TEST REQUIRED - Physical works Programme to be uploaded to WestLink Sharepoint site, emailed to Bryan Crean and start and end dates to by updated in RAMM Contractor prior to physical works.
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Minimum 10 working days prior to commencement of physical works.
label | TASK ASSIGNED TO - Construction Project Manager
label | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint | 1.5 - Quantity Review
label | SPECIFICATION REFERENCE - NTP
label | TEST REQUIRED - Confirm construction set-out and drawings align with quantities provided in schedule of quantities
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - After construction set-out, prior to commencement of physical works.
label | TASK ASSIGNED TO - Construction Project Manager
label | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
checkpoint | 1.6 - Existing Pavement Walkover
label | SPECIFICATION REFERENCE - NTP
label | TEST REQUIRED - Visual Inspection of existing pavement
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to ripping seal construction. Site walkover between WestLink Delivery Manager and Construction Project Manager to identify and agree any isolated treatments required in existing pavement to normalise strength.
label | TASK ASSIGNED TO - Construction Project Manager
label | MEASURING DEVICES OR METHOD - Eye, spray paint, mark-up on drawings
label | ACCEPTANCE CRITERIA - Confirmation received by Delivery Manager by scheduled task timing
label | QUALITY DOCUMENTATION - Mark-up on drawings
section | 2.0 - SUBBASE MATERIAL TESTING
checkpoint | 2.1 - Crushing Strength
label | SPECIFICATION REFERENCE - Design
label | TEST REQUIRED - Crushing Resistance Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 test) - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 110 KN load
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 2.2 - Weathering Quality
label | SPECIFICATION REFERENCE - Design
label | TEST REQUIRED - Weathering Quality Index Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 test) - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 2.3 - Soaked CBR
label | SPECIFICATION REFERENCE - Design
label | TEST REQUIRED - Remoulded soaked CBR
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 500m3 - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | ACCEPTANCE CRITERIA - ≥ 80%
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 2.4 - Sand equivalent
label | SPECIFICATION REFERENCE - WBOPDC DC 2009
label | TEST REQUIRED - String line or equivalent
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 500m3 - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | ACCEPTANCE CRITERIA - ≥ 40 (unless agreed otherwise with Paul Anderson)
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 2.5 - Particle size distribution
label | SPECIFICATION REFERENCE - Design
label | TEST REQUIRED - Wet sieving test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 sample per 500m3 - 1 tests (1 test on same sample as MDD/OMC curve)
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | ACCEPTANCE CRITERIA -
label | • 100% passing 63mm
label | • 55 – 80% passing 37.5mm
label | • 35 – 65% passing 19mm
label | • 20 – 50% passing 9.5mm
label | • 10 – 35% passing 4.75mm
label | • 2 – 20% passing 1.18mm
label | • ≤6% passing 75micron
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 2.6 - Solid Density
label | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | TEST REQUIRED - Solid Density
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | ACCEPTANCE CRITERIA - report value only
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 2.7 - Determination of MDD & OWC
label | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | TEST REQUIRED - 5 point compaction curve
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | ACCEPTANCE CRITERIA - report value only
label | QUALITY DOCUMENTATION - IANZ Test report
section | 3.0 - SUBBASE LAYER CONSTRUCTION
checkpoint | 3.1 - Formation
label | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | TEST REQUIRED - 3m straight edge or approved equivalent
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 38 Tests
label | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | ACCEPTANCE CRITERIA - +/- 10mm
label | QUALITY DOCUMENTATION - Inspection checklist
checkpoint | 3.2 - Finished Level
label | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | TEST REQUIRED - String line or equivalent
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 38 Tests
label | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | ACCEPTANCE CRITERIA - +5mm / -25mm
label | QUALITY DOCUMENTATION - Inspection checklist
checkpoint | 3.3 - Compaction
label | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | TEST REQUIRED - NDM
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 7 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NDM
label | ACCEPTANCE CRITERIA - Mean ≥ 95% MDD, Min ≥ 92%, Total voids ≤ 20%
label | QUALITY DOCUMENTATION - IANZ Test report
section | 4.0 - BASECOURSE LAYER MATERIAL TESTING - TNZ M/4 AP40
checkpoint | 4.1 - Crushing Strength
label | SPECIFICATION REFERENCE - TNZ M/4 3.3.1
label | TEST REQUIRED - Crushing Resistance Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.10
label | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 130 KN load
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 4.2 - Weathering Quality
label | SPECIFICATION REFERENCE - TNZ M/4 3.3.2
label | TEST REQUIRED - Weathering Quality Index Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.11
label | ACCEPTANCE CRITERIA - AA, AB, AC, BA, BB or CA
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 4.3 - Soaked CBR
label | SPECIFICATION REFERENCE - TNZ M/4 3.3.3
label | TEST REQUIRED - Remoulded soaked CBR
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 10,000m3 (min 1 per source) - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - Compaction to NZS 4402: 1986 Test 4.1.3 at OMC. CBR testing to NZS 4407 : 1981 Test 3.15
label | ACCEPTANCE CRITERIA - ≥ 80%
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 4.4 - Sand equivalent
label | SPECIFICATION REFERENCE - TNZ M/4 4.2.1.1
label | TEST REQUIRED - Sand equivalent
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400-1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | • 2 Tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS4407 : 1991, Test 3.6
label | ACCEPTANCE CRITERIA - ≥ 40
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 4.5 - Broken Faces Content
label | SPECIFICATION REFERENCE - TNZ M/4 4.2.2
label | TEST REQUIRED - Broken face content
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400-1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | • 2 Tests. n.b. not required if sourced from 100% crushed rock quarry
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.14
label | ACCEPTANCE CRITERIA - ≥ 70%
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 4.6 - Particle size distribution
label | SPECIFICATION REFERENCE - Design
label | TEST REQUIRED - Wet sieving test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 0-400m3=2 tests; 400-1500m3=3 tests; 1500- 4000m3=4 tests; >4000m3=1 test/1000m3
label | • 2 Tests (1 test must be from same sample as MDD/OMC test)
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS4407 4407 : 1991, Test 3.8.1
label | ACCEPTANCE CRITERIA -
label | • 100% passing 37.5mm
label | • 66 - 81% passing 19mm
label | • 43 - 57 passing 9.5mm
label | • 28 - 43 passing 4.75mm
label | • 19 - 33 passing 2.36mm
label | • 12 - 25 passing 1.18mm
label | • 7 - 19 passing 600µm
label | • 3 - 14 passing 300µm
label | • 0 - 10 passing 150µm
label | • 0 - 7 passing 75µm
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 4.7 - Solid Density
label | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | TEST REQUIRED - Solid Density
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407 : 1991, Test 3.7
label | ACCEPTANCE CRITERIA - report value only
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 4.8 - Determination of MDD & OWC
label | SPECIFICATION REFERENCE - TNZ B/2 7.5
label | TEST REQUIRED - 5 point compaction curve
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test per 5000m2 - 1 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4402 : 1986, Test 4.1.3
label | ACCEPTANCE CRITERIA - report value only
label | QUALITY DOCUMENTATION - IANZ Report
section | 5.0 - BASECOURSE LAYER CONSTRUCTION - TNZ M/4 AP40
checkpoint | 5.1 - Formation
label | SPECIFICATION REFERENCE - TNZ B/2 7.7
label | TEST REQUIRED - 3m straight edge or approved equivalent
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 38 Tests
label | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | MEASURING DEVICES OR METHOD - 3m straight edge, tape measure
label | ACCEPTANCE CRITERIA - +/- 10mm
label | QUALITY DOCUMENTATION - Inspection checklist
checkpoint | 5.2 - Finished Level
label | SPECIFICATION REFERENCE - TNZ B/2 5.1
label | TEST REQUIRED - String line or equivalent
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 20m centres each side - 38 Tests
label | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | MEASURING DEVICES OR METHOD - Stringline, tape measure
label | ACCEPTANCE CRITERIA - +15mm / -5mm
label | QUALITY DOCUMENTATION - Inspection checklist
checkpoint | 5.3 - Plateau Density Test
label | SPECIFICATION REFERENCE - TNZ B/2 7.5 (b)
label | TEST REQUIRED - Plateau Density Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test minimum
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NDM
label | ACCEPTANCE CRITERIA - report value only
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 5.4 - Compaction
label | SPECIFICATION REFERENCE - TNZ B/2 7.6
label | TEST REQUIRED - NDM
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 7 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NDM
label | ACCEPTANCE CRITERIA - Mean ≥ 98% MDD or Plateau Density Test, Min ≥ 95%, Total voids ≤ 20%
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 5.5 - Compaction - Feather Edge
label | SPECIFICATION REFERENCE - TNZ B/2 8
label | TEST REQUIRED - Visual Inspection
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Inspect full length each side
label | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | MEASURING DEVICES OR METHOD - truck with 4 tonne wheel load
label | ACCEPTANCE CRITERIA - the surface shall be able to withstand a moving wheel load of up to 4 tonnes without displacement
label | QUALITY DOCUMENTATION - Inspection checklist
checkpoint | 5.6 - Degree of Saturation
label | SPECIFICATION REFERENCE - TNZ B/2 12
label | TEST REQUIRED - NDM
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - min 5 tests per lot (max lot size = 1,000m2) - 7 tests
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NDM
label | ACCEPTANCE CRITERIA - < 60% (or 80% on consultation with the pavement designer)
label | QUALITY DOCUMENTATION - IANZ Report
checkpoint | 5.7 - Surface Finish
label | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | TEST REQUIRED - Visual Inspection
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | TASK ASSIGNED TO - Pavement subcontractor quality representative
label | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | ○ The large aggregate is
label | ○ exposed to the surface;
label | ○ held in place with a matrix of smaller aggregates
label | ○ The smaller aggregate is held firmly in place by fine material;
label | ○ The matrix does not displace under normal trafficking or sweeping.
label | • The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
checkpoint | 5.8 - Ride Quality
label | SPECIFICATION REFERENCE - Internal measure
label | TEST REQUIRED - Ride quality test to AG:AM/T002
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Prior to sealing
label | TASK ASSIGNED TO - WestLink will pay for NAASRA after sweeping before sealing. To be arranged by contractor.
label | MEASURING DEVICES OR METHOD - inertial laser profiler or response-type roughness meter
label | ACCEPTANCE CRITERIA - no 100m moving average > 65 counts
label | QUALITY DOCUMENTATION - Certified test report
section | 6.0 - BITUMEN - TO GAIN APPROVAL
checkpoint | 6.1 - Penetration
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Penetration at 25°C, 100g, five seconds
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - ASTM D5
label | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint | 6.2 - Viscosity
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Viscosity PaS at 60°C
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - AS 2341.2 or ASM D2171
label | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint | 6.3 -
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Viscosity mm2/s at 135°C
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - AS 2341.3 or ASM D2170
label | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint | 6.4 - Flash Point
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Flash point (Cleveland open cup), °C
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - ASTM D92
label | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
label | QUALITY DOCUMENTATION - Letter of compliance from NZTA
checkpoint | 6.5 - Solubility
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Solubility in Trichloroethylene, % or Solubility in Toluene, %
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - ASTM D2042, AS 2341.8
label | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint | 6.6 - Rolling Thin Film
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Rolling Thin Film Oven Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - ASTM D2872 or AS 2341.10
checkpoint | 6.7 - Penetration
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Penetration of residue, at 25°C, 100g, five seconds, % of original
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - ASTM D5
label | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
checkpoint | 6.8 - Ductility
label | SPECIFICATION REFERENCE - TNZ M/1 Table 1
label | TEST REQUIRED - Ductility of residue, at 25°C, (metres)
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 test
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - ASTM D113
label | ACCEPTANCE CRITERIA - Complies with requirements for penetration grade as per TNZ M/01 Table 1
section | 7.0 - SEALING CHIP MATERIAL TESTING
checkpoint | 7.1 - Crushing Strength
label | SPECIFICATION REFERENCE - TNZ M/6 3.2
label | TEST REQUIRED - Crushing Resistance Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.10
label | ACCEPTANCE CRITERIA - <10% fines passing 2.36mm under 230 KN load
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.2 - Weathering Quality
label | SPECIFICATION REFERENCE - TNZ M/6 3.3
label | TEST REQUIRED - Weathering Quality Index Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.11
label | ACCEPTANCE CRITERIA - AA or BA
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.3 - Weak Particles Test
label | SPECIFICATION REFERENCE - TNZ M/6 3.4
label | TEST REQUIRED - Australian Weak Particles Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Only undertaken in cases of dispute
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - AS 1141.32-1995
label | ACCEPTANCE CRITERIA - Maximum of 1%
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.4 - Polished Stone Value
label | SPECIFICATION REFERENCE - TNZ M/6 3.5
label | TEST REQUIRED - Polished Stone Value Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | TASK ASSIGNED TO - Accredited PSV Testing Agency
label | MEASURING DEVICES OR METHOD - BS 812: Part 114
label | ACCEPTANCE CRITERIA - PSV Required = 43
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.5 - Cleanliness
label | SPECIFICATION REFERENCE - TNZ M/6 4.1.1
label | TEST REQUIRED - Cleanliness Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | ACCEPTANCE CRITERIA -
label | • Grade 2 - 89 min
label | • Grade 3 - 87 min
label | • Grade 4 - 85 min
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.6 - Size & Shape
label | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | TEST REQUIRED - Size & Shape
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.13
label | ACCEPTANCE CRITERIA -
label | • Grade 2 - ALD 9.5 - 12.0, 65% within 2.5% ALD
label | • Grade 3 - ALD 7.5 - 10.0, 70% within 2.5% ALD
label | • Grade 4 - ALD 5.5 - 8.0, 65% within 2.5% ALD
label | • 1.1% passing 4.75mm
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.7 - Broken Faces
label | SPECIFICATION REFERENCE - TNZ M/6 4.1.2
label | TEST REQUIRED - Broken Faces Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.14
label | ACCEPTANCE CRITERIA - 98% with minimum two broken faces
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.8 - Grading
label | SPECIFICATION REFERENCE - TNZ M/6 4.2.2
label | TEST REQUIRED - Grading
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality Assurance of Aggregates for Chipseals and Bituminous Mixes (BCA 9805)
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.8
label | ACCEPTANCE CRITERIA -
label | ○ Grade 5
label | • 100% passing 13.2mm
label | • 95 - 100% passing 9.5mm 8% max passing 4.75mm 2% max passing 2.36mm 0% passing 300µm
label | ○ Grade 6
label | • 100% passing 9.5mm
label | • 95-100% max passing 6.7mm 15% max passing 2.36mm 8% max passing 300µm
label | QUALITY DOCUMENTATION - IANZ Test report
checkpoint | 7.9 - Cleanliness
label | SPECIFICATION REFERENCE - TNZ M/6 4.2.3
label | TEST REQUIRED - Cleanliness Test
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - Check the NZ Pavement & Bitumen Contractors Association (BCA) Guidelines: Quality
label | TASK ASSIGNED TO - IANZ accredited laboratory
label | MEASURING DEVICES OR METHOD - NZS 4407:1991, Test 3.9
label | ACCEPTANCE CRITERIA - Report Value Only
label | QUALITY DOCUMENTATION - IANZ Test report
section | 8.0 - SEAL DESIGN
checkpoint | 8.1 - Seal design
label | SPECIFICATION REFERENCE - TNZ P/3
label | TEST REQUIRED - Seal design
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | TASK ASSIGNED TO - Contractor's Quality Manager
label | MEASURING DEVICES OR METHOD - report only
label | ACCEPTANCE CRITERIA - report only
label | QUALITY DOCUMENTATION - Seal design
checkpoint | 8.2 - Seal design approval
label | SPECIFICATION REFERENCE - Internal measure
label | TEST REQUIRED - Internal verification
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 2 weeks Prior to sealing
label | TASK ASSIGNED TO - Downer Surfacing Expert
label | MEASURING DEVICES OR METHOD - report only
label | ACCEPTANCE CRITERIA - report only
label | QUALITY DOCUMENTATION - Email from Downer surfacing expert confirming that the treatment selection and seal design has been reviewed to confirm it is fit for purpose
checkpoint | 8.3 - Surface Finish
label | SPECIFICATION REFERENCE - TNZ B/2 7.8
label | TEST REQUIRED - Visual Inspection
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - 1 day prior to surfacing. Photographs at 50m centres each side of the road, minimum 8MP, geotagged with pen or keys as scale.
label | TASK ASSIGNED TO - Sealing subcontractor quality representative
label | MEASURING DEVICES OR METHOD - Stiff bristled broom, camera, eye
label | ACCEPTANCE CRITERIA - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept, in which;
label | ○ The large aggregate is
label | ○ exposed to the surface;
label | ○ held in place with a matrix of smaller aggregates
label | ○ The smaller aggregate is held firmly in place by fine material;
label | ○ The matrix does not displace under normal trafficking or sweeping.
label | • The standard of sweeping shall be sufficient to remove all loose aggregate, dirt, dust, silt and other deleterious matter.
label | QUALITY DOCUMENTATION - Inspection checklist and photographs supplied electronically.
section | 9.0 - SEALING RECORDS
checkpoint | 9.1 - Blend sheet
label | SPECIFICATION REFERENCE - Client request
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | TASK ASSIGNED TO - Bitumen blending facility
label | ACCEPTANCE CRITERIA - Report value only
label | QUALITY DOCUMENTATION - Blend sheet
checkpoint | 9.2 - Spray sheets
label | SPECIFICATION REFERENCE - Client request
label | TASK TIMING OR TASK FREQUENCY & MINIMUM REQUIREMENTS - On day of seal
label | TASK ASSIGNED TO - Sealing Manager
label | ACCEPTANCE CRITERIA - Report value only
label | QUALITY DOCUMENTATION - Spray sheets