## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-CIV-Pump Station (Supply and Install)
ITP Description: |  | Pump Station (Supply and Install)
Discipline (e.g. CIV/STR/RAIL: |  | CIV
Revision Number: |  | 1
Revision Date: |  | 2023-01-16
ITP created by: |  | Paolo Oliva
ITP approved for use by: |  | Pradeep Talasila
Special Notes to ConQA Team : |  | ITP for Robinsons Road only
Inspection & Test Plan - Pump Station
[9 empty] | Revision: | 1
[9 empty] | Date: | 2023-01-16
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | VicRoads Section ### Month Year | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 |  | VicRoads Section ### Month Year
1.3 |  | VicRoads Section ### Month Year
2 | Pre-construction / Pre-installation Activities
2.1 | Drawings approved | IFC Drawings | Signed drawings for construction | Visual | N/A | IP | SE/PE/SPE | Signed drawings for construction
2.2 | Penetration Drawings Checked | Shop Drawings | Authorisation by Aquatec Engineer | Dimension Check | N/A | IP | SE/PE/SPE | Authorisation by Aquatec Engineer
2.3 | Craning and excavation details created | Lift Plans | Craning and excavation document # issued to client for reference. | Calculation Check | N/A | IP | SE/PE/SPE | Manufacturer Component Specs
2.4 | Pre-Cast Concrete Product Control | Australian Standards | Concrete Test Report | QA test by manufacturer | During Manufacturer | IP | SE/PE/SPE | Concrete Test Report
4 | Construction / Installation Activities
4.1 | Check concrete components are correctly loaded on truck |  | Approved by Project Manager or Engineer | Visual | Checked prior to dispatch | IP | SE/PE/SPE | Photos
4.2 | Installation of Concrete Pump Station Components | Approved Drawings | Signed Civil Installation Site Record Relevant Photos IFC Drawings marked up to 'AS CONCSTRUCTED' | As per Civil Installation Site Record | Continuosly during phase | N/A | SE/PE/SPE | Civil Installation Site Record
4.3 | Installation of fixtures to pump station | Approved Drawings | Signed Mechanical Fit Out Site Record | As per Mechanical Fit Out Site Record Document # | Continuosly during phase | N/A | SE/PE/SPE | Mechanical Fit Out Site Record Document #
4.4 | Fabrication of switchboard | AS3000 | Signed FAT Sheet | Review Manufacturers ITP | Continuosly during phase | N/A | SE/PE/SPE | AQT FAT Test Sheet - Switchboard
4.5 | Installation of Switchboard, Mains Cabling & Metering Application | AS3001 | Signed Eletrical Site Record Relevant photos Certified Certificate of Electrical Safety IFC Drawings marked up as 'AS CONSTRUCTED' | As per Electrical Installation Site Record | Continuosly during phase | N/A | SE/PE/SPE | Electrical Site Record Certificate of Electrical Safety
4.6 | Installation of pumps and other electrical equipment | AS3002 | Signed Eletrical Site Record Relevant photos IFC Drawings marked up as 'AS CONSTRUCTED' | As per Electrical Site Record | Continuosly during phase | N/A | SE/PE/SPE | Electrical Site Record
5 | Post-construction / Post-installation Activities
5.1 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
5.2 | Commissioning of Pump Station | Approved Drawings | SAT Form Completed and Signed | SAT Form Used | Continuosly during phase | N/A | SE/PE/SPE | SAT Form Used
5.3 | Sub-contractor ITP attached and Signed-off |  |  |  |  | HP*
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /