## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-CIV-Pump Station (Supply and Install) | itp |  |  |  |  | ITP-CIV-Pump Station (Supply and Install) Rev 1
section | Referenced Documentation
checkpoint | Referenced Documentation
note | Document Title: ITP-CIV-Pump Station (Supply and Install)
note | ITP Description: Pump Station (Supply and Install)
note | Document Number (in Teambinder): N/A
note | Discipline (e.g. CIV/STR/RAIL): CIV
note | Revision Number: 1
note | Revision Date: 16/01/2023
note | ITP created by: Paolo Oliva
note | ITP approved for use by: Pradeep Talasila
note | 1.1 Non Dependent
note | Reference: VicRoads Section ### Month Year
note | 1.2 Non Dependent
note | Reference: VicRoads Section ### Month Year
note | 1.3 Non Dependent
note | Reference: VicRoads Section ### Month Year
section | Pre-construction / Pre-installation Activities
checkpoint | 2.1 Drawings approved
note | REFERENCE: IFC Drawings
note | ACCEPTANCE CRITERIA: Signed drawings for construction
note | METHOD: Visual
note | FREQUENCY: N/A
note | CATEGORY: IP
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Signed drawings for construction
textbox | Date Completed:
checkpoint | 2.2 Penetration Drawings Checked
note | REFERENCE: Shop Drawings
note | ACCEPTANCE CRITERIA: Authorisation by Aquatec Engineer
note | METHOD: Dimension Check
note | FREQUENCY: N/A
note | CATEGORY: IP
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Authorisation by Aquatec Engineer
textbox | Date Completed:
checkpoint | 2.3 Craning and excavation details created
note | REFERENCE: Lift Plans
note | ACCEPTANCE CRITERIA: Craning and excavation document # issued to client for reference.
note | METHOD: Calculation Check
note | FREQUENCY: N/A
note | CATEGORY: IP
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Manufacturer Component Specs
textbox | Date Completed:
checkpoint | 2.4 Pre-Cast Concrete Product Control
note | REFERENCE: Australian Standards
note | ACCEPTANCE CRITERIA: Concrete Test Report
note | METHOD: QA test by manufacturer
note | FREQUENCY: During Manufacturer
note | CATEGORY: IP
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Concrete Test Report
textbox | Date Completed:
section | Construction / Installation Activities
checkpoint | 4.1 Check concrete components are correctly loaded on truck
note | ACCEPTANCE CRITERIA: Approved by Project Manager or Engineer
note | METHOD: Visual
note | FREQUENCY: Checked prior to dispatch
note | CATEGORY: IP
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Photos
textbox | Date Completed:
checkpoint | 4.2 Installation of Concrete Pump Station Components
note | REFERENCE: Approved Drawings
note | ACCEPTANCE CRITERIA: Signed Civil Installation Site Record
note | Relevant Photos
note | IFC Drawings marked up to 'AS CONSTRUCTED'
note | METHOD: As per Civil Installation Site Record
note | FREQUENCY: Continuosly during phase
note | CATEGORY: N/A
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Civil Installation Site Record
textbox | Date Completed:
checkpoint | 4.3 Installation of fixtures to pump station
note | REFERENCE: Approved Drawings
note | ACCEPTANCE CRITERIA: Signed Mechanical Fit Out Site Record
note | METHOD: As per Mechanical Fit Out Site Record Document #
note | FREQUENCY: Continuosly during phase
note | CATEGORY: N/A
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Mechanical Fit Out Site Record Document #
textbox | Date Completed:
checkpoint | 4.4 Fabrication of switchboard
note | REFERENCE: AS3000
note | ACCEPTANCE CRITERIA: Signed FAT Sheet
note | METHOD: Review Manufacturers ITP
note | FREQUENCY: Continuosly during phase
note | CATEGORY: N/A
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: AQT FAT Test Sheet - Switchboard
textbox | Date Completed:
checkpoint | 4.5 Installation of Switchboard, Mains Cabling & Metering Application
note | REFERENCE: AS3001
note | ACCEPTANCE CRITERIA: Signed Eletrical Site Record
note | Relevant photos
note | Certified Certificate of Electrical Safety
note | IFC Drawings marked up as 'AS CONSTRUCTED'
note | METHOD: As per Electrical Installation Site Record
note | FREQUENCY: Continuosly during phase
note | CATEGORY: N/A
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Electrical Site Record, Certificate of Electrical Safety
textbox | Date Completed:
checkpoint | 4.6 Installation of pumps and other electrical equipment
note | REFERENCE: AS3002
note | ACCEPTANCE CRITERIA: Signed Eletrical Site Record
note | Relevant photos
note | IFC Drawings marked up as 'AS CONSTRUCTED'
note | METHOD: As per Electrical Site Record
note | FREQUENCY: Continuosly during phase
note | CATEGORY: N/A
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: Electrical Site Record
textbox | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 5.1 Non-conformance Report (NCR) Closure
note | REFERENCE: MRPA Quality Management Plan
note | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
note | METHOD: Document Review
note | FREQUENCY: Once, prior to closure of this lot / element / Work area
note | CATEGORY: HP*
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: This ITP
textbox | Date Completed:
checkpoint | 5.2 Commissioning of Pump Station
note | REFERENCE: Approved Drawings
note | ACCEPTANCE CRITERIA: SAT Form Completed and Signed
note | METHOD: SAT Form Used
note | FREQUENCY: Continuosly during phase
note | CATEGORY: N/A
note | RESPONSIBILITY: SE/PE/SPE
note | VERIFYING DOCUMENTS: SAT Form Used
textbox | Date Completed:
checkpoint | 5.3 Sub-contractor ITP attached and Signed-off
note | CATEGORY: HP*
checkpoint | Metropolitan Roads Program Alliance Final Inspection
note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
textbox | Name:
textbox | Position:
textbox | Date Completed:
signoff | Sign ITP