## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-067-CIV-CAMMS-Line marking | itp |  |  |  |  | ITP-067-CIV-CAMMS-Line marking Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-067-CIV-CAMMS-Line marking
label | ITP Description: CAMMS-Line marking
label | ITP number: 067-CIV
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): CIV
label | Revision Number: 0
label | Revision Date: 13/10/2023
label | ITP created by: Victor Mira
label | ITP approved for use by: Victor Mira
label | 1.1 Non Dependent
label | Reference: Vicroads Section 721 February 2017
label | 1.2 Non Dependent
label | Reference: Vicroads Section 175 November 2019
label | 1.3 Non Dependent
label | Reference: Vicroads Section 853 February 1994
section | Preliminaries - Materials
checkpoint | 2.2 Type of marking material as shown on design drawings and shall conform to the Standard
label | REFERENCE: Vicroads 721.A05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Type as per relevant design drawings, obtain Conformance Certificates and test reports from supplier
label | ○ Provide the principle a list of materials that to be used with a certificate of conformance with associated test report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.3 Raised Pavement Markers
label | REFERENCE: Vicroads 721.A05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Raised pavement markers shall comply with the relevant requirements of AS 1906, Part 3 as listed in Section 175.
label | (ii) Temporary raised reflective pavement markers shall comply with the relevant requirements of AS 1906 as listed in Section 175, and shall be at least 100 mm in width and to a height of 50 mm with white reflective material on both sides and include protective covers for the reflective material
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Material
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.4 Adhesive
label | REFERENCE: Vicroads 721.A05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Hot melt bitumen adhesive shall comply with Section 853 - Hot Melt Bitumen Adhesive for Raised Pavement Marker Installation.
label | ○ Other types of adhesive materials shall only be used with the approval of the Superintendent
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Material
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.5 Line marking and Road marking Paint
label | REFERENCE: Vicroads 721.A05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent-borne paint or AS/NZS 4049.3 for water-borne paint as listed in Section 175.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Material
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.6 Glass beads
label | REFERENCE: Vicroads 721.A05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Material
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
checkpoint | 2.6 Glass beads
label | REFERENCE: Vicroads 721.A05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Glass beads shall be used on all applications of material and for all pavement markings and shall conform to the requirements in AS/NZS 2009 and the Australian Paint Approval Scheme (APAS) Specification 0042.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Material
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Material certificate
date | Date Completed:
section | Preliminaries - Procedures & Documentation
checkpoint | 2.1 Accreditation to Painting Contractors Certification Program
label | REFERENCE: Vicroads 721.D01
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide evidence that the work is being undertaken by a contractor eligible for accreditation under painting Certification Program(PCCP). This Programme is administered by the CSIRO.
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release, PCCP Accreditation
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-construction Activities
checkpoint | 3.1 Surface preparation
label | REFERENCE: Vicroads 721.A06, Vicroads 721.A09
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The area to be marked is dry free of dirt, gravel, flaking and other loose foreign material
label | ○ The area around making area is also clean to avoid tracking into the marking area
label | ○ Removal of existing unsound, obsolete or redundant pavement markings
label | ○ Removal of any foreign materials and debris within reasonable limits.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual, Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.3 Redundant pavement / unsuitable marking markers removal
label | REFERENCE: Vicroads 721.A12, Vicroads 721.A06, Vicroads 721.A08
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Where removal of existing pavement marking/unsuitable pavement marking to the standard is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual /Site Inspection & Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 3.2 Set out the works for installation of pavement markings / raised markers
label | REFERENCE: Vicroads 721.B05
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless a written exemption has been granted by the Superintendent
label | – – – – – – – – – – – – – – – – –
label | METHOD: Survey Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Construction Activities
checkpoint | 3.4 Application of pavement marking / markers
label | REFERENCE: Vicroads 721
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check conditions for application of marking paint & materials.
label | (i) Paints and markers installed as per manufacturer’s recommendations.
label | (ii) The same materials used with those nominated in the certifications.
label | (ii) All longitudinal lines have been applied by the nominated machine unless approved by superintendent
label | (iv) Verify markings are straight or with smooth, even curves where intended.
label | (v) Edges are clean sharp cut off.
label | (vi) Markings uniform in appearance, texture, width & thickness & free from unbeaded areas
label | (vii) Waterorne Paint & Glass Beads application rate conform to the requirements of Vic road 721.E01 requirements.
label | (viii) Markings are neat & free from traffic damage or other defects
label | (ix) Marking protected from traffic until hardened
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual /Site Inspection & Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.5 Tolerances for new marking/marker installations
label | REFERENCE: Vicroads 721.A10 Table 721.A101
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pavement marking :
label | ○ Distance between the centreline of the marking and the centreline of the set out mark - <30 mm
label | ○ Distance between the centreline of the completed marking and the centreline of the previous marking - <15 mm
label | ○ Width of completed painted markings - ±10 mm of the specified dimensions
label | ○ Width of completed markings for long life materials0 mm to +10 mm
label | ○ Length of completed stripes and blocks - 0% to +10% of the specified length
label | ○ Gap between double lines - - 10 mm to +0 mm of the required 100 mm gap
label | Raised Pavement Markers:
label | (i)Markers in line with broken segments
label | ○ Transverse position - ±25 mm of the centreline of segments
label | ○ Longitudinal position - ±0.5 m of the specified position
label | (ii) Markers in a longitudinal group
label | ○ Transverse position - ±25 mm of specified position and ±10 mm of a line joining the centres of the end markers
label | ○ Longitudinal position - ±0.5 m
label | ○ Spacing of markers within the group - 50 mm of specified spacing
label | (iii) Markers adjacent to an unbroken line
label | ○ Clearance to edge line - ±5 mm of the specified dimensions
label | ○ Longitudinal mismatch between markers in transverse pairs - <25 mm
label | ○ Longitudinal position - Lesser of: 0.5 m or 10%
label | (iv) Orientation of reflective markers - Lower edge of the reflective face at 85º to 95º to centreline of roadway or adjacent line
label | ○ Thermoplastic profiled lines
label | (i) Tolerances on dimension
label | ○ Line width - +20 mm, - 5 mm
label | ○ Line height - +2 mm, - 0 mm
label | ○ Extrusion breadth - +10 mm, - 0 mm
label | ○ Extrusion spacing - ±15 mm
label | ○ Extrusion shape - ±25 mm at any point from rectangular shape
label | (ii) Tolerances on position
label | ○ Distance between the centreline of the marking and the centreline of the set out - <30 mm
label | ○ Length of the completed lines - - 0% to +5% of the specified length
label | ○ Longitudinal position of individual extrusions - ±50 mm of any previously applied profiled lining
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual /Site Inspection & Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per Lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 3.6 Retroreflectivity Report
label | REFERENCE: Vicroads 721.B06 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Complete and forward Retro reflectivity Report in a form approved by the Superintendent showing the level of retro reflectivity determined for each test lot in accordance with the requirements of Clause 721.A12.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Job Completion Report
label | REFERENCE: Vicroads 721.B06 (a)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: For New Markings the Contractor shall complete and forward to the Superintendent a Job Completion Report (Pavement Markings).
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Per lot When applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP