## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-071-STR-CAMMS-Misc Steel Structures Installation | itp |  |  |  |  | ITP-071-STR-CAMMS-Misc Steel Structures Installation Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-071-STR-CAMMS-Misc Steel Structures Installation
label | ITP Description: CAMMS-Misc Steel Structures Installation
label | ITP number: 071-STR
label | Document Number (in Teambinder): MRP-0000-MRPA-ALT-ITP-00XX
label | Discipline (e.g. CIV/STR/RAIL): 071-STR
label | Revision Number: 0
label | Revision Date: 19/10/2023
label | ITP created by: VM
label | ITP approved for use by: VM
label | 1.1 Non Dependent
label | Reference: VicRoads Section 610 June 2019
label | 1.2 Non Dependent
label | Reference: VicRoads Section 630 October 2013
label | 1.3 Non Dependent
label | Reference: VicRoads Section 631 February 2009
section | Preliminaries - Materials
checkpoint | 2.1 Structural Steel Components
label | REFERENCE: IFC Drawings, MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Fabricator is required to provide the Manufacturer's Data Record (MDR) for each component.
label | Typically this consists of but not limited to:
label | i. Certificate of Compliance
label | ii. Completed ITP
label | iii. Weld Procedure Specifications
label | iv. Weld Procedure Qualifications
label | v. Welder Qualifications
label | vi. Material Certificates and traceability
label | vii. Quality Assurance check sheets
label | viii. Welding Consumable batch certificates
label | ix. Coating certificate(s)
label | x. Non-destructive Testing (NDT) Reports
label | xi. As-built Drawings to demonstrate compliance with dimensional tolerances of structural steel
label | Collate: Structural Steel Quality Assurance Documentation and upload in a TeamBinder Lot.
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/SE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 2.2 Fasteners
label | REFERENCE: 630.20 IFC Drawing
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bolts, nuts and washers for Property Class 4.6 bolting shall be supplied in accordance with AS 1111 and AS 1112
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
date | Date Completed:
checkpoint | 2.2 Base Plate Structural Grout or Mortar
label | REFERENCE: IFC Drawings 610.33
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Product to be selected based on the following criteria:
label | i. either a single component, self consolidating and dual shrinkage compensating cementitious grout
label | ii. have the required strength at 28 days as noted on the IFC drawings, but 40MPa minimum
label | iii. have a flowable consistency
label | iv. the surface preparation matches the concrete surface underneath the post base-plate as per the IFC drawings (see 5.1 also)
label | v. have the characteristics capable of being applied to the minimum and maximum thickness as noted on the IFC drawings
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, for each product, prior to placement of product
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.3 Curing Compound
label | REFERENCE: 610.23 (d)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Details of curing compound and NATA test certificate stating compliance with AS3799 no more than 3 years from issue, to be submitted for review to the Nominated Authority.
label | Note: This may be the same product used for the concrete curing
textbox | Enter: Teambinder Material Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, once, for each product, prior to placement of product
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Preliminaries - Procedures
checkpoint | 3.1 Installation Methodology & Works Method Statiment
label | REFERENCE: 630.20 AS5131 Clause 11.2.3
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Details of how the Structural & Architectural Steel will be Installed will need to be privided including the following:
label | – Transported to site;
label | – Handled on site;
label | – Installation Procedure (subcontracor ITP's);
label | Attach: Subcontractor ITP
textbox | Enter: Teambinder Approval number
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, once, 14 days prior to use of devices
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Nominated Authority
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Subcontractor ITP, ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
section | Pre-installation Activities
checkpoint | 4.1 IFC Drawings
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Check the revision of the IFC drawings are current as per the drawing register (on Teambinder)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Prior to starting Works and at regular intervals
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: All
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Materials Inspection
label | REFERENCE: IFC Drawings VR 630
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: General inspection of structural steel elements for defects including cracks, handling and storage damage & distortion.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.3 Materials Inspection
label | REFERENCE: IFC Drawings VR 630
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Bolts, nuts and washers shall be the size, material, strength grade and coating as noted on the IFC Drawings.
label | ○ Where bolted faces are sloping at 1:20 or greater, tapered washers must be used.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Materials Inspection
label | REFERENCE: IFC Drawings VR 631
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Galvanised coating - no loss of adhesion, damage, blisters, roughness, sharp points and flux residues.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.5 Materials Inspection
label | REFERENCE: IFC Drawings VR 631
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Paint or powder coating - uniform in appearance, colour & texture with no loss of adhesion, damage, blisters, holidays, chalking or any other visible defects.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Installation Activities
checkpoint | 5.1 Bearing / Mounting Surface Preparation
label | REFERENCE: IFC Drawings Product TDS
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure the bearing surface clean and free from loose particles that will prevent solid seating of the parts
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each installation location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Structural Steel Handling
label | REFERENCE: 630.09, 631.14
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The method of handling and erection of the steelwork shall ensure that the members are not stressed or deformed beyond the design limit and that there is no damage to the protective coating during these operations.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.3 Structural Steel Erection
label | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level, square and within tolerances shown in 5.6.
label | ○ Where mounting to supports or foundations, adjust RL accordingly using suitably sized shims, levelling or jacking nuts (where applicable).
label | ○ Where a misalignment is found, only rheaming, milling, drilling or machine flame or plasma cut are allowed. Internal surface of the hole to remain smooth and free from burrs.
label | ○ Holes shall not exceed the greater of: 1.25 x bolt dia. OR bolt dia. + 8mm
label | ○ Slots shall not exceed the greater of: 1.33 x (bolt dia. + 10mm) OR 2.5 x bolt dia
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Fastener Tightening - Snug Tight Condition
label | REFERENCE: IFC Drawings VR 630
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | For posts base plates, the arrangement is to be (from the base plate):
label | – Base Plate
label | – Washer as specified
label | – Lock Nut as specified
label | – Nut
label | – Bolt protrusion (1 clear tread)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each bolted connection
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Fastener Tightening - Snug Tight Condition
label | REFERENCE: IFC Drawings VR 630
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Washers shall cover the hole or slotted hole completely by 0.5 x bolt diamter.
label | ○ Tapered washers shall be positioned if specified.
label | ○ Tighten from the stiffest section working towards the free edges with a few impacts of an impact wrench or the full effort of a person using a podger spanner.
label | ○ Protrusion to be at least 1 clear thread shows beyond the nut but no greater than 12mm.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each bolted connection
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.6 Survey Conformance
label | REFERENCE: IFC Drawings AS4100 Clause 15.3.1 - 7, AS5131 Appendix F, Table F3
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Grouting of base plates and/or tensioning of bolts shall not commence until verification that the Works meet level and location requirements within the tolerances below:
label | Departure from RL = ±10mm
label | Departure from plan position = ±6mm
label | Departure from alignment = ±6mm
label | Irregularities in alignment = 25mm in 30m
label | Projection of bolt = +25mm, 5mm
label | Location of beam = ±3mm
label | Location of column = height/500, 10mm max.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: PE/Surveyor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.7 Base Plate Formwork Construction & Placement
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Dimensions as per drawings to achieve the profile.
label | ○ Formwork rigid, sufficiently braced to support the pressure of the grout/mortar product and sealed to prevent leaks.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.8 Pre-soaking Concrete Surface
label | REFERENCE: Product TDS
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Pre-soak the concrete surface with potable water for the recommended time frame indicated on the Product's TDS.
label | ○ Prior to mixing the product, remove excess water that has not leaked out of the forms or been soaked into the substrate by appropriate means such as a leaf blower.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.9 Weather Conditions
label | REFERENCE: 610.17 Table 610.171
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Do not commence grouting operations if inclement weather is forecast and the Works cannot be protected.
label | ○ The temperature of the cementitious products, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | Record: Required information on the Grout Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.10 Mixing Product
label | REFERENCE: Product TDS 610.28
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Size of mixer should match the application.
label | ○ Only whole bags to be mixed with potable water.
label | ○ Volume of water matches the required amount for flowable consistency and accurately measured.
label | ○ Product poured into the mixer slowly.
label | ○ Mixing time as per TDS so that a smooth, even consistency is obtained.
textbox | Enter: Required information on the Grout Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each batch
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.11 Product Testing - Compressive Strength Cubes
label | REFERENCE: 610.28, 610.33
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Cube moulds to be 75mm x 75mm maximum, made from rigid steel moulds and require lids due to the expansive nature of shrinkage compensating products.
label | ○ Testing is be in accordance with the following frequencies:
label | ○ First batch = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
label | ○ Every 100kg of product thereafter = 3 cubes (2 no. 7 day strength, 1 no. 28 day strength)
textbox | Enter: Required information on the Grout Pour Record.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Tester, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.12 Placement & Compaction
label | REFERENCE: Product TDS
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All batches are traceable.
label | ○ Product poured from one side of the formwork to eliminate the entrapment of air or surplus pre-soaking water.
label | ○ Product should flow to all areas and self consolidate.
label | ○ Product that stiffens or is showing signs of stiffening shall not be used.
textbox | Enter: Required information on the Grout Pour Record
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.13 Surface Finishes & Protection of Works
label | REFERENCE: IFC Drawings 610.17
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: If shaping of the unformed surface is required, shape prior to the product fully hardening.
label | ○ All freshly finished surfaces shall be protected where required from the sun, wind or rain, until curing is implemented.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each post location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.14 Curing
label | REFERENCE: Curing Methodology 610.23 Table 610.231
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Curing to commence immediately after finishing operations and continue for the duration specified in table 610.231.
label | ○ Curing methodology to be in accordance with the approved procedure and manufacturer's TDS.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each post location
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.15 Architectural Steel Erection
label | REFERENCE: AS4100 Clause 15.2.3, AS5131 Clause 11.5.7, 630.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place steel component into position, ensuring that it is plumb, level and square
label | ○ Where steel to steel connections exist, holes shall be aligned so that a drift pin equal in diamter of the bolts can pass through freely
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.16 Architectural Steel Erection-Fasteners
label | REFERENCE: IFC Drawings VR 630
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Place bolts, washers and nuts as detailed on the IFC Drawings.
label | For architectural/Security screens, the arrangement is to be (from themounting post):
label | – Post
label | – Washer (s) as specified
label | – Insulating washer
label | – insulating bush
label | – Insulating washer
label | – washer as specified
label | – Lock nut
label | – Nut
label | – Bolt protrusion (1 clear tread)
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Where applicable, each bolted connection
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.17 Installation of Electrical Isolation Materials
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Installation of Electrical Isolation Material in locations specified on the IFC drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-installation Activities
checkpoint | 6.1 Inspection of Coating
label | REFERENCE: IFC Drawings VR 630
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: After installation Works are complete, inspect the steel element for damage to the coatings.
label | ○ Where damage exists, it shall be repaired using an approved repair procedure.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each component
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.2 Compressive Strength Test Results
label | REFERENCE: IFC Drawings Product TDS 610.28, 610.33
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 7 day compressive strength (average of the 2 no. cubes) per sample for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength per sample comply with the design strength.
label | Attach: Compressive Strength Test Results
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each cube
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.3 As-built Survey
label | REFERENCE: IFC Drawings AS5131 Appendix F, Table F3
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate that all Works meet level and location requirements within the tolerances below:
label | Departure from RL = ±10mm
label | Departure from plan position = ±6mm
label | Departure from alignment = ±6mm
label | Irregularities in alignment = 25mm in 30m
label | Projection of bolt = +25mm, 5mm
label | Location of beam = ±3mm
label | Location of column = height/500, 10mm max.
label | Attach: Survey As-builts / Survey Report
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 6.4 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP*
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP