## Project Structure
Folder Structure |  | Checklists
Manufacturing QA
| Precasting | Precast casting
| 301 | Precast Product Pre-Pour & Post-Pour Checklist
| 302 | Precast Product Pre-Pour & Post-Pour Checklist
| 303 | Precast Product Pre-Pour & Post-Pour Checklist
| 304 | Precast Product Pre-Pour & Post-Pour Checklist
| 304-A | Precast Product Pre-Pour & Post-Pour Checklist
| 305 | Precast Product Pre-Pour & Post-Pour Checklist
| 306 | Precast Product Pre-Pour & Post-Pour Checklist
| 307 | Precast Product Pre-Pour & Post-Pour Checklist
| 307-A | Precast Product Pre-Pour & Post-Pour Checklist
| 308 | Precast Product Pre-Pour & Post-Pour Checklist
| 309 | Precast Product Pre-Pour & Post-Pour Checklist
| 310 | Precast Product Pre-Pour & Post-Pour Checklist
| 311 | Precast Product Pre-Pour & Post-Pour Checklist
| 311-A | Precast Product Pre-Pour & Post-Pour Checklist
| 312 | Precast Product Pre-Pour & Post-Pour Checklist
| 313 | Precast Product Pre-Pour & Post-Pour Checklist
| 314 | Precast Product Pre-Pour & Post-Pour Checklist
| 315 | Precast Product Pre-Pour & Post-Pour Checklist
| 316 | Precast Product Pre-Pour & Post-Pour Checklist
| 317 | Precast Product Pre-Pour & Post-Pour Checklist
| 318 | Precast Product Pre-Pour & Post-Pour Checklist
| 319 | Precast Product Pre-Pour & Post-Pour Checklist
| 319-A | Precast Product Pre-Pour & Post-Pour Checklist
| 320 | Precast Product Pre-Pour & Post-Pour Checklist
| 321 | Precast Product Pre-Pour & Post-Pour Checklist
| 321-A | Precast Product Pre-Pour & Post-Pour Checklist
| 322 | Precast Product Pre-Pour & Post-Pour Checklist
| 322-A | Precast Product Pre-Pour & Post-Pour Checklist
| 323 | Precast Product Pre-Pour & Post-Pour Checklist
| 324 | Precast Product Pre-Pour & Post-Pour Checklist
| 325 | Precast Product Pre-Pour & Post-Pour Checklist
| 325-A | Precast Product Pre-Pour & Post-Pour Checklist
| 326 | Precast Product Pre-Pour & Post-Pour Checklist
| 327 | Precast Product Pre-Pour & Post-Pour Checklist
| 328 | Precast Product Pre-Pour & Post-Pour Checklist
| 329 | Precast Product Pre-Pour & Post-Pour Checklist
| 329-A | Precast Product Pre-Pour & Post-Pour Checklist
| 330 | Precast Product Pre-Pour & Post-Pour Checklist
| 331 | Precast Product Pre-Pour & Post-Pour Checklist
| 332 | Precast Product Pre-Pour & Post-Pour Checklist
| 333 | Precast Product Pre-Pour & Post-Pour Checklist
| 333-A | Precast Product Pre-Pour & Post-Pour Checklist
Site QA
| Mains Drawings | Site QA
| Shop Drawings | Site QA
| 301 | Site QA
| 302 | Site QA
| 303 | Site QA
| 304 | Site QA
| 304-A | Site QA
| 305 | Site QA
| 306 | Site QA
| 307 | Site QA
| 307-A | Site QA
| 308 | Site QA
| 309 | Site QA
| 310 | Site QA
| 311 | Site QA
| 311-A | Site QA
| 312 | Site QA
| 313 | Site QA
| 314 | Site QA
| 315 | Site QA
| 316 | Site QA
| 317 | Site QA
| 318 | Site QA
| 319 | Site QA
| 319-A | Site QA
| 320 | Site QA
| 321 | Site QA
| 321-A | Site QA
| 322 | Site QA
| 322-A | Site QA
| 323 | Site QA
| 324 | Site QA
| 325 | Site QA
| 325-A | Site QA
| 326 | Site QA
| 327 | Site QA
| 328 | Site QA
| 329 | Site QA
| 329-A | Site QA
| 330 | Site QA
| 331 | Site QA
| 332 | Site QA
| 333 | Site QA
| 333-A | Site QA

## Checklists
type | name | values
checklist | Precast Product Pre-Pour & Post-Pour Checklist
section | Pre-Pour
checkpoint | Current, approved & attached
text | Production Actual Date
text | Delivery Date
checkpoint | Forms clean & release agent/oil applied
checkpoint | Chamfers installed as per the drawings
checkpoint | Drawing Dimensions within Tolerances
checkpoint | Order Number recorded on manufacture drg.
checkpoint | Reo in accordance with drawings, within tolerance and marked on drawing
checkpoint | E.g. Block outs, Drains, Bolts, Ferrules, Debonding, couplers, etc. Correct type, correctly located, secure and marked on drawing.
signoff | Sign Off Required Alpha Precast Pty Ltd Representative & Client Representative
checkpoint | Correct rating, length, location
checkpoint | Void Formers, Location & correct installation
signoff | Sign Off Required Alpha Precast Pty Ltd Representative & Client Representative
checkpoint | Pour arrangements agreed & equipment adequate.
checkpoint | Concrete mix selected as per approved mix design
checkpoint | Unit ID has been placed on reo/lifter or embedded in concrete face/ edge.
checkpoint | All checks and hold points signed before concrete may be placed.
signoff | Sign Off Required Alpha Precast Pty Ltd Representative & Client Representative
section | Post Pour
checkpoint | Strength achieved - Lifting strength at least 15 Mpa
signoff | Sign Off Required Alpha Precast Pty Ltd Representative & Client Representative
checkpoint | Membrane curing - if required, coating as per specification CONCURE 99A REMOVAL BY OTHERS
checkpoint | Embedded items alignment and position correct and marked on drawing
checkpoint | NCR raised and closed as required. All repairs completed
checkpoint | Survey complete and dimensions marked up on shop drawing issued for construction.
checklist | Precast casting
section | Authorised Documentation for commencement of new work is in place
checkpoint | All 'preconstruction' authorisations & checks completed
section | Concrete Mix Design and Approval
checkpoint | Concrete Mix Design and Approval AS 1379
section | Supply of Reinforcing Steel and Receipt
checkpoint | Supply of Reinforcing Steel and Receipt AS 4671
checkpoint | Supplier and Mill ACRS accredited
checkpoint | Reo Bent to shop drawing schedule
section | Approval of Shop Drawings
checkpoint | Shop Drawings as per AFC Drawings
checkpoint | Shop Drawings Approved - Lift Certificate
section | Steel, Void Formers and Cast-in Fixings
checkpoint | Pre-pour Inspection Checklist Complete, pour to proceed
section | Pour Arrangement
checkpoint | Confirm Pour with Supplier:
text | Product ID
text | Schedule/Time
label | Mix Type: 40mpa, High early, shrinkage limited - B80 ( delete as required)
section | Concrete Placement
checkpoint | Concrete and placement to AS3600
section | Sampling and Testing
checkpoint | Sampling Frequency to AS1012
section | Stripping and demoulding
checkpoint | Stripping strength >/= 15 MPA = what is shown on the drawing
checkpoint | Lifting points in the correct locations
section | Product Inspection, As-built Measurements, and Repairs (where required)
checkpoint | As-built dimensions noted on manufacture drawing
checkpoint | Finish complies with drawing- Post-pour Inspection Checklist Complete
section | Identification, Handling and Storage
checkpoint | Weight & ID written on each member
checkpoint | Items adequately supported
checkpoint | Dunnage and Lifting as shown on shop drawings
section | Items Released for Delivery
checkpoint | Concrete Transport Test Results Comply as specified- Concrete strength complies to minimum strength for lifting
checkpoint | Relevant NCR and repair action records closed
section | Final Documentation Review
checkpoint | Concrete Transport Test Results Comply as specified
checkpoint | All Manufacture and Delivery Dockets closed, signed and filed
checkpoint | As a representative of Alpha Precast Pty Ltd I certify that the precast panels manufactured under the scope of this ITP conform in all respects with the standards and the requirements specified in the contract documents, and All necessary documentation proving conformance of the units manufactured under the scope of this ITP are attached herewith.
signoff | Sign Off Required Alpha Precast Pty Ltd Representative & Client Representative
checklist | NCR Form
section | Description of Non-conformance
checkpoint | Attach any relevant photos & documents
text | Description of Non-conformance
label | Raised due to : (delete not applicable) Internal Audit / Customer Complaint / Normal Working
section | Remedial Action
checkpoint | Attach any relevant photos & documents
text | Remedial Action
text | Action by
text | To be completed by
text | Date
section | Action to Prevent Recurrence
checkpoint | Attach any relevant photos & documents
text | Action to Prevent Recurrence
text | Action by
text | To be completed by
text | Date
section | Corrective Action Completed
checkpoint | Attach any relevant photos & documents
text | Corrective Action Completed
text | Actioned by
signoff | Sign Off Required Alpha Precast Quality Manager
checklist | Pre Start Talk Record
section | Pre Start Talk Record
checkpoint | Attach any relevant photos & documents
text | Date
text | Time
text | Changes in daily tasks
label | Meeting Held at Chullora Plant
label | Daily Task : Manufacture Precast Panels
section | Safety Requirements
checkpoint | PPE Must be mandatory worn
label | Clothing - HI VIS
label | Shoes – Steel cap boots
label | Safety glasses
label | Gloves
checkpoint | PPE as required
label | Ear plugs
label | Barrier cream
label | Double face shield when using Grinders
section | Safety Checks
checkpoint | Leads and electrical equipment to be check and tagged to be adhered to
checkpoint | All exclusions zone are marked when working around crane.
checkpoint | Keep work area clean at all the times
checkpoint | Environment
label | Rubbish to be placed in rubbish bins
label | Metal waste to be place in recycling bin
label | Concrete waste to be placed in concrete recycling bin
label | Keep work area clean around you, prior to making out next task
checkpoint | If you see someone is at risk of an unsafe area advise them and help them make it more safe
checkpoint | Crane operation by suitable qualified person
checkpoint | Forklift operation by suitable qualified person
checkpoint | Hot works, welding operation by suitable qualified person.
section | Issues to be covered
checkpoint | Attach any relevant photos & documents
text | Issues to be covered
section | Other issues addressed
checkpoint | Attach any relevant photos & documents
text | Other issues addressed
section | Issues to be followed up
checkpoint | Attach any relevant photos & documents
text | Issues to be followed up
section | Sign Off
checkpoint | Please sign off and add name
checklist | Site QA
checkpoint | Attach any relevant QA photos or documents
checklist | Site Photos
checkpoint | Please add site photos and attach relevant documents