## Project Structure
Folder Structure |  |  |  | Checklists | #NAME?
Site QA
Inground services
External ducting - Harvey Norman
|  |  | Mains incoming ducts | Inground services
|  |  | Pits | Inground services
|  |  | Ducting from pit to Tx | Inground services
|  |  | Pole light | Inground services
|  |  | Sign | Inground services
|  |  | gate - front north | Inground services
|  |  | fibre | Inground services
|  |  | Sign | Inground services
|  |  | Main earth | Inground services
|  |  | gate front south | Inground services
|  |  | Fibre duct from internal trench to data room | Inground services
|  |  | gate rear south | Inground services
Internal ducting
|  |  | A1 | Inground services
|  |  | A13 | Inground services
|  |  | A21,22 | Inground services
|  |  | A44 | Inground services
|  |  | A11 | Inground services
|  |  | A12 | Inground services
|  |  | A19,20 | Inground services
|  |  | A43 | Inground services
|  |  | A60,61,62,48 | Inground services
|  |  | A50 | Inground services
|  |  | A49 | Inground services
|  |  | A58 | Inground services
|  |  | A38 | Inground services
|  |  | A46 | Inground services
|  |  | A39 | Inground services
|  |  | A47,64 | Inground services
|  |  | A40 | Inground services
|  |  | A32 | Inground services
|  |  | A31 | Inground services
|  |  | A4,15,16,24 | Inground services
|  |  | A30 | Inground services
|  |  | A63 | Inground services
|  |  | A65 | Inground services
|  |  | A29 | Inground services
|  |  | A27 | Inground services
|  |  | A28 | Inground services
|  |  | A42 | Inground services
|  |  | A36 | Inground services
|  |  | A33 | Inground services
|  |  | A35 | Inground services
|  |  | A34 | Inground services
|  |  | A37,55,56,57 | Inground services
|  |  | A66 | Inground services
|  |  | A45 | Inground services
|  |  | Hydraulic area | Inground services
|  |  | pump room | Inground services
Cable Tray
Warehouse
|  |  | data | Cable Tray
|  |  | power | Cable Tray
|  |  | droppers | Cable Tray
Switchboard's
Switchboards
|  |  | Main Switchboard | Switchboards
|  |  | Office DB | Switchboards
|  |  | Pump room | Switchboards
First Fix
|  | Warehouse | A1 | First Fix Electrical
|  |  | A13 | First Fix Electrical
|  |  | A21,22 | First Fix Electrical
|  |  | A44 | First Fix Electrical
|  |  | A11 | First Fix Electrical
|  |  | A12 | First Fix Electrical
|  |  | A19,20 | First Fix Electrical
|  |  | A43 | First Fix Electrical
|  |  | A60,61,62,48 | First Fix Electrical
|  |  | A50 | First Fix Electrical
|  |  | A49 | First Fix Electrical
|  |  | A58 | First Fix Electrical
|  |  | A38 | First Fix Electrical
|  |  | A46 | First Fix Electrical
|  |  | A39 | First Fix Electrical
|  |  | A47,64 | First Fix Electrical
|  |  | A40 | First Fix Electrical
|  |  | A32 | First Fix Electrical
|  |  | A31 | First Fix Electrical
|  |  | A4,15,16,24 | First Fix Electrical
|  |  | A30 | First Fix Electrical
|  |  | A63 | First Fix Electrical
|  |  | A65 | First Fix Electrical
|  |  | A29 | First Fix Electrical
|  |  | A27 | First Fix Electrical
|  |  | A28 | First Fix Electrical
|  |  | A42 | First Fix Electrical
|  |  | A36 | First Fix Electrical
|  |  | A33 | First Fix Electrical
|  |  | A35 | First Fix Electrical
|  |  | A34 | First Fix Electrical
|  |  | A37,55,56,57 | First Fix Electrical
|  |  | A66 | First Fix Electrical
|  |  | A45 | First Fix Electrical
|  |  | Mains | First Fix Electrical
|  |  | Main Earth | First Fix Electrical
|  |  | sub mains office | First Fix Electrical
|  |  | sub mains pump | First Fix Electrical
|  |  | ware house socket outlets | First Fix Electrical
|  |  | roller doors | First Fix Electrical
|  |  | lighting | First Fix Electrical
|  |  | warehouse floor office | First Fix Electrical
|  |  | Pump room, | First Fix Electrical
|  |  | compressor room | First Fix Electrical
|  |  | canopy front | First Fix Electrical
|  |  | Quiet room | First Fix Electrical
|  |  | server room | First Fix Electrical
|  |  | lighting | First Fix Electrical
|  |  | emergency lighting | First Fix Electrical
office
|  |  | Mains | First Fix Electrical
|  |  | Main Earth | First Fix Electrical
|  |  | open plan office | First Fix Electrical
|  |  | offices | First Fix Electrical
|  |  | reception | First Fix Electrical
|  |  | boardroom | First Fix Electrical
|  |  | focus | First Fix Electrical
|  |  | utility | First Fix Electrical
|  |  | staff room | First Fix Electrical
|  |  | toilets staff | First Fix Electrical
|  |  | toilets reception | First Fix Electrical
|  |  | toilets ACC | First Fix Electrical
|  |  | break out | First Fix Electrical
|  |  | open plan factory | First Fix Electrical
|  |  | meeting | First Fix Electrical
|  |  | MD meeting | First Fix Electrical
|  |  | GM office | First Fix Electrical
|  |  | utility | First Fix Electrical
|  |  | locker room area | First Fix Electrical
|  |  | emergency lighting | First Fix Electrical
Pump room
|  |  | Mains | First Fix Electrical
|  |  | Main Earth | First Fix Electrical
|  |  | lighting | First Fix Electrical
|  |  | power | First Fix Electrical
|  |  | emergency lighting | First Fix Electrical
exterior
|  |  | Pole light | First Fix Electrical
|  |  | Front gate north | First Fix Electrical
|  |  | front gate south | First Fix Electrical
|  |  | rear gate | First Fix Electrical
Second Fix
|  | Warehouse | A1 | Second Fix
|  |  | A13 | Second Fix
|  |  | A21,22 | Second Fix
|  |  | A44 | Second Fix
|  |  | A11 | Second Fix
|  |  | A12 | Second Fix
|  |  | A19,20 | Second Fix
|  |  | A43 | Second Fix
|  |  | A60,61,62,48 | Second Fix
|  |  | A50 | Second Fix
|  |  | A49 | Second Fix
|  |  | A58 | Second Fix
|  |  | A38 | Second Fix
|  |  | A46 | Second Fix
|  |  | A39 | Second Fix
|  |  | A47,64 | Second Fix
|  |  | A40 | Second Fix
|  |  | A32 | Second Fix
|  |  | A31 | Second Fix
|  |  | A4,15,16,24 | Second Fix
|  |  | A30 | Second Fix
|  |  | A63 | Second Fix
|  |  | A65 | Second Fix
|  |  | A29 | Second Fix
|  |  | A27 | Second Fix
|  |  | A28 | Second Fix
|  |  | A42 | Second Fix
|  |  | A36 | Second Fix
|  |  | A33 | Second Fix
|  |  | A35 | Second Fix
|  |  | A34 | Second Fix
|  |  | A37,55,56,57 | Second Fix
|  |  | A66 | Second Fix
|  |  | A45 | Second Fix
|  |  | Mains | Second Fix
|  |  | Main Earth | Second Fix
|  |  | sub mains office | Second Fix
|  |  | sub mains pump | Second Fix
|  |  | ware house socket outlets | Second Fix
|  |  | roller doors | Second Fix
|  |  | lighting | Second Fix
|  |  | warehouse floor office | Second Fix
|  |  | Pump room, | Second Fix
|  |  | compressor room | Second Fix
|  |  | canopy front | Second Fix
|  |  | Quiet room | Second Fix
|  |  | server room | Second Fix
|  |  | lighting | Second Fix
|  |  | emergency lighting | Second Fix
office
|  |  | Mains | Second Fix
|  |  | Main Earth | Second Fix
|  |  | open plan office | Second Fix
|  |  | offices | Second Fix
|  |  | reception | Second Fix
|  |  | boardroom | Second Fix
|  |  | focus | Second Fix
|  |  | utility | Second Fix
|  |  | staff room | Second Fix
|  |  | toilets staff | Second Fix
|  |  | toilets reception | Second Fix
|  |  | toilets ACC | Second Fix
|  |  | break out | Second Fix
|  |  | open plan factory | Second Fix
|  |  | meeting | Second Fix
|  |  | MD meeting | Second Fix
|  |  | GM office | Second Fix
|  |  | utility | Second Fix
|  |  | locker room area | Second Fix
|  |  | emergency lighting | Second Fix
Pump room
|  |  | Mains | Second Fix
|  |  | Main Earth | Second Fix
|  |  | lighting | Second Fix
|  |  | power | Second Fix
|  |  | emergency lighting | Second Fix
exterior
|  |  | Pole light | Second Fix
|  |  | Front gate north | Second Fix
|  |  | front gate south | Second Fix
|  |  | rear gate | Second Fix

## Inground services
type | name
checklist | Inground Services
section | Ducts and Conduits
checkpoint | Correct size installed
checkpoint | Start and finish locations correct as per plan
checkpoint | separation from other services
checkpoint | Clean inside and in good condition
section | Electrical Pits
checkpoint | Set out correct
checkpoint | Correct size installed
checkpoint | Duct entry holes sealed / water proofed
checkpoint | Pits installed to correct height and level
checkpoint | Clean inside and in good condition
section | Light Pole Foundations
checkpoint | Set out correct
checkpoint | Ducting in correct position - centre of cage
checkpoint | Correct Cage Installed
checkpoint | Cage installed to correct height / level
checkpoint | Ground Plant pole installed to correct height / level
section | Photos

## First Fix Electrical
type | name
checklist | QA - First Fix
section | Flush Boxes
checkpoint | Fire Rated or Acoustic
checkpoint | Height as per plan
checkpoint | Location as per plan
checkpoint | Intumescent Pad In Place
section | Cabling
checkpoint | Power cables installed correctly
checkpoint | Lighting cables installed correctly
checkpoint | Equipment cables installed correctly
checkpoint | Circuits clearly labelled
checkpoint | Separation between Data and Power at 300mm or as specified
checkpoint | All cables secured via cable ties with ends cut
section | Cable Ladder
checkpoint | Minimum 25% spare capacity left on cable tray
section | QA - Lights
checkpoint | Setout Correct
checkpoint | Cabling in correct location
checkpoint | Emergency/ Exit Lighting
checkpoint | Nogging installed for Electrical Services
section | Seismic Bracing
checkpoint | For Lighting
checkpoint | Cable Tray
checkpoint | Switchboard
section | Conduits
checkpoint | Correct size installed
checkpoint | Location as per plan
checkpoint | All conduits glued & watertight
checkpoint | Clean inside and in good condition
checkpoint | Stainless screws used
section | Photos

## Cable Tray
Section | Cable Ladder
Checkpoint | Unistrutt Filed & Painted
Checkpoint | Hangers Spaced as Specified
Checkpoint | Correct Size Ladder Installed
Checkpoint | Ladder Joined Correctly
Checkpoint | Hangers Sceismicly Restrained as per Design
Checkpoint | Ladder Fastened to Hangers
Checkpoint | Correct Anchors used fixing to Ceiling / Walls
Checkpoint | Cable Ladder Bonded
section | Photos

## Switchboards
section | Switchboard
checkpoint | Spatial certificate signed if required
checkpoint | Fixings installed in wall correctly if board is wall mounted
checkpoint | All clearances sighted to ensure location is compliant
checkpoint | All cables correctly installed in protection device and earth and neutral bars and fully secured
checkpoint | Cables neatly dressed
checkpoint | Phase tabs on chassy covered
checkpoint | All earths and neutrals labelled to match phase numbers
checkpoint | Switchboard is clean on the inside and outside
checkpoint | Masking blanks installed
checkpoint | DB legend installed
checkpoint | Feisst label on the door installed
section | Photos

## Second Fix Electrical
type | name | values
checklist | QA - Second fix
section | Power Outlets
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Outlet Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Switches
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Light switch Installed level
checkpoint | Circuit Tested and results recorded
checkpoint | Description Labelled on the outlet face with vivid and with dymo labeller on cover plate and ensure label is level
section | Light Fixtures
checkpoint | Correct type installed
checkpoint | Correctly installed with terminations all secured properly
checkpoint | Tested for operation
checkpoint | Correctly installed with stainless screws & 90 / 45 angle
section | Photos

## SM Weekly Checklist
type | name
checklist | FEL SM Weekly Site Checklist
section | Monday
checkpoint | Prestart Meeting with Team
checkpoint | Health Check
checkpoint | Review Tasks for the week
checkpoint | Identify Targets Including Hours
checkpoint | Approve hours by 9AM for previous week
checkpoint | Sign off Subcontractor Hours & Submit
checkpoint | Review SWMS
checkpoint | Site Toolbox Meeting
checkpoint | SSSP in Order
section | Tuesday
checkpoint | Follow up outstanding RFI's with PM
section | Wednesday
checkpoint | Review Roadblocks & Follow Up if still unresolved
checkpoint | QAs up to date
section | Thursday
checkpoint | Weekly planner filled out for week ahead
checkpoint | Roadblocks identified and actioned
checkpoint | Materials organized for week ahead
checkpoint | Plans printed with any relevant notes added
section | Friday
checkpoint | Submit Toolbox minutes to main contractor and FEL office
checkpoint | Job Cards up to date and submitted
checkpoint | Team tasks for week ahead filled out on whiteboard