## QA Folder Structure
QA Folder Structure |  |  |  | Checklists
Fabrication & Site QA
Apartment 1
CLADDING
Delap/Condition Report
Demolition
Photo/evidece of exisiting structure
Note any condition report or latent condition
Framing
Photo/evidence of top hat, paper/ flashing tape joint
New cladding
Photo/evidence of new cladding
Completion
Photo/evidence of render/paint
Handover
Photo of balcony completion
photo of all fixtures reinstalled
TILING
Current condition
Photo/evidece of exisiting structure
Note any condition report or latent condition
Owners remediation decision
Signed form
demolition
Photo/evidence
re screed
Photo/evidence
waterproofing
Photo/evidence
tiling
Photo/evidence
handover
Photo/evidence
| Apartment 2 |  |  | As Above
Apartment 3
Apartment 4
Apartment 5
Apartment 6
Apartment 7
Apartment 8
Apartment 9
Apartment 10
Apartment 11
Apartment 12
Apartment 13
Apartment 14
Apartment 15
Apartment 16
Apartment 17
Apartment 18
Apartment 19
Apartment 20
Apartment 21
Apartment 22
Apartment 23
Apartment 24
Apartment 25
Apartment 26
Apartment 27
Apartment 28
Apartment 29
Apartment 30
Apartment 31
Apartment 32
Apartment 33
Apartment 34
Apartment 35
Apartment 36
Apartment 37
Apartment 38
Apartment 39
Apartment 40
Apartment 41
Apartment 42
Apartment 43
Apartment 44
Apartment 45
Apartment 46
Apartment 47
Apartment 48
Apartment 49
Apartment 50
Apartment 51
Apartment 52
Apartment 53
Apartment 54
Apartment 55
Apartment 56
Apartment 57
Apartment 58
Apartment 59
Apartment 60
Apartment 61
Apartment 62
Apartment 63
Apartment 64
Apartment 65
Apartment 66
Apartment 67
Apartment 68
Apartment 69
Apartment 70
Apartment 71
Apartment 72
Apartment 73
Apartment 74
Apartment 75
Apartment 76
Apartment 77
Apartment 78
Apartment 79
Apartment 80
Apartment 81
Apartment 82
Apartment 83
Apartment 84
Common Areas
Corridor 2 LG
Corridor 2 LG (Courtyard)
Corridor 6 LG
Corridor 6 LG (Courtyard)
Corridor 2 GF (Eastern Elevation)
Common Balcony (Western Elevation)
Entry
Fence Paint
North
Delap/Condition Report
Photo/evidece of exisiting structure
Note any condition report or latent condition
New Painting
Photo/evidence of new painting
Completion
Photo/evidence of render/paint
Handover
Photo
East
South
West

## ITPs Checklists
type | name | values | prefix | postfix
checklist-flat | Dispatch / Document Upload Checklist
checkpoint | Document type selected and uploaded below
select | document type uploaded | Butterfly Test Record,Sealant Inspection Record,Sealant Deglazing Checklist,Sealant Silicone Application Checklist
text | date
checklist-flat | Fabrication
checkpoint | Panel delivery & material finish
checkpoint | Cutting flat sheet & Flat panel folding
label | Photo's lodged to CONQA
checklist-flat | Receival of panels onsite Checklist
checkpoint | Check deliveries of materials for damage that may have occurred in transportation on truck prior to unloading
checkpoint | Delivered panels have protective film and are free of damage
checkpoint | Stiffener installed
checkpoint | Delivery Docket provided
checklist-flat | Base framing Checklist
checkpoint | Check Latent condition / Alignment of existing panel prior to installation of panel
checkpoint | Base framing observed on site consistant with documentaion
checklist-flat | Installation of panels Checklist
checkpoint | Check Latent condition / Alignment of existing panel prior to installation
checkpoint | Fixing and fixtures are installed as documented in 'Crown Metropol Hotel - Cladding Replacement IFC (Rev D)'
checkpoint | Panel installed in accordance with 'Crown Metropol Hotel - Cladding Replacement IFC (Rev D)'
checkpoint | Final check "per level"
checkpoint | Panels are installed as documented and within tolerance
checkpoint | Check for damages / scratches

## Panel Numbers
Zone 1 | Zone 2 | Zone 3 | Zone 4 | Zone 5 | Zone 6 | Zone 7 | Zone 8 | Zone 9 | Zone 10 | Zone 11 | Zone 12
TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA | TBA