## Sheet1
type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist | Concrete Slabs "on grade" Checklist |  |  |  |  | Yes | Concrete Slabs Checklist | 033afa97-7aa0-40be-b56c-2b133622d0df
section | Prepour
checkpoint | General Pour Information |  | Delete
checkpoint | Pour Details Complete |  | Delete Pass Fail option |  |  | Need to create another checklist for "Suspended Slabs" Will be similar but have some options removed and others added
dropdown | Slab Type: | Fibre Slab, Mesh Slab, Other, PT Slab,Combi Slab
dropdown | Pour Description: | Internal Building slab, Other, Warehouse slab ,Freezer wear slab
textbox | Pour time & date:
textbox | Pour size: (m2)
textbox | Concrete Volume: (m3)
textbox | Latest drawings used: |  | Delete
checkpoint | Water on site |  | Delete
checkpoint | Power on site |  | Delete
checkpoint | Preliminary Pour Information |  | Delete
checkpoint | Beam test results
checkpoint | Blinding checked
checkpoint | Datum sited and correct
checkpoint | Formwork checked for line & level
checkpoint | Movement joints in place and correct
checkpoint | Isolations complete and checked
checkpoint | Spoutings & downpies in place
checkpoint | Building water & weather proof
checkpoint | Polythene slip layer in place and correct
checkpoint | Reinforcing in place and correct
checkpoint | Reo cover checked
checkpoint | Reinforcing type:
tickbox | Single layer mesh
tickbox | Double layer mesh
tickbox | Trimmer bars
tickbox | Conventional re-bar
textbox | Insert Size
checkpoint | Supplier Approved:
dropdown |  | Other,Complete Reo, Nauriha
textbox | If other please specify:
checkpoint | Installed by:
dropdown |  | Other,Conslab, Complete Reo, Nauriha
textbox | If other please specify:
checkpoint | Supplementary pour information complete
textbox | Site Supervisor/Leading Hand
dropdown | Lighting provided by: | Conslab,Client
dropdown | Light towers required (1-5) | 2, 3, 4, 5,1
button | Light Towers Confirmed | No,Yes
dropdown | Type of finish | Heavy broom, Less than burnished, Light broom, Medium broom, Pan texture,Burnished
textbox | Product name:
textbox | If other please specify product name:
dropdown | Saw cut method: | Soft cut, Wet saw,None
dropdown | Slurry control: | Squeegee, Vacuum, Wet vac,Other
textbox | If other please specify:
dropdown | Saw cut pattern: | Conslab discretion, Main contractors Instruction,As per drawings
checkpoint | Concrete Supply & placing Information Complete
dropdown | Supplier: | Bridgeman, ChCh Readymix, Firth, Other, Stevenson,Allied
textbox | If other please specify company name:
textbox | Primary supply plant:
textbox | Back up plant:
textbox | Stength Grade: (MPa)
textbox | Mix code:
textbox | Target Slump: (mm)
textbox | Tolerance: (+/-)
button | Fibre: | No,Yes
textbox | Type:
textbox | Dose:
note | Testing at plant requested:
tickbox | Slump
tickbox | Air
tickbox | Bleed
tickbox | Cylinders
tickbox | Fibre wash out
note | Site testing and technician confirmed:
tickbox | Slump
tickbox | Air
tickbox | Conc Temperature
tickbox | Cylinders
button | External testing required: | No,Yes
textbox | If yes please specify the details and by who:
dropdown | Method of placing: | Crane & skip, Direct discharge, Line pump,Boom pump
textbox | Pump Supplier confirmed: |  | Drop down option "Pioneer" |  |  | Add in "Placers" option then give drop down menu for "Conslab, Concrete Consultants, Performance Concrete"
textbox | Number of pumps required:
button | Truck Wash allowed on site: | No,Yes
checkpoint | Final Pre pour check & sign off
checkpoint | Pour area blown out & free of contaminants
textbox | Date slab can be lightly trafficked:
textbox | Date slab can be fully loaded:
textbox | Person responsible for slab protection & contact:
section | Pour process
checkpoint | Concrete Test Records |  |  |  | Add to pour test records
checkpoint | Concrete consistency & slump records attached
checkpoint | Air & Bleed tests attached
textbox | Concrete Temperature
checkpoint | Concrete Adjustments
checkpoint | Concrete adjustments complete |  | Delete
button | Retarder added: | No,Yes
textbox | Confirm dose:
button | Accelerator added: | No,Yes
textbox | Confirm dose:
checkpoint | Environment & Finishing
checkpoint | Environment & Finishing Complete |  | Delete
textbox | External weather forecast (Attach Record):
textbox | Ambient temperature:
textbox | Relative Humidity: (RH)
textbox | Wind speed at pour face:
button | Anti vap used: | No,Yes
textbox | Record when anti vap used (Attach photo:)
checkpoint | Process Timings
checkpoint | Pour start time ( first truck on site )
textbox | Time: (1st Docket)
checkpoint | Pour Finish time ( last truck on site )
textbox | Time: (last docket)
checkpoint | Time initial finishing starts ( walk behind )
textbox | Time:
checkpoint | Confirm bleed water visually evaporated
textbox | Time:
checkpoint | Confirm boot indent <6mm
textbox | Time:
checkpoint | Time ride on panning starts
textbox | Time:
checkpoint | Time ride on floating starts
textbox | Time:
checkpoint | Time final trowling starts
textbox | Time:
checkpoint | Time final finishing complete
textbox | Time:
checkpoint | Time curing applied
textbox | Time:
checkpoint | Additional Information
checkpoint | Gaps or interuptions in supply
textbox | Record time:
textbox | Concrete volume at time:
textbox | Reason:
textbox | Any other issues:
section | Post-pour
checkpoint | Pour Information | Delete
checkpoint | Post Pour Inspection
textbox | Date of inspection:
textbox | Inspection carried out by:
checkpoint | Flatness/Level testing
checkpoint | Level/Flatness spec
dropdown |  | EN 15620 FM1, EN 15620 FM2, EN 15620 FM3, TR34 FM1, TR34 FM2, TR34 FM3,BS 8204 SR2
textbox | Date survey carried out:
textbox | Carried out by:
radio | Polythene in place: | No,Yes
checkpoint | Curing
checkpoint | Curing method
dropdown |  | Curing blankets,Curing blankets; Spray on membrane; Wet under poly,Spray on membrane,Wet under poly
textbox | Date curing blankets or polythene removed:
textbox | Surface treatment applied (record date:)
dropdown | Surface treatment applied | N/A,N/A; Yes; No,No,Yes
dropdown | Surface treatment type | other,Conslab diamond, Sinak |  | Add Sinak
textbox | If other please specify product name:
checkpoint | Finish/Aesthetics
dropdown | General surface finish | Fair, Good, Poor,Excellent
checkpoint | Edge finishing
checkpoint | Edge forms straight
checkpoint | Level across joints, edges and columns
checkpoint | Isolation and formwork removed and tidy
checkpoint | Saw cutting to correct depth, straight & free of chipping
checkpoint | Final assessment score
checkpoint | Main Contractor sign off required
textbox | Confirmed by:
section | Pour Test Records
checkpoint | Concrete Strength Results Attached
checkpoint | Level/Flatness survey attached
checkpoint | Fibre Count Attached
checkpoint | Mesh Test Cert Attached
checkpoint | Observation/Remedials |  | Move to Post Pour
checkpoint | Concrete Dockets
checklist | Columns - |  |  |  |  | Yes | Vertical - Columns Checklist | 094afd93-6553-4fda-a86f-e7631ec3e55e
section | Plans/RFI's |  | Delete
checkpoint | Plan- Drawing No, Rev: |  | Delete
checkpoint | Sections- Drawing No, Rev: |  | Delete
checkpoint | Additional Plan Reviews |  | Delete
checkpoint | RFI's Aconex reference details |  | Delete
section | Workface Start/Pour/Completion Dates
checkpoint | All Dates recorded below |  | Delete
textbox | Area Received Date:
textbox | Works Started Date:
textbox | Pour Date:
textbox | Handover Date:
checkpoint | Area and substrates acceptable
section | Column Pre Pour
checkpoint | General Pour Information Complete
textbox | Column Reference
textbox | Grid line reference
textbox | Offset from Grid lines |  | Delete
textbox | Concrete Volume: (m3)
checkpoint | Formwork checked for line & height against FFL
checkpoint | Formwork are propped & supported based on installation spec
textbox | Reference Line (R.L) at the top of the Column:
checkpoint | Reinforcing in place
checkpoint | Reo spacings checked
checkpoint | Correct Cover Top & Bottom & Sides
checkpoint | Engineer Inspection / Reo Sign off Reuired
textbox | Date and Time
checkpoint | Supplementary pour information complete
dropdown | Reinforcing type/ Detail Sheet for the Steel
checkpoint | Supplier Approved:
dropdown |  | Other,Complete Reo
textbox | If other please specify:
checkpoint | Installed by:
dropdown |  | Conslab, Other,Complete Reo
textbox | If other please specify:
checkpoint | Cover to reinforcing recorded
checkpoint | Checked against shop drawings
checkpoint | Reo inspection and sign off
section | HD Bolts
checkpoint | Template orientation check
checkpoint | Dimensions cl to grids measured
checkpoint | Bolt height above FFL
section | Concrete
checkpoint | Pour Details Completed
textbox | Pour time & date:
checkpoint | Aquaron additive
checkpoint | Fibre dosage
checkpoint | Volume expected/Actual |  | Delete
checkpoint | Pump booked | Placement Method, give drop down options for Boom Pump, Line Pump, Skip
checkpoint | Concrete booked
checkpoint | Placers available |  | Delete
checkpoint | RL & finish given to placing team
button | Technician booked | Not required,Yes
section | Post-pour
checkpoint | Pour Information (true) |  | Delete
textbox | Pour date:
textbox | Date of inspection:
textbox | Inspection carried out by:
checkpoint | Level checked and correct
checkpoint | Curing (true)
dropdown | Curing method | Curing blankets,Hessian,Spray on membrane,Wet under poly |  |  |  | Delete
textbox | Surface treatment applied (record date:)
dropdown | Surface treatment applied | N/A ,No,Yes
dropdown | Curing Compound used: | others,Sinak S102
textbox | If other please specify product name:
checkpoint | Concrete finish review
textbox | If other please specify :
checkpoint | Edge finishing
checkpoint | Edge forms straight
checkpoint | Level across edges of the columns
checkpoint | Isolation and formwork removed and tidy
checkpoint | Main Contractor sign off required |  | Delete
textbox | Confirmed by: |  | Delete
section | Observation/Remedials
checkpoint | Observations / Remedials Checked
section | Close Out
checkpoint | Bolt location, height and orientation
checkpoint | Concrete dockets attached |  | Add to folder called "Pour Records"
checkpoint | Concrete test results |  | Add to folder called "Pour Records"
checkpoint | Curing completed and signed off
checkpoint | Shutter stripped and area cleaned
section | Handover |  | Delete
checkpoint | Conslab Rep Sign Off |  | Delete
signoff | Request Sign Off |  | Delete
checkpoint | Scentre Group Sign Off |  | Delete
signoff | Request Sign Off |  | Delete
checklist | Holdup/Delay - |  |  |  |  | Yes | Holdup/Delay - | 32bbaedd-deae-420c-880b-b39be27f79c3
checkpoint | Delay |  | Delete Pass or fail
textbox | Reasons for delay |  | Add 'Date and Time of Delay"
textbox | Total delay time
checklist | Toolbox Talk - |  |  |  |  | Yes | Toolbox Talk - | 64837f3b-33b6-470c-a178-c25c8ada220a
checkpoint | Toolbox Talk Details
textbox | Foreman / Supervisor:
textbox | Date:
textbox | Main Contractor: |  | Delete (we don’t need to capture this every day as the main contractor doesn’t change for the project and this info has been caught in the job set up details)
textbox | Client: |  | Delete (we don’t need to capture this every day as the client doesn’t change for the project and this info has been caught in the job set up details)
checkpoint | Meeting Details / Attendees
textbox | Carried Out by:
textbox | Signed:
note | All attendees names listed below and signature / photo attached (click on paperclip to add photo / signatures)
checkpoint | Site Activities Listed - any corrective actions discussed, actioned, reviewed and closed out
note | Site activity, safe work practices, accident, incident investigations discussed
checkpoint | Near Misses / Incidents to report - any corrective actions discussed, actioned, reviewed and closed out
note | Near Misses / Incidents to report (name of person involved, type of injury)
checkpoint | Employee issues raised and resolved within specified timeframe (Pass once issues have been resolved)
textbox | Employee issues raised:
textbox | Date to be resolved by:
checkpoint | Safe Observations reviewed / discussed
textbox | Review Date:
checkpoint | Task Analysis/Job Safety Analysis (JSA) completed/reviewed
textbox | Checked By:
textbox | Date:
textbox | Received By
textbox | Date:
signoff | Request Signoff
checklist | Foundations |  |  |  |  | Yes | Foundations | a189917d-d728-4597-9d99-b3b3ee63c399
section | Details |  | Delete Details
checkpoint | Details Completed
note | 1st Plan
textbox | Revision No:
note | 2nd Plan
textbox | Revision No:
note | 3rd Plan
textbox | Revision No:
textbox | Date area received:
textbox | Works started dates:
textbox | Pour Date: |  |  | Roll all this together under a menu called "set up"
textbox | Handover Date:
section | Prestart |  |  | Delete
checkpoint | Area accessible and substrate acceptable
section | Set Up
checkpoint | Datum by Surveyor in area
checkpoint | Gridline on profiles
checkpoint | Base prep height check
checkpoint | HD Bolt template orientation and location info
section | Prelim / Before Works Commence
checkpoint | Base prep within tolerance, +0-20mm
checkpoint | Work area barricaded
checkpoint | Excavation correct
checkpoint | Site Concrete required
checkpoint | Formwork Required
checkpoint | Photos taken
section | Formwork
checkpoint | RL transposed onto boxing
checkpoint | Adequately braced
checkpoint | Measure cover to reinforcing
textbox | Results: |  | Delete
checkpoint | Service penetrations installed
checkpoint | Formwork dimensions checked to grids
textbox | Measures: |  | Delete
checkpoint | Photos taken
section | HD Bolts | HD Bolts and Dross Backs
checkpoint | Template orientation check |  |  | Add Dross Back Template and orentation Check
checkpoint | Dimensions to grids measured |  |  | Add Dross Back Demension to grids
checkpoint | Bolt height above footing top
section | Additional
checkpoint | Reo sign off
checkpoint | Engineers Inspection booked
textbox | Time and date:
section | Concrete
checkpoint | Mix Code | Drop Down Menu |  | Give Options 202P,302P, 402P then option for other with a text box
checkpoint | Admixtures | Add drop down menu for "RT Con 1" and "RT Con 2"
checkpoint | Pour date
checkpoint | Pump booked | Change to Placing Method |  | Give Drop down options, Boom Pump, Line Pump, Skip. |  |  |  | If pump then drop down menu for pump supplier (Pioneer or other with text box)
checkpoint | Concrete booked
checkpoint | Placers available |  | Drop down menu "Conslab" or "Others"
checkpoint | Testing booked
section | Curing
checkpoint | Method
checkpoint | Time and Date undertaken
checkpoint | Photos taken
section | Close Out
checkpoint | Concrete finish type
checkpoint | RL checked
checkpoint | Bolts checked
checkpoint | Concrete dockets attached |  | Move to separate folder called "pour records"
checkpoint | Concrete test results
checkpoint | Shutter stripped and area cleaned
section | Handover
checkpoint | Conslab Rep Sign Off
signoff | Request Sign Off
checklist | Elevated Slabs ITP |  |  |  |  | Yes | Elevated Slabs ITP | c7ad386e-b858-43bd-a45a-dfede29c5f3d
section | Plans/RFI's
checkpoint | First Plan
checkpoint | Second Plan
checkpoint | Third Plan
checkpoint | RFI's Procore reference details
section | Workface Start/Pour/Completion Dates
checkpoint | All Dates recorded below
textbox | Area Received Date:
textbox | Pour Date:
textbox | Handover Date
section | Prestart
checkpoint | Work area safety rails
checkpoint | Traydeck Complete
checkpoint | Penetrations, setdowns or HD bolts identified on plan
checkpoint | Tray deck supported as per design
checkpoint | Datum provided by surveyor
checkpoint | Measure and record levels of beams mid span and at columns
section | Formwork
checkpoint | Stop Ends conform to Engineer's specification
checkpoint | Service penetrations layout checked
tickbox | Measurements to grids and dimensions recorded
section | Reinforcing
checkpoint | Cover to reinforcing recorded
checkpoint | Checked against shop drawings
checkpoint | Reo sign off
section | HD Bolts
checkpoint | Template orientation check
checkpoint | Dimensions cl to grids measured
checkpoint | Bolt height above FFL
section | Concrete
checkpoint | Mix code
checkpoint | Volume expected/Actual
checkpoint | Pour date/actual time and date
checkpoint | Pump booked
checkpoint | Concrete booked
checkpoint | Placers available
checkpoint | RL & finish given to placing team
checkpoint | Testing required
checkpoint | Weather - temp, wind, RH, rain
section | Finish Level Check
checkpoint | Concrete finish review
tickbox | Results attached:
checkpoint | SR2 measurements taken
tickbox | Results attached:
checkpoint | Date and time SR2 measured:
textbox
note | SR2 measurements: To be taken as one result for each ten square metres of the pour area. Take measurements parallel and perpendicular to grids/beams. Each test to be recorded as a pass
section | Close Out
checkpoint | Curing signed off and checked.
checkpoint | Concrete dockets attached
checkpoint | Concrete test results
checkpoint | Shutter stripped and area cleaned
section | Handover
checkpoint | Conslab Rep Sign Off
signoff | Request Sign Off
checkpoint | H&R Group Sign Off
signoff | Request Sign Off
checklist | Defect Number: |  |  |  |  | Yes | Defect Number: | cb88de19-8c90-45a3-b6b7-92a15bce824c
checkpoint | Defect Status
button | Defect Status: | Closed,Open
checkpoint | Defect Details
dropdown | Type of project: | Slab on Grade,Vertical
textbox | Defect Number:
textbox | Defect Location:
textbox | Description of Defect:
checkpoint | Date of inspection:
textbox | Date of inspection:
checkpoint | Photos attached of defect before remedial
checkpoint | Date of remedial:
textbox | Date of remedial:
checkpoint | Photos attached of defect after remedial
checkpoint | Remedial:
textbox | Cost of remedial work:
radio | Who is responsible for fixing Defect: | Client,Conslab,Main Contractor
textbox | Who is responsible for managing the fixing of defect (Conslab)
checkpoint | Defect has been closed
signoff | Add Final Sign Off