## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | Concrete Slabs "on grade" Checklist |  |  |  |  | Yes | Concrete Slabs Checklist | 033afa97-7aa0-40be-b56c-2b133622d0df
checkpoint-group | Prepour
checkpoint-no-status | Pour Details Complete
select | Slab Type: | Fibre Slab, Mesh Slab, Other, PT Slab,Combi Slab
select | Pour Description: | Internal Building slab, Other, Susbpended slab, Warehouse slab ,Freezer wear slab
text | Pour time & date:
text | Pour size: (m2)
text | Concrete Volume: (m3)
checkpoint-status | Beam test results ok
checkpoint-status | Blinding checked and ok
checkpoint-status | Datum sited and correct
checkpoint-status | Formwork checked for line & level
checkpoint-status | Movement joint in place and correct
checkpoint-status | Isolations complete and checked
checkpoint-status | Spoutings & downpies in place
checkpoint-status | Building water & weather proof
checkpoint-status | Polythene slip layer in place and correct
checkpoint-status | Reinforcing in place and correct
checkpoint-status | Reo cover checked
checkpoint-status | Reinforcing type:
boolean | Single layer mesh
boolean | Double layer mesh
boolean | Trimmer bars
boolean | Conventional re-bar
text | Insert Size
checkpoint-status | Supplier Approved:
select |  | Other,Complete Reo
text | If other please specify:
checkpoint-status | Installed by:
select |  | Other,Conslab
text | If other please specify:
checkpoint-status | Supplementary pour information complete
text | Site Supervisor/Leading Hand
select | Lighting provided by: | Conslab,Client
select | Light towers required (1-5) | 2, 3, 4, 5,1
button | Light Towers Confirmed | No,Yes
select | Type of finish | Heavy broom, Less than burnished, Light broom, Medium broom, Pan texture,Burnished
text | Product name:
text | If other please specify product name:
select | Saw cut method: | Soft cut, Wet saw,None
select | Slurry control: | Squeegee, Vacuum, Wet vac,Other
text | If other please specify:
select | Saw cut pattern: | Conslab discretion, Main contractors Instruction,As per drawings
checkpoint-status | Concrete Supply & placing Information Complete
select | Supplier: | Bridgeman, ChCh Readymix, Firth, Other, Stevenson,Allied
text | If other please specify company name:
text | Primary supply plant:
text | Back up plant:
text | Stength Grade: (MPa)
text | Mix code:
text | Target Slump: (mm)
text | Tolerance: (+/-)
button | Fibre: | No,Yes
text | Type:
text | Dose:
label | Testing at plant requested:
boolean | Slump
boolean | Air
boolean | Bleed
boolean | Cylinders
boolean | Fibre wash out
label | Site testing and technician confirmed:
boolean | Slump
boolean | Air
boolean | Conc Temperature
boolean | Cylinders
button | External testing required: | No,Yes
text | If yes please specify the details and by who:
select | Method of placing: | Crane & skip, Direct discharge, Line pump,Boom pump
select | Pump Supplier confirmed: | Pioneer
select | Placers | Conslab,Concrete Consultants,Performance Concrete
text | Number of pumps required:
button | Truck Wash allowed on site: | No,Yes
checkpoint-status | Final Pre pour check & sign off
checkpoint-status | Pour area blown out & free of contaminants
text | Date slab can be lightly trafficked:
text | Date slab can be fully loaded:
text | Person responsible for slab protection & contact:
checkpoint-group | Pour process
checkpoint-status | Concrete Test Records
checkpoint-status | Concrete consistency & slump records attached
checkpoint-status | Air & Bleed tests attached
text | Concrete Temperature
checkpoint-status | Concrete Adjustments
button | Retarder added: | No,Yes
text | Confirm dose:
button | Accelerator added: | No,Yes
text | Confirm dose:
checkpoint-status | Environment & Finishing
text | External weather forecast (Attach Record):
text | Ambient temperature:
text | Relative Humidity: (RH)
text | Wind speed at pour face:
button | Anti vap used: | No,Yes
text | Record when anti vap used (Attach photo:)
checkpoint-status | Process Timings
checkpoint-status | Pour start time ( first truck on site )
text | Time: (1st Docket)
checkpoint-status | Pour Finish time ( last truck on site )
text | Time: (last docket)
checkpoint-status | Time initial finishing starts ( walk behind )
text | Time:
checkpoint-status | Confirm bleed water visually evaporated
text | Time:
checkpoint-status | Confirm boot indent <6mm
text | Time:
checkpoint-status | Time ride on panning starts
text | Time:
checkpoint-status | Time ride on floating starts
text | Time:
checkpoint-status | Time final trowling starts
text | Time:
checkpoint-status | Time final finishing complete
text | Time:
checkpoint-status | Time curing applied
text | Time:
checkpoint-status | Additional Information
checkpoint-status | Gaps or interuptions in supply
text | Record time:
text | Concrete volume at time:
text | Reason:
text | Any other issues:
checkpoint-group | Post-pour
checkpoint-status | Post Pour Inspection
text | Date of inspection:
text | Inspection carried out by:
checkpoint-status | Flatness/Level testing
checkpoint-status | Level/Flatness spec
select |  | EN 15620 FM1, EN 15620 FM2, EN 15620 FM3, TR34 FM1, TR34 FM2, TR34 FM3,BS 8204 SR2
text | Date survey carried out:
text | Carried out by:
radio | Polythene in place: | No,Yes
checkpoint-status | Curing
checkpoint-status | Curing method
select |  | Curing blankets,Curing blankets; Spray on membrane; Wet under poly,Spray on membrane,Wet under poly
text | Date curing blankets or polythene removed:
text | Surface treatment applied (record date:)
select | Surface treatment applied | N/A,N/A; Yes; No,No,Yes
select | Surface treatment type | other,Conslab diamond,Sinak
text | If other please specify product name:
checkpoint-status | Finish/Aesthetics
select | General surface finish | Fair, Good, Poor,Excellent
checkpoint-status | Edge finishing
checkpoint-status | Edge forms straight
checkpoint-status | Level across joints, edges and columns
checkpoint-status | Isolation and formwork removed and tidy
checkpoint-status | Saw cutting to correct depth, straight & free of chipping
checkpoint-status | Final assessment score
checkpoint-status | Main Contractor sign off required
text | Confirmed by:
checkpoint-status | Observation/Remedials
checkpoint-group | Pour Test Records
checkpoint-status | Concrete Test Records
checkpoint-status | Concrete consistency & slump records attached
checkpoint-status | Air & Bleed tests attached
checkpoint-status | Concrete Strength Results Attached
checkpoint-status | Level/Flatness survey attached
checkpoint-status | Fibre Count Attached
checkpoint-status | Mesh Test Cert Attached
checkpoint-status | Concrete Dockets
checklist-sectioned | Columns - |  |  |  |  | Yes | Vertical - Columns Checklist | 094afd93-6553-4fda-a86f-e7631ec3e55e
checkpoint-group | Workface Start/Pour/Completion Dates
checkpoint-status | Area and substrates acceptable
text | Area Received Date:
text | Works Started Date:
text | Pour Date:
text | Handover Date:
checkpoint-group | Column Pre Pour
checkpoint-status | General Pour Information Complete
text | Column Reference
text | Grid line reference
text | Concrete Volume: (m3)
checkpoint-status | Formwork checked for line & height against FFL
checkpoint-status | Formwork are propped & supported based on installation spec
text | Reference Line (R.L) at the top of the Column:
checkpoint-status | Reinforcing in place
checkpoint-status | Reo spacings checked
checkpoint-status | Correct Cover Top & Bottom & Sides
checkpoint-status | Engineer Inspection / Reo Sign off Reuired
text | Date and Time
checkpoint-status | Supplementary pour information complete
text | Reinforcing type/ Detail Sheet for the Steel
checkpoint-status | Supplier Approved:
select |  | Other,Complete Reo
text | If other please specify:
checkpoint-status | Installed by:
select |  | Conslab, Other,Complete Reo
text | If other please specify:
checkpoint-status | Cover to reinforcing recorded
checkpoint-status | Checked against shop drawings
checkpoint-status | Reo inspection and sign off
checkpoint-group | HD Bolts
checkpoint-status | Template orientation check
checkpoint-status | Dimensions cl to grids measured
checkpoint-status | Bolt height above FFL
checkpoint-group | Concrete
checkpoint-status | Pour Details Completed
text | Pour time & date:
checkpoint-status | Aquaron additive
checkpoint-status | Fibre dosage
checkpoint-status | Pump booked
checkpoint-status | Concrete booked
checkpoint-status | RL & finish given to placing team
button | Technician booked | Not required,Yes
checkpoint-group | Post-pour
checkpoint-status | Level checked and correct
text | Pour date:
text | Date of inspection:
text | Inspection carried out by:
checkpoint-status | Curing (true)
text | Surface treatment applied (record date:)
select | Surface treatment applied | N/A ,No,Yes
select | Curing Compound used: | others,Sinak S102
text | If other please specify product name:
checkpoint-status | Concrete finish review
text | If other please specify :
checkpoint-status | Edge finishing
checkpoint-status | Edge forms straight
checkpoint-status | Level across edges of the columns
checkpoint-status | Isolation and formwork removed and tidy
checkpoint-group | Observation/Remedials
checkpoint-status | Observations / Remedials Checked
checkpoint-group | Close Out
checkpoint-status | Bolt location, height and orientation
checkpoint-status | Concrete dockets attached
checkpoint-status | Concrete test results
checkpoint-status | Curing completed and signed off
checkpoint-status | Shutter stripped and area cleaned
checkpoint-group | Pour Records
checkpoint-status | Concrete dockets attached
checkpoint-status | Concrete test results
checklist-flat | Holdup/Delay - |  |  |  |  | Yes | Holdup/Delay - | 32bbaedd-deae-420c-880b-b39be27f79c3
checkpoint-no-status | Delay
text | Date and Time of Delay
text | Reasons for delay
text | Total delay time
checklist-flat | Toolbox Talk - |  |  |  |  | Yes | Toolbox Talk - | 64837f3b-33b6-470c-a178-c25c8ada220a
checkpoint-status | Toolbox Talk Details
text | Foreman / Supervisor:
text | Date:
checkpoint-status | Meeting Details / Attendees
text | Carried Out by:
text | Signed:
label | All attendees names listed below and signature / photo attached (click on paperclip to add photo / signatures)
checkpoint-status | Site Activities Listed - any corrective actions discussed, actioned, reviewed and closed out
label | Site activity, safe work practices, accident, incident investigations discussed
checkpoint-status | Near Misses / Incidents to report - any corrective actions discussed, actioned, reviewed and closed out
label | Near Misses / Incidents to report (name of person involved, type of injury)
checkpoint-status | Employee issues raised and resolved within specified timeframe (Pass once issues have been resolved)
text | Employee issues raised:
text | Date to be resolved by:
checkpoint-status | Safe Observations reviewed / discussed
text | Review Date:
checkpoint-status | Task Analysis/Job Safety Analysis (JSA) completed/reviewed
text | Checked By:
text | Date:
text | Received By
text | Date:
holdpoint | Request Signoff
checklist-sectioned | Foundations |  |  |  |  | Yes | Foundations | a189917d-d728-4597-9d99-b3b3ee63c399
checkpoint-group | Set Up
checkpoint-status | Details Completed
label | 1st Plan
text | Revision No:
label | 2nd Plan
text | Revision No:
label | 3rd Plan
text | Revision No:
text | Date area received:
text | Works started dates:
text | Pour Date:
text | Handover Date:
checkpoint-status | Area accessible and substrate acceptable
checkpoint-status | Datum by Surveyor in area
checkpoint-status | Gridline on profiles
checkpoint-status | Base prep height check
checkpoint-status | HD Bolt template orientation and location info
checkpoint-group | Prelim / Before Works Commence
checkpoint-status | Base prep within tolerance, +0-20mm
checkpoint-status | Work area barricaded
checkpoint-status | Excavation correct
checkpoint-status | Site Concrete required
checkpoint-status | Formwork Required
checkpoint-status | Photos taken
checkpoint-group | Formwork
checkpoint-status | RL transposed onto boxing
checkpoint-status | Adequately braced
checkpoint-status | Measure cover to reinforcing
checkpoint-status | Service penetrations installed
checkpoint-status | Formwork dimensions checked to grids
checkpoint-status | Photos taken
checkpoint-group | HD Bolts and Dross Backs
checkpoint-status | Dross Back Template and orentation Check
checkpoint-status | Dross Back Demension to grids
checkpoint-status | Template orientation check
checkpoint-status | Dimensions cl to grids measured
checkpoint-status | Bolt height above footing top
checkpoint-group | Additional
checkpoint-status | Reo sign off
checkpoint-status | Engineers Inspection booked
text | Time and date:
checkpoint-group | Concrete
checkpoint-status | Mix Code
select | Mix Code: | 202P,302P,402P,other
text | Other:
checkpoint-status | Admixtures
select | Admixtures: | RT Con 1,RT Con 2
checkpoint-status | Pour date
checkpoint-status | Placing Method
select | Placing Method: | Boom Pump,Line Pump,Skip
select | Pump supplier | Pioneer,other
text | Other:
checkpoint-status | Concrete booked
checkpoint-status | Placers available
select | Placers available: | Conslab,Others
checkpoint-status | Testing booked
checkpoint-group | Curing
checkpoint-status | Method
checkpoint-status | Time and Date undertaken
checkpoint-status | Photos taken
checkpoint-group | Close Out
checkpoint-status | Concrete finish type
checkpoint-status | RL checked
checkpoint-status | Bolts checked
checkpoint-status | Shutter stripped and area cleaned
checkpoint-group | Handover
checkpoint-status | Conslab Rep Sign Off
holdpoint | Request Sign Off
checkpoint-group | Pour records
checkpoint-status | Concrete dockets attached
checkpoint-status | Concrete test results