## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-sectioned | Foundations |  |  |  |  | Yes | Foundations | a189917d-d728-4597-9d99-b3b3ee63c399
checkpoint-group | Set Up
checkpoint-status | Details Completed
label | 1st Plan
text | Revision No:
label | 2nd Plan
text | Revision No:
label | 3rd Plan
text | Revision No:
text | Date area received:
text | Works started dates:
text | Pour Date:
text | Handover Date:
checkpoint-status | Area accessible and substrate acceptable
checkpoint-status | Datum by Surveyor in area
checkpoint-status | Gridline on profiles
checkpoint-status | Base prep height check
checkpoint-status | HD Bolt template orientation and location info
checkpoint-group | Prelim / Before Works Commence
checkpoint-status | Base prep within tolerance, +0-20mm
checkpoint-status | Work area barricaded
checkpoint-status | Excavation correct
checkpoint-status | Site Concrete required
checkpoint-status | Formwork Required
checkpoint-status | Photos taken
checkpoint-group | Formwork
checkpoint-status | RL transposed onto boxing
checkpoint-status | Adequately braced
checkpoint-status | Measure cover to reinforcing
checkpoint-status | Service penetrations installed
checkpoint-status | Formwork dimensions checked to grids
checkpoint-status | Photos taken
checkpoint-group | HD Bolts and Dross Backs
checkpoint-status | Dross Back Template and orentation Check
checkpoint-status | Dross Back Demension to grids
checkpoint-status | Template orientation check
checkpoint-status | Dimensions cl to grids measured
checkpoint-status | Bolt height above footing top
checkpoint-group | Additional
checkpoint-status | Reo sign off
checkpoint-status | Engineers Inspection booked
text | Time and date:
checkpoint-group | Concrete
checkpoint-status | Mix Code
select | Mix Code: | 202P,302P,402P,other
text | Other:
checkpoint-status | Admixtures
select | Admixtures: | RT Con 1,RT Con 2
checkpoint-status | Pour date
checkpoint-status | Placing Method
select | Placing Method: | Boom Pump,Line Pump,Skip
select | Pump supplier | Pioneer,other
text | Other:
checkpoint-status | Concrete booked
checkpoint-status | Placers available
select | Placers available: | Conslab,Others
checkpoint-status | Testing booked
checkpoint-group | Curing
checkpoint-status | Method
checkpoint-status | Time and Date undertaken
checkpoint-status | Photos taken
checkpoint-group | Close Out
checkpoint-status | Concrete finish type
checkpoint-status | RL checked
checkpoint-status | Bolts checked
checkpoint-status | Shutter stripped and area cleaned
checkpoint-group | Pour records
checkpoint-status | Concrete dockets attached
checkpoint-status | Concrete test results
checkpoint-group | Handover
checkpoint-status | Conslab Rep Sign Off
holdpoint | Request Sign Off