## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Balcony tiling installation checklist |  |  |  |  | Yes | Balcony tiling installation checklist | 050832c5-c192-454f-bc39-266b481ed36d
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Floor
checkpoint-status |  |  | checkpoint | Paving and Pedestals installed as per specifications -Attach photos-
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Bathroom tiling checklist |  |  |  |  | Yes | Bathroom tiling checklist | 08957918-b51c-4e4f-832f-b41ce37f13cc
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Floor
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Wall
checkpoint-status |  |  | checkpoint | Under Tile Heating cables installed – Attach Photo
checkpoint-status |  |  | checkpoint | Floor preparation Prior Tiling - Attach photos-
checkpoint-status |  |  | checkpoint | Waterproofing to floors - Attach Photos
checkpoint-status |  |  | checkpoint | Waterproofing to walls Prior Tiling - Attach photos-
checkpoint-status |  |  | checkpoint | Floor Tiling installed - Attach photos-
checkpoint-status |  |  | checkpoint | Wall Tiling installed - Attach photos-
checkpoint-status |  |  | checkpoint | Skirt Tiling installed - Attach Photos
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Tiling Installation External Checklist |  |  |  |  | Yes | Tiling Installation External Checklist (Old) | 14a83075-2ea6-423b-a9a7-0c03dd6af521
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous floor substrate acceptable
checkpoint-status |  |  | checkpoint | Tiling installed in Area as per specifications (attach photos)
checkpoint-status |  |  | checkpoint | Floor Tiling completed (attach photos)
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | WC Tiling Checklist |  |  |  |  | Yes | WC Tiling Checklist (Old) | 1a619a39-3075-4d64-8410-119689a290e8
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous floor & wall substrate acceptable
checkpoint-status |  |  | checkpoint | Floor preparation prior tiling (attach photos)
button | 472f4f17-9616-5a82-b46e-b4d362990999 |  | button | Waterproofing floor installed | Yes, No, N/A
button | 39b82939-d62b-5565-8383-9214570e3670 |  | button | Screed completed in shower area | Yes, No, N/A
button | 6bae1f31-6928-5e5b-b6cb-0b6b00c73c78 |  | button | Under tile heating & leveller installed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Waterproofing to walls prior tiling (attach photos)
button | f0f8b910-b594-5013-9545-a094648d7d81 |  | button | Shower enclose area | Yes, No, N/A
button | 020a94b3-3cd0-53ec-aee2-8992a3c95aba |  | button | Behind vanity | Yes, No, N/A
button | cbd90eb6-0fe2-5627-8630-46b75341ef06 |  | button | Tile skirting | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Tiling installed in Area as per specifications (attach photos)
checkpoint-status |  |  | checkpoint | Floor Tiling
checkpoint-status |  |  | checkpoint | Wall Tiling
checkpoint-status |  |  | checkpoint | Tile skirting
checkpoint-status |  |  | checkpoint | Splashback Tiling Installed
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Tiling Common Areas Checklist |  |  |  |  | Yes | Tiling Common Areas Checklist (Old) | 3edb9c06-5448-42b3-abb1-08906ffebbd8
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous floor substrate acceptable
checkpoint-status |  |  | checkpoint | Screeding completed
checkpoint-status |  |  | checkpoint | Tiling installed in Area as per specifications (attach photos)
checkpoint-status |  |  | checkpoint | Floor Tiling completed (attach photos)
button | 12a93d77-65e9-5686-8c07-9f999cc84572 |  | button | Tile skirting | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Bathroom Tiling Checklist |  |  |  |  | Yes | Bathroom Tiling Checklist (Old) | 54b2f415-f15f-4964-83ac-b37fb3af53bb
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous floor & wall substrate acceptable
checkpoint-status |  |  | checkpoint | Floor preparation prior tiling (attach photos)
button | 88f2e3c8-b697-5912-b79a-65d062e48309 |  | button | Waterproofing floor installed | Yes, No, N/A
button | 6f051ae5-fa52-57aa-9772-beea718411f3 |  | button | Screed completed in shower area | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Under Tile Heating cables & leveller installed (attach photos)
checkpoint-status |  |  | checkpoint | Waterproofing to walls prior tiling (attach photos)
button | d7793377-e66a-5dd2-8611-3bea32b24ae5 |  | button | Shower enclose area | Yes, No, N/A
button | 5c2a6a49-51aa-586b-b624-b1905fb14c7a |  | button | Behind vanity | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Floor Tiling installed (attach photos)
checkpoint-status |  |  | checkpoint | Wall Tiling installed (attach photos)
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Ensuite tiling checklist |  |  |  |  | Yes | Ensuite tiling checklist | 6f7ac885-4d90-40a7-8d46-37a533b22c3a
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Floor
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Wall
checkpoint-status |  |  | checkpoint | Under Tile Heating cables installed – Attach Photo
checkpoint-status |  |  | checkpoint | Floor preparation Prior Tiling - Attach photos-
checkpoint-status |  |  | checkpoint | Waterproofing to floors - Attach Photos
checkpoint-status |  |  | checkpoint | Waterproofing to walls Prior Tiling - Attach photos-
checkpoint-status |  |  | checkpoint | Floor Tiling installed - Attach photos-
checkpoint-status |  |  | checkpoint | Wall Tiling installed - Attach photos-
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Splashback Tiling Checklist |  |  |  |  | Yes | Splashback Tiling Checklist | 74df8f3d-12dd-4430-a750-8e75cbe77a9a
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous wall substrate acceptable
checkpoint-status |  |  | checkpoint | Wall Tiling installed (attach photos)
checkpoint-status |  |  | checkpoint | Joinery Tiling installed (attach photos)
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Balcony Tiling Installation Checklist |  |  |  |  | Yes | Balcony Tiling Installation Checklist (Old) | 871f1b36-cdaf-4041-baff-0eb6201bd8ae
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Waterproofing installed (attach photos)
button | ebc91670-cf0d-522a-9deb-3d285d626e3c |  | button | Windows set downs | Yes, No, N/A
button | cfc3a53e-788e-5285-99fe-ff8d23a11248 |  | button | Balcony Floor | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Screed completed
checkpoint-status |  |  | checkpoint | Paving and Pedestals installed as per specifications (attach photos)
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Kitchenette tiling checklist |  |  |  |  | Yes | Kitchenette tiling checklist | 9a8b1277-0d24-472f-8d09-1d55108cb47f
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Floor
checkpoint-status |  |  | checkpoint | Acoustic matting installed - Attach photos-
checkpoint-status |  |  | checkpoint | Floor Tiling installed - Attach photos-
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | WC tiling checklist |  |  |  |  | Yes | WC tiling checklist | 9be69a53-3442-490e-bd46-7a9a2b6f29e8
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Floor
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Wall
checkpoint-status |  |  | checkpoint | Floor Tiling
checkpoint-status |  |  | checkpoint | Tile skirting
checkpoint-status |  |  | checkpoint | Splashback Tiling Installed
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Seperate Laundry tiling checklist |  |  |  |  | Yes | Seperate Laundry tiling checklist | a459c798-5c30-48d1-bcb8-143e080111bf
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Floor
checkpoint-status |  |  | checkpoint | Previous substrate acceptable - Wall
checkpoint-status |  |  | checkpoint | Floor Tiling
checkpoint-status |  |  | checkpoint | Tile skirting
checkpoint-status |  |  | checkpoint | Splashback Tiling Installed
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Tiling common areas |  |  |  |  | Yes | Tiling common areas | a4d1dd57-5b04-48c6-8bb8-690b4ff892b9
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
label | 53542927-1d61-5bc8-a7c4-62a720b0ae82 |  | note | Attach Photo if any issues - Send remedial to Ryman-
button | ea3f6257-9cd0-5823-b2a4-43c39c72281f |  | button | Previous substrate acceptable - Floor | Yes, No, N/A
label | 4cb670ab-6102-5264-befc-098ffe674393 |  | note | Attach Photo if any issues - Send remedial to Ryman-
checkpoint-status |  |  | checkpoint | Screeding completed
checkpoint-status |  |  | checkpoint | Tiling installed in Area as per specifications
label | 3fd1c1d7-a2a6-5779-93e8-bfe56c8c2c05 |  | note | Attach photo(s) area
button | ea2ae98e-3bd8-5fb0-bfb9-28c04b23da16 |  | button | Floor Tiling completed - Attach photos- | Yes, No, N/A
button | d2fd7a93-b09f-5cd8-836a-4a2143c06a4a |  | button | Tile skirting | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Kitchenette Tiling Checklist |  |  |  |  | Yes | Kitchenette Tiling Checklist (Old) | d46adb08-8743-4ad7-b71b-503432d03cc7
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous floor substrate acceptable
checkpoint-status |  |  | checkpoint | Acoustic matting installed (attach photos)
checkpoint-status |  |  | checkpoint | Floor Tiling installed (attach photos)
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | TILING INSTALLATION EXTERNAL |  |  |  |  | Yes | TILING INSTALLATION EXTERNAL | e1414cf8-71de-426f-b205-65a9cc7e09d7
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
label | 093c19b3-23bf-5917-8c66-e08686482c77 |  | note | Attach Photo if any issues - Send remedial to Ryman-
button | 3ab6d0c3-4d65-5b18-820f-5247029e7a7a |  | button | Previous substrate acceptable - Floor | Yes, No, N/A
label | 41643719-9cc1-5aa4-8749-d422df6d7222 |  | note | Attach Photo if any issues - Send remedial to Ryman-
button | c7a247b0-56ae-5825-921a-741e54ff3259 |  | button | Floor Tiling completed - Attach photos- | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | ALS Laundry Tiling Checklist |  |  |  |  | Yes | ALS Laundry Tiling Checklist | e4759de5-982f-4b4b-b824-b8899b2ba0fb
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous floor & wall substrate acceptable
checkpoint-status |  |  | checkpoint | Floor preparation prior tiling (attach photos)
button | e7a0f174-9a53-579c-8a7d-168cdb34fd39 |  | button | Waterproofing floor installed | Yes, No, N/A
button | ffe10f9e-2640-5e7b-a7dd-069d376f8eb6 |  | button | Screed completed in shower area | Yes, No, N/A
button | 2ad67c17-d063-5cb8-81be-fe2582a44114 |  | button | Under tile heating and leveller installed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Waterproofing to walls prior tiling (attach photos)
button | 39b0295f-120d-55d1-b292-d68e22cb4647 |  | button | Shower enclose area | Yes, No, N/A
button | f53d7df2-f12f-5201-9bc8-a0ab5edb48cb |  | button | Behind vanity | Yes, No, N/A
button | 01270291-715c-5405-a322-07cc107108c6 |  | button | Tile skirting | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Floor Tiling installed (attach photos)
checkpoint-status |  |  | checkpoint | Wall Tiling installed (attach photos)
checkpoint-status |  |  | checkpoint | Tile skirting (attach photos)
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Silicone
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off
checklist-flat |  |  | checklist | Pool Tiling Checklist |  |  |  |  | Yes | Pool Tiling Checklist | fdd8f6f7-cf5e-42dd-a0f4-545802e333e0
checkpoint-status |  |  | checkpoint | Area clear, tidy and accessible
checkpoint-status |  |  | checkpoint | Previous floor & wall substrate acceptable
checkpoint-status |  |  | checkpoint | Render Top Coat completed
checkpoint-status |  |  | checkpoint | Waterproofing prior to tiling (attach photos)
button | 9911fc30-45f3-587f-8d18-36b814e00b46 |  | button | Waterproofing floor installed | Yes, No, N/A
button | 20c92328-69f0-516c-b7c3-5dbd5f018f1b |  | button | Waterproof walls installed | Yes, No, N/A
checkpoint-status |  |  | checkpoint | Tiling installed in Area as per specifications
checkpoint-status |  |  | checkpoint | Floor Tiling completed (attach photos)
checkpoint-status |  |  | checkpoint | Wall Tiling completed (attach photos)
checkpoint-status |  |  | checkpoint | Correct Grouting Installed as per specifications
checkpoint-status |  |  | checkpoint | Works completed 100% & area left clean/tidy
holdpoint |  |  | signoff | Sharp Tiling Sign Off