## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Area Ready Checklist |  |  |  |  | Yes | Area Ready Checklist | 2043ccfb-328d-45c4-9f13-4c0bb05f3697
checkpoint-group |  |  | section | Substrate
checkpoint-status |  |  | checkpoint | Substrate Acceptable
checkpoint-status |  |  | checkpoint | Wet Area Screed Installed
checkpoint-group |  |  | section | Walls / Ceiling
checkpoint-status |  |  | checkpoint | Ceiling Installed
checkpoint-status |  |  | checkpoint | Gyprock
checkpoint-status |  |  | checkpoint | Plastered
checkpoint-status |  |  | checkpoint | Plaster Sanded
checkpoint-status |  |  | checkpoint | Painted
checklist-flat |  |  | checklist | Variation Details - |  |  |  |  | Yes | Variation | a2b06419-e72c-4729-ac1e-2cf17cf8d37e
checkpoint-status |  |  | checkpoint | Variation Details Approved
text | 27012f07-168c-5bd5-a7c2-93705d21c66e |  | textbox | Reference/Drawing/Instruction Number
text | 5c14ef04-0321-5b49-bfb5-c7604e269965 |  | textbox | Variation Area
text | 20133cb6-cb12-5808-89ab-895b4c0e3de7 |  | textbox | Materials & labour breakdown
holdpoint |  |  | signoff | Request Variation Acknowledgement
checkpoint-status |  |  | checkpoint | Variation Completed
holdpoint |  |  | signoff | Request Variation Signoff
checklist-flat |  |  | checklist | Daily Pre Start |  |  |  |  | Yes | Daily Pre Start | c0550f67-82eb-4d46-9464-16a2ee574cb4
checkpoint-status |  |  | checkpoint | Details
text | 1dec023f-afbc-52d1-8193-6ef779b4bf62 |  | textbox | Supervisor Leading Meeting
text | e89c8632-e55b-5e3a-80b3-21c7f0ef93b6 |  | textbox | Date
text | be969398-c61f-554c-a30c-00fea5f0b8e1 |  | textbox | Time
checkpoint-status |  |  | checkpoint | 1. Issues arising from previous day
text | bd68918e-7255-5bde-a427-71c7aec5b295 |  | textbox | Issues arising from previous day
label | 9e81d05e-45c9-5d32-8d84-d3373f532018 |  | note | NOTE: If this requires a change to the SWMS then please ensure this is captured and relevant personnel inducted.
checkpoint-status |  |  | checkpoint | 2. Planned work / activities being carried out today
boolean | 2614fdcd-42a0-5ff1-bff4-71e54cdd23d8 |  | tickbox | Carpet and resilient finishes
boolean | 998b3457-dde7-5719-b3e0-29f375effe68 |  | tickbox | Other:
text | b4c9f406-3fd7-55ae-b6e6-b631f39c4182 |  | textbox
text | 5e7f80cb-9728-5c9b-b635-e1330377cfd3 |  | textbox
text | ce597019-62f2-59e9-8089-8beb9889dfab |  | textbox
text | 49dd41db-bd57-5074-8642-fbe7dd80927a |  | textbox
checkpoint-status |  |  | checkpoint | 3. Is a SWMS in place for ALL high risk construction work and work procedures in place for all other works?
label | 84e1b38a-455a-510e-9ebf-d6eda88cfdec |  | note | If FAIL, stop and develop
checkpoint-status |  |  | checkpoint | 4. Are you subcontracting out any works today and will you be interacting with other trades?
text | f5db0e90-868e-56a5-946e-0da5851b868e |  | textbox | If PASS, please list
checkpoint-status |  |  | checkpoint | 5. Permits in place for today’s Activities - Stating Permit No. and Description
button | bcfb583f-b0d4-509c-9844-49931a712736 |  | button | Hot Works | No,Yes
text | c58530ef-51ff-5dd5-85b9-966c246d6e64 |  | textbox | Number:
text | dac47730-a7ed-5cef-8c46-0836194627b7 |  | textbox | Number / Description:
text | 14f60c3b-f3ea-5eee-84e0-cd50c3a1edee |  | textbox | Number / Description:
text | 66954184-04ef-5294-8865-6be946f4f0b4 |  | textbox | Number / Description:
checkpoint-status |  |  | checkpoint | 6. Hazardous Substances being used, or will be brought to/or stored on site today?
boolean | 3121e52a-c21c-5841-a15a-14324b854381 |  | tickbox | Flooring adhesives
boolean | 740f89c0-ab8f-5fb2-bc0e-57950791f2dd |  | tickbox | Floor preparation materials
boolean | f0a4662f-5e30-53dc-bf2e-32802801abed |  | tickbox | Gas cylinders
text | ccc459b5-caa1-5f01-94cd-30123a4cc172 |  | textbox | Other:
checkpoint-status |  |  | checkpoint | 7. Is there an MSDS on site for ALL the above listed substances (less than 5 years old)
checkpoint-status |  |  | checkpoint | 8. What controls are in place to manage environmental risk on site, specific for today; e.g. Wash out areas, maintenance of sediment fences and drains, monitoring of dust? List
boolean | cc653e65-46da-5c99-be12-577fbfc8302e |  | tickbox | New self igniting gas guns fitted and exclusion barriers set up
boolean | 839d652c-150d-54d3-a31f-ba775df67b80 |  | tickbox | Vacuums to control dust, Wash out bays provided used for cleaning, Bins provided used for waste
text | 8533e795-dd0f-5f67-8cc0-0f2a6a91bd3d |  | textbox | Other:
text | 4d906410-50b9-54fd-8860-7d1b8b5ca07e |  | textbox | Other:
text | db43e0b7-50b8-5cda-9f21-358598539da0 |  | textbox | Other:
text | d84fc431-f9ea-5b23-a683-bc640beda50d |  | textbox | Other:
checkpoint-status |  |  | checkpoint | 9. Checklist for activities complete
label | 28bcb967-7973-5477-8e39-b86727e91ce4 |  | note | Complete activities or issues must be detailed in Notes section below
button | 4935872a-85dc-5765-a819-ff7fdb80c717 |  | button | Daily Risk Assessment Completed | No,Yes
button | 58fdd356-5e60-54dc-8fba-537334c2859a |  | button | Work area inspected and safe for staff to enter and work in today | No,Yes
text | e4e4377c-bb7a-5678-8bd4-ffdc6f54ac7a |  | textbox | Indicate number of people in your work group
button | 6e7438d6-f4f3-5e22-8b4c-17f312ccfe45 |  | button | Qualifications/training of staff adequate for work activities | No,Yes
button | f480716a-e83a-5f0b-a376-f70bbe1653e7 |  | button | Appropriate and adequate PPE supplied to work teams (SWMS/SDS) | No,Yes
text | 990af5ba-7329-5c1e-884a-9ad02fd66392 |  | textbox | Indicate number of workers allocated for today's clean up
button | eba43a87-acd4-5fd2-9bb2-33f306183566 |  | button | Plant and equipment on/off site | No,Yes
button | ff2f4078-9f77-5858-963f-c6db0b2a2a5a |  | button | Equipment safe to use | No,Yes
button | 62b8a254-d4ea-5ae1-aee0-d8b0c5977ce7 |  | button | Weather conditions for work to be conducted / assessed | No,Yes
button | 5b2cdee7-b244-5671-8f67-d04a0c8e4f75 |  | button | Pre-start communicated to all work teams including all trades and subcontractors listed in section 4. | No,Yes
checkpoint-status |  |  | checkpoint | Builder's Briefing Notes reviewed and understood by all workers
text | 2551b540-cc6f-5b9b-a2ac-8daf04156c02 |  | textbox
checkpoint-status |  |  | checkpoint | General Notes
text | 3c32ac35-a8b4-5ba8-8d6c-ad34fb511149 |  | textbox
text | 242c6398-da7a-5b7b-8e01-f60cb894d5ec |  | textbox
text | e3589e54-6bec-5110-b35c-cc19304ed237 |  | textbox
text | dfe8b5b0-056e-5483-af9e-aef871dcd7a8 |  | textbox
checkpoint-no-status |  |  | checkpoint | Attendees noted
checklist-sectioned |  |  | checklist | Floor Finishes ITP |  |  |  |  | Yes | Floor Finishes ITP | e3b58790-66fc-48b1-8128-6f3296ef669d
checkpoint-group |  |  | section | Subfloor, Floor Preparation, Adhesive
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
checkpoint-status |  |  | checkpoint | Subfloor mechanically diamond ground
checkpoint-status |  |  | checkpoint | Moisture readings compliant to AS 1884-2020 APPENDIX A
checkpoint-status |  |  | checkpoint | Floor preparation product installed in accordance with manufacturer's instructions
button | fed95e16-c577-5748-9e6d-5a7720ce0d35 |  | button | Product: | Mapei Ultraplan Eco, Mapei Planiprep
text | ab2995ae-93cc-53e8-b6eb-119ec9ca7319 |  | textbox | Average thickness: | mm
checkpoint-status |  |  | checkpoint | Correct adhesive used
button | b4b7f9a7-7c94-5bb5-a1a0-2da9137c2679 |  | button | Adhesive: | Mapei V4SP Vinyl Adhesive, Mapei Pressure Sensitive
checkpoint-group |  |  | section | Carpet / Vinyl
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | 83b581a7-dbd0-5206-a9c9-9e4b9a5c6ec1 |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Vinyl installed as per plan
select | bb3f3324-5a19-513d-a9d6-870c89c7eb22 |  | dropdown | Material: | ON ANOTHER TAB
checkpoint-status |  |  | checkpoint | Carpet installed as per plan
select | c3def4d1-3262-5053-a76d-129a19492210 |  | dropdown | Material: | PRODUCTS TBC
text | f2c45fbb-beab-58c6-841f-0ed144735b48 |  | textbox | Other colour:
checkpoint-status |  |  | checkpoint | Joints sealed with heat welded seams and mitres as per AS 1884-2020
checkpoint-status |  |  | checkpoint | Vinyl skirt and coving used as per finishes markup - 150mm
text | bbc59726-a529-5384-82ae-936a1d24993f |  | textbox | Custom height:
checkpoint-status |  |  | checkpoint | Installer Sign Off: Carpet / Vinyl installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Add-Floors Sign Off
checkpoint-status |  |  | checkpoint | Adco Foreman installation sign off
checkpoint-group |  |  | section | Walls
checkpoint-status |  |  | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
text | 09e6da95-d399-58ed-8a93-fefa8d841e9d |  | textbox | Drawing & revision number(s)
checkpoint-status |  |  | checkpoint | Wall Finish installed as per plan
select | dfb34611-6ccf-50b2-afa6-8fa9f0075f67 |  | dropdown | Material: | Tarkett Wallguard 2mm colour
checkpoint-status |  |  | checkpoint | Joints sealed with heat welded seams and mitres as per AS 1884-2020
checkpoint-status |  |  | checkpoint | Installer Sign Off: Wall finish installed as per manufacturer's instructions
checkpoint-status |  |  | checkpoint | Add-Floors Sign Off
checkpoint-status |  |  | checkpoint | Adco Foreman installation sign off
checkpoint-group |  |  | section | Protection and Handover
checkpoint-status |  |  | checkpoint | Installation complete, checked and reviewed - as per specification
text | b58494be-3cda-509f-bbc3-9642f8765f83 |  | textbox | General comments / observations
checkpoint-status |  |  | checkpoint | Vinyl protected with Bubbleweave and/or MDF floor protection
checkpoint-status |  |  | checkpoint | Installer Sign Off: Protection installed as per manufacturer's instructions
checklist-flat |  |  | checklist | Delivery Checklist |  |  |  |  | Yes | Delivery Checklist | e47edf83-0f6a-4b99-ac9b-36ac5c760cf9
checkpoint-status |  |  | checkpoint | Delivery details input
text | 3b98017b-ec44-51fa-b004-173e647864c7 |  | textbox | Date
text | e16f2e32-02e2-565c-90ef-d838e54098c8 |  | textbox | Delivered by
text | 3909a160-d362-5e34-8a05-6d5b43e76eee |  | textbox | From
text | 87b64105-be41-538e-95c7-5da36a918ef2 |  | textbox | Description
text | 1691094e-11a2-5eba-9fe1-dd2fca73be2c |  | textbox | Comments
text | 23ad9b26-0137-5f7e-93e7-7c5ecacc4587 |  | textbox | Stored where
checkpoint-status |  |  | checkpoint | Materials checked
boolean | 2ca2791d-614b-5c83-929f-382e5b4d54fa |  | tickbox | Materials in good order
boolean | 98f629eb-1ca8-5e3b-ae12-2af83882ed45 |  | tickbox | Photo of materials
boolean | 94cc1ec3-df68-50db-ae3a-cf16fda7282d |  | tickbox | Photo of Con Note
boolean | 1e40ac75-cf93-5038-80e8-422c5e5a35c4 |  | tickbox | Photo Packing Slip / Slips
text | 98650974-2e7b-5d8c-b886-381745cbe972 |  | textbox | Comments