## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
folder-normal |  |  | checklist | RC Number |  |  |  |  | Yes | Consent Documents - New Resource Consent Checklist | 15a29932-3768-4867-9d0e-e7eab19a86b1
checklist-flat |  |  | checklist-flat | Resource Consent Lodgement Checklist
checklist-flat |  |  | checklist-flat | Latest Resource Consent - RC Number
folder-normal |  |  | folder-normal | Resource Consent Amendments - RC Number
folder-normal |  |  | folder-normal | Minor Variations - RC Number
checklist-flat |  |  | checklist | Roof Water Proofing |  |  |  |  | Yes | Roof Water Proofing | 184d4570-e46b-43a8-80b8-2d09a86dddb2
checkpoint-status |  |  | checkpoint | Ensure the materials are as per approved project specifications
checkpoint-status |  |  | checkpoint | Ensure the surface is clean
checkpoint-status |  |  | checkpoint | Ensure Sealant is applied in all corners/gaps/screws
checkpoint-status |  |  | checkpoint | Check the application of waterproofing membrane as per drawing &TDS
checkpoint-status |  |  | checkpoint | Check waterproofing membrane thickness, over lapping and curing time as per approved drawing and TDS
checkpoint-status |  |  | checkpoint | Check Installation of Ubar+Fastner (If Any)
checkpoint-status |  |  | checkpoint | Ensure the Gutter Hole is Treated and Sealed Properly( if any)
checkpoint-status |  |  | checkpoint | Ensure the final Slope (if Any)
checkpoint-status |  |  | checkpoint | Final Cleaning/Protection
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Passive Fire |  |  |  |  | Yes | ICS - Passive Fire | 3922195f-10cf-4931-8f51-ab96788d348d
checkpoint-status |  |  | checkpoint | Ensure the materials are as per approved project specifications
checkpoint-status |  |  | checkpoint | Ensure all approved documented the fire paint specification, Engineering judgment, and test report.
checkpoint-status |  |  | checkpoint | Ensure Penetration Openings are as Per Approved Engineering Judgements
checkpoint-status |  |  | checkpoint | Ensure Fire Stop Sealant/Fire Collars is applied as per Approved Engineering Judgements
checkpoint-status |  |  | checkpoint | Ensure are following the fire paint specification
checkpoint-status |  |  | checkpoint | Destructive Testing for fire penetration
checkpoint-status |  |  | checkpoint | Ensure Fire Stop penetarions are Mapped for Fire Walls
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-sectioned |  |  | checklist | NCR: |  |  |  |  | Yes | Add NCR | 464a1b2d-b400-4c5d-b46c-559fc2244220
checkpoint-group |  |  | section | NCR Status
checkpoint-no-status |  |  | checkpoint | Status:
button | 1a05f2ee-88ca-5769-913f-15e2fcbf2a14 |  | button | NCR Status | New, Assigned, To reply that NCR resolved by assignee, To reject by QC, Inspected, To close
text | 9a6b278f-5a13-57c9-9d0a-9e6b958ac955 |  | textbox | Reason for rejection:
checkpoint-group |  |  | section | NCR Details
checkpoint-status |  |  | checkpoint | NCR Details Captured below
text | cba7a7dc-4932-5bd6-b189-c5d4a3bac2d1 |  | textbox | Title:
text | e8a34740-fd99-5788-9f01-3031bd485897 |  | textbox | Description:
text | c6055be5-1fd6-5b36-b57a-1615edcf6d39 |  | textbox | Project:
text | f5c218bb-7a3c-5002-9e9a-e249cd80f883 |  | textbox | Subproject:
text | 57f2f402-55ed-5e44-94b3-4fd8bc7523af |  | textbox | Prod Routing:
text | a374ff79-8cea-59e2-8d2a-1dabf02671e3 |  | textbox | Prod Order:
text | 1c369dfe-1df0-5fdb-9576-36d3bca780bf |  | textbox | Discipline:
text | 3bf00c01-1d88-5c9b-8872-56a66a318128 |  | textbox | Discipline 1:
text | defac75c-eb14-5cf4-93a2-f37bde3eedcf |  | textbox | Discipline 2:
text | 5d0b6d49-a633-5987-b04a-72a93583929d |  | textbox | Responsible Team:
text | 23dd09f2-d848-508e-865f-2c6b6efb4b5b |  | textbox | Internal/Externals:
text | c0260f31-36c3-5798-908d-6bae9842cf60 |  | textbox | Priority:
date | f5f6739b-4fe5-5e71-91e9-c5324423bb00 |  | date | Due Date:
button | 65a4a43e-52e0-553a-8eb0-3490b7ff72da |  | button | Root Cause: | Design, Materials, Workmanship
button | 41b6569d-f54c-5810-a9fa-cd3a43822f79 |  | button | Disposition: | Reject, Repair, Replace, Return to Supplier
button | e6e5f309-bacc-5c0b-accc-38a90868a7ba |  | button | Severity: | High, Low
button | 8c647180-c30e-5995-a1e2-8d1dd6b0553a |  | button | Report Type: | Defect, NCR
checkpoint-no-status |  |  | checkpoint | Defective Photos
checkpoint-no-status |  |  | checkpoint | Attached PDF
text | 08953e8a-72e1-5d46-9cbd-4613c86686c5 |  | textbox | Assignee to:
text | 919a4857-06ac-51c7-afc4-86ef7c5be062 |  | textbox | Monitors:
checkpoint-group |  |  | section | Intermediate
checkpoint-no-status |  |  | checkpoint | Request for Review
text | 85cb59a9-a936-5e72-9365-79a16d2749db |  | textbox | Qty Manpower:
text | 56c71b84-ac5c-52d3-b8b7-e6fa20eb94ab |  | textbox | Hour/Man:
text | e2972c76-9c88-5b0e-b0d8-ec45792a67d5 |  | textbox | Total Hour:
holdpoint |  |  | signoff | Request for Review
checkpoint-no-status |  |  | checkpoint | Request Inspection
text | 6ea8fef6-07c1-53c1-9d3a-48389d2e1706 |  | textbox | Inspection Rejected Reason:
holdpoint |  |  | signoff | Request Inspection
checkpoint-no-status |  |  | checkpoint | Corrective Photos
checkpoint-no-status |  |  | checkpoint | Attached PDF
text | f52b35ef-ff75-58ca-a699-05c18c9b4cbd |  | textbox | Inspector:
checklist-sectioned |  |  | checklist | ICS - Roof System |  |  |  |  | Yes | ICS - Roof System | 57121ec9-3284-4850-8c39-8aadb14688ef
checkpoint-group |  |  | section | Inspect
checkpoint-status |  |  | checkpoint | Inspect - Preparatory Steel works (Shearing, Drilling & Cutting)
checkpoint-status |  |  | checkpoint | Inspect - Blasting works for steel materials (SA-2.5)
checkpoint-status |  |  | checkpoint | Inspect - Painting (D.F.T) works for steel materials (ISO 16276-2 or required Project Painting Specifications)
checkpoint-status |  |  | checkpoint | Inspect- Fit-up dimension and steel members orientation
checkpoint-status |  |  | checkpoint | Inspect- Full welding
checkpoint-status |  |  | checkpoint | Inspect - Painting touch up or Final coat (D.F.T) as per ISO 16276-2 or required Project Painting Specifications
checkpoint-status |  |  | checkpoint | Inspect- Final assembly and Ensure all parts are properly tagged
checkpoint-status |  |  | checkpoint | Inspect- Roof underlay application.
checkpoint-status |  |  | checkpoint | Inspect- CFC board/ Lining installation over the roof underlay( if any)
checkpoint-status |  |  | checkpoint | Inspect- Roof sheeting substrate( Bottom ) installation with necessary fasteners.
checkpoint-status |  |  | checkpoint | Inspect- Insulation application ( if any)
checkpoint-status |  |  | checkpoint | Inspect- Breather membrane application over the roof sheeting substrate.( if any)
checkpoint-status |  |  | checkpoint | Inspect- Locked Seam clip, foam filler installation with necessary fasteners.
checkpoint-status |  |  | checkpoint | Inspect- Rubber washer/ Neoprene washer with all screw fittings
checkpoint-status |  |  | checkpoint | Inspect- Seam roofing ( top layer) installation.
checkpoint-status |  |  | checkpoint | Inspect-Cutting of Roof sheet for pipe penetration.
checkpoint-status |  |  | checkpoint | Inspect- Ridge capping installation.
checkpoint-status |  |  | checkpoint | Inspect- EPDM flexible cone sleeve installation with compatible waterstopped sealant roof cladding to Pipe
checkpoint-status |  |  | checkpoint | Inspect- Full pipe penetration through the roof sheeting.
checkpoint-status |  |  | checkpoint | Inspect- Gable flashing installation.
checkpoint-status |  |  | checkpoint | Inspect- External Box gutter installation.
checkpoint-status |  |  | checkpoint | Ensure- Proper slope has been achievement.
checkpoint-group |  |  | section | Inspector Signature
checkpoint-status |  |  | checkpoint | Inspector Signature
text | b2110d0b-6da8-5079-85bb-dd38cb098c96 |  | textbox | Inspector Name
holdpoint |  |  | signoff | Signature
checklist-flat |  |  | checklist | Bulk Excavation - |  |  |  |  | Yes | On Site QA - Bulk Excavation Checklist | 5c075b3f-678c-41cc-83eb-870b49b1582a
checkpoint-status |  |  | checkpoint | Excavation depth determined using appropriate RL's
checkpoint-status |  |  | checkpoint | Confirm location and isolation of relevant services
checkpoint-status |  |  | checkpoint | General excavation documentation and photos attached
checkpoint-status |  |  | checkpoint | Any batters formed correctly
checkpoint-status |  |  | checkpoint | Any trenches/ pits / hazardous areas appropriately isolated
checkpoint-status |  |  | checkpoint | Any soft spots identified and appropriate remedial completed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Any hardfill/ blinding installed correctly to required specification
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached and any observations recorded and closed out
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Trades QA / Signoff
checkpoint-status |  |  | checkpoint | Excavation completed - Correct locations and RL's achieved
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-sectioned |  |  | checklist | Sub-Structural Checklist |  |  |  |  | Yes | Offsite QA - Sub-Structural Checklist | 5e463986-18ce-4fe7-bfc0-1b00499d76b8
checkpoint-group |  |  | section | Preparatory Works
checkpoint-status |  |  | checkpoint | Inspect - Preparatory Steel works (Shearing, Drilling & Cutting)
checkpoint-status |  |  | checkpoint | Inspect Section Length/Width/Drill Hole Dimensions/Locations are as per approved drawing
checkpoint-group |  |  | section | Fit-Up Works
checkpoint-status |  |  | checkpoint | Inspection - Fit-up Dimensions & Orientations are done as per approved drawing
checkpoint-status |  |  | checkpoint | Ensure all tack weldings are done
checkpoint-group |  |  | section | Welding Works
checkpoint-status |  |  | checkpoint | Visually Inspect - Complete Welding process and welded areas are free from any flaws
checkpoint-group |  |  | section | Non - Destructive Examinations
checkpoint-status |  |  | checkpoint | Inspect - NDE (MPI / UT) if required
checkpoint-group |  |  | section | Surface preparations
checkpoint-status |  |  | checkpoint | Inspect - Blasting process & blasted surfaces on material
checkpoint-group |  |  | section | Anti-Corrosion Coating system
checkpoint-status |  |  | checkpoint | Inspect - Painting touch up or Final coat (D.F.T) as per ISO 8503 or required Project Painting Specifications
checkpoint-group |  |  | section | Part Identifications
checkpoint-status |  |  | checkpoint | Ensure all pieces are properly TAGGED as per drawing part mark number
checkpoint-group |  |  | section | Sign Offs
checkpoint-status |  |  | checkpoint | TLC - Inspector Sign off
checklist-flat |  |  | checklist | Internal painting |  |  |  |  | Yes | ICS - Internal painting | 6845806f-fee4-468b-8368-f089a9ba5dc1
checkpoint-status |  |  | checkpoint | Ensure the Painting Surface Condition Check and Protection works
checkpoint-status |  |  | checkpoint | Painting Surface Joint Treatment and Corner Bead installation Check
checkpoint-status |  |  | checkpoint | Ensure, Approved Skim, sealer and Painting are used at designated area
checkpoint-status |  |  | checkpoint | Internal Skimcoat application and Sanding Works Check
checkpoint-status |  |  | checkpoint | Ensure the sealer undercoat application
checkpoint-status |  |  | checkpoint | Ensure Final Coat Paint application (2 Coats)
checkpoint-status |  |  | checkpoint | Check coating surface imperfections and defects repair check
checkpoint-status |  |  | checkpoint | Work acceptance. Check the color, gloss, texture,adhesion (Optional)
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Built up structure checklist |  |  |  |  | Yes | Built up structure checklist | 6957afba-462a-408e-b0d6-3064d74c0cba
checkpoint-status |  |  | checkpoint | Verify - Welding Procedure Specification document
checkpoint-status |  |  | checkpoint | Verify - Welder Qualification Test document
checkpoint-status |  |  | checkpoint | Verify - Welder qualified Certification document
checkpoint-status |  |  | checkpoint | Verify - Equipment calibration document
checkpoint-status |  |  | checkpoint | Verify - Drawing cutting list
checkpoint-status |  |  | checkpoint | Inspect - Raw materials. An inspection document outcome signed off by parties involved
checkpoint-status |  |  | checkpoint | Submit 3rd party material test records
checkpoint-status |  |  | checkpoint | Inspect - Fit up and Visual of element, (Dimension & Geometry). An inspection document outcome signed off by parties involved
checkpoint-status |  |  | checkpoint | Inspect - NDT test of the welded element. An inspection document outcome signed off by parties involved
checkpoint-status |  |  | checkpoint | Inspect - inspect Visual after NDT test. An inspection document outcome signed off by parties involved
checkpoint-status |  |  | checkpoint | Inspect - Release Note document. Document outcome signed off by parties involved + As build drawing + Packing list
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | Tiling & Grouting |  |  |  |  | Yes | ICS - Tiling & Grouting | 6e2685a2-6c55-4559-bd4b-7216986f55e5
checkpoint-status |  |  | checkpoint | Check Water proofed Surface Condition and MEP Clearance
checkpoint-status |  |  | checkpoint | Ensure Correct Application of Screed/Render
checkpoint-status |  |  | checkpoint | Ensure Screed to Cure
checkpoint-status |  |  | checkpoint | Check Proper slope is achieved as per approved drawing
checkpoint-status |  |  | checkpoint | Ensure Correct Tile Setting Out (Floor & Wall)
checkpoint-status |  |  | checkpoint | Ensure Correct Preparation and Mixing of Tile adhesive Material
checkpoint-status |  |  | checkpoint | Ensure to use plastic spacers for specified size of tiling joints
checkpoint-status |  |  | checkpoint | Ensure Tile trim has been installed at required area.
checkpoint-status |  |  | checkpoint | Check Tile Surface level and Proper Installation
checkpoint-status |  |  | checkpoint | Ensure Tiles and Joints cleaned before Grouting
checkpoint-status |  |  | checkpoint | Ensure Proper materials for grouting and correct application
checkpoint-status |  |  | checkpoint | Final Acceptance and slope Check
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Internal Wall Linings |  |  |  |  | Yes | ICS - Internal Wall Linings | 6eed657c-02e6-4df8-b043-ea56ae0439c3
checkpoint-status |  |  | checkpoint | Framing Works Installation Check (Wall,Floor,Ceiling)
checkpoint-status |  |  | checkpoint | Openings & Lateral Bracings Check
checkpoint-status |  |  | checkpoint | Internal Ceiling,Floor Board installation Check
checkpoint-status |  |  | checkpoint | Internal Wall Board and Partition Wall Installation Check
checkpoint-status |  |  | checkpoint | Internal Insulation Material Installation Check
checkpoint-status |  |  | checkpoint | Check- Vapour barrier installation
checkpoint-status |  |  | checkpoint | Internal Fire Selant Application Check
checkpoint-status |  |  | checkpoint | Internal Boards Alignment,Joint Spacing Check
checkpoint-status |  |  | checkpoint | PIR insulation board installation as per approved drawing
checkpoint-status |  |  | checkpoint | Secondary Ceiling or Bulkhead Installation Check
checkpoint-status |  |  | checkpoint | Ensure Metal strip installation as per approved drawing
checkpoint-status |  |  | checkpoint | Joints, Corner and Interfacing & Repairs Check
checkpoint-status |  |  | checkpoint | Final Acceptance
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Final |  |  |  |  | Yes | Final | 6ff736b6-3c6d-416b-bbcc-3531e1be28fd
checkpoint-status |  |  | checkpoint | Main Door/Riser Door/Bathroom Door/Bedroom Door
checkpoint-status |  |  | checkpoint | Bulk Head
checkpoint-status |  |  | checkpoint | Wall Painting/Wallpaper/Panels/Bed Head
checkpoint-status |  |  | checkpoint | Wall/Floor Tiles & Grouting
checkpoint-status |  |  | checkpoint | Timber/Vinyl Floor/Skirtings/Carpets
checkpoint-status |  |  | checkpoint | Laundry/Mirror/Vanity/Wardrobe cabinet
checkpoint-status |  |  | checkpoint | Windows/Curtains/Pelmet
checkpoint-status |  |  | checkpoint | Kithen Cabinet/Kitchen Island
checkpoint-status |  |  | checkpoint | Selant Finishes
checkpoint-status |  |  | checkpoint | Kitchen/Cistern/Vanity Top/Splash Backs
checkpoint-status |  |  | checkpoint | Bath Tub Screen/Glass Shelves
checkpoint-status |  |  | checkpoint | Threshold/Transitional Trims
checkpoint-status |  |  | checkpoint | Access panel
checkpoint-status |  |  | checkpoint | Towel Racks/Paper Holder/Robe Hook
checkpoint-status |  |  | checkpoint | Shower Set/Bath Set
checkpoint-status |  |  | checkpoint | WC/BathTub/Wash Basin
checkpoint-status |  |  | checkpoint | Floor Drain covers/Floor Traps
checkpoint-status |  |  | checkpoint | Finished Floor Protection
checkpoint-status |  |  | checkpoint | Module Cleaning
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Sub-Structure |  |  |  |  | Yes | ICS - Sub-Structure | 7592ebfc-4303-4316-bde0-53c6a519bc68
checkpoint-status |  |  | checkpoint | Inspect - Preparatory Steel works (Bending,Drilling & Cutting)
checkpoint-status |  |  | checkpoint | Inspect Section Length/Width/ Drill Holes Dimension/Location
checkpoint-status |  |  | checkpoint | Inspect - Fit-Up as per Drawing
checkpoint-status |  |  | checkpoint | Inspect - Full Welding
checkpoint-status |  |  | checkpoint | Inspect - MPI/UT
checkpoint-status |  |  | checkpoint | Inspect - Blasting
checkpoint-status |  |  | checkpoint | Inspect - D.F.T - Painting/Hot-Dip Galvanizing as per Painting Specification
checkpoint-status |  |  | checkpoint | Inspect - TAG/Part Mark
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | WP System |  |  |  |  | Yes | ICS - WP System | 759d3297-157b-4437-9dff-8695ade2c2f6
checkpoint-status |  |  | checkpoint | Check-The floor and wall surface
checkpoint-status |  |  | checkpoint | Check- Internal Board Joint Sealant application
checkpoint-status |  |  | checkpoint | Check- Angle Fillet or Fiber Mesh Rendering and upturn on Joints
checkpoint-status |  |  | checkpoint | Ensure the Floor traps & drains are treated well
checkpoint-status |  |  | checkpoint | Check- Waterproofing Membrane application as per approved drawing
checkpoint-status |  |  | checkpoint | Check-waterproofing Membrane Thickness, number of coats, and curing time
checkpoint-status |  |  | checkpoint | Conduct Wet Area Waterponding and Spray Test (All wet areas) & Ensure No Leaks
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-sectioned |  |  | checklist | WIR: |  |  |  |  | Yes | Add Work Inspection Report | 7608f220-916a-481a-b908-bd8310b4f841
checkpoint-group |  |  | section | WIR Status
checkpoint-no-status |  |  | checkpoint | Status:
button | b0999c35-d3e7-565c-ba0b-6c1c6d11a4a2 |  | button | WIR Status | New, Assigned, To Reject, Closed
text | 2fc0e2eb-5ae8-57b1-998d-7d253666ef8c |  | textbox | Reason for rejection:
checkpoint-group |  |  | section | WIR Details
checkpoint-status |  |  | checkpoint | WIR Details Captured below
text | 4f2b921a-be9a-5897-947e-d82d16c63007 |  | textbox | Project:
text | 4e18a2cc-e6f9-5b29-8fa6-9a1d30d9ec2b |  | textbox | Sub Project:
text | 82565a4e-07f9-55b6-b3b9-91cb0ba8307f |  | textbox | Prod Routing:
text | ac7b581b-af05-57a7-ad0a-b88f3be6daea |  | textbox | Prod Order:
text | ecdd712c-8e15-54d4-a0a3-497ff929a1cd |  | textbox | Discipline:
text | c6446948-0e00-56bc-8b2e-323c060c6973 |  | textbox | WIR Description:
text | 906a7010-ead8-5130-837a-dde69c9dafe6 |  | textbox | Description:
text | 04601a92-e65a-5dca-921b-198fd7905411 |  | textbox | Priority:
date | 16258194-9fc0-5e9b-8fd7-7869381ea415 |  | date | Due Date:
text | fb048de3-cf20-5817-b19d-6c0a93fe74c9 |  | textbox | Assignee:
text | 0dd2fd1d-8bde-56cf-ae28-0058604d98c9 |  | textbox | Monitors:
checklist-flat |  |  | checklist | On Site - Site Concrete Checklist |  |  |  |  | Yes | On Site QA - Site Concrete Checklist | 83ea7656-f019-4f2e-92c4-80a174bb3001
checkpoint-status |  |  | checkpoint | Excavation depth and location checked and correct
checkpoint-status |  |  | checkpoint | Ground conditions acceptable
checkpoint-status |  |  | checkpoint | Concrete specifications checked, correct and delivery docket photographed
checkpoint-status |  |  | checkpoint | Site concrete placed
text | cbc07217-99ce-44fb-8eca-e539395b94cc |  | textbox | Placed by:
holdpoint |  |  | signoff | Raise remedial / Request trades QA / Signoff
checkpoint-status |  |  | checkpoint | Concrete placed to the correct height
checkpoint-status |  |  | checkpoint | Site concrete pour completed and finish acceptable
holdpoint |  |  | signoff | Raise Remedial / Request Signoff
checklist-flat |  |  | checklist | Sprinkler System |  |  |  |  | Yes | ICS - Sprinkler System | 881e4897-f34c-4e0a-b7c4-5818e92bd1c0
checkpoint-status |  |  | checkpoint | Verify the materials, pipe and sprinkler type as per the drawing or spec, standard.
checkpoint-status |  |  | checkpoint | Ensure the Location of sprinkler as per the drawing and standard
checkpoint-status |  |  | checkpoint | Ensure piping adequately supported by brackets, clips or hangers and be fixed directly to the structural elements
checkpoint-status |  |  | checkpoint | Pipeline shall be identified in accordance with The British Standards BS 1710 /BS 4800
checkpoint-status |  |  | checkpoint | Freezing protection if applicable
checkpoint-status |  |  | checkpoint | Ensure the sprinkler head are free from dynamic bend near the joint.
checkpoint-status |  |  | checkpoint | Check the joints
checkpoint-status |  |  | checkpoint | Test Hot and Cold Water Service As Per The Standard 1500 Kpa - 60 mins hydrostatic test
checkpoint-status |  |  | checkpoint | Remove All Residual Water From Pipe Sections
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | External Wall Lining |  |  |  |  | Yes | ICS - External Wall Lining | 8a2d45db-e048-43d6-8b4e-71553e920cfa
checkpoint-status |  |  | checkpoint | Ensure All Materials are checked as per approved drawings
checkpoint-status |  |  | checkpoint | Ensure Suface Cleanliness & MEP clearance check
checkpoint-status |  |  | checkpoint | Check External Insulation Installation
checkpoint-status |  |  | checkpoint | Check External Thermal Break installation
checkpoint-status |  |  | checkpoint | Check External Wall Lining Installation as per approved shop drawings and manufacturer specification
checkpoint-status |  |  | checkpoint | Ensure External Wall Linings joints treated with approved Sealant
checkpoint-status |  |  | checkpoint | Check External Waterproofing application check
checkpoint-status |  |  | checkpoint | External Buildwrap/Breather Membrane installation Check as per approved drawing & manufacturer specification
checkpoint-status |  |  | checkpoint | Application of flasing tape as per approved drawing & manufacturer specification in heads, sill & jambs of Windows/Sliding Doors
checkpoint-status |  |  | checkpoint | Check & Ensure all MEP Service Penetrations on Buildwrap/ Breather membrane is treated as per manufacturer specification
checkpoint-status |  |  | checkpoint | Final Acceptance and Wrapping
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Consultant Inspections - Site Inspection Checklist |  |  |  |  | Yes | Consultant Inspections - Site Inspection Checklist | 917b7669-915b-4b4c-93d7-2fd4a35b70af
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out
text | 921bb2eb-eacf-435b-8287-f274f3669ab2 |  | textbox | Date of Inspection:
text | 0745deed-d3ac-429e-a1cf-eae9de73cc76 |  | textbox | Type of Inspection:
text | f7fd2f50-7be0-400e-8cbe-58975a73d071 |  | textbox | Area inspection relates to
boolean | d724a674-1fa2-44d5-b1fb-2218e6c859ad |  | tickbox | Consultant Inspection attached
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | e35b2254-3175-4558-961a-a29e3a6051d4 |  | textbox | Corrective Actions Required
holdpoint |  |  | signoff | Request Signoff
checklist-sectioned |  |  | checklist | Final Acceptance Checklist |  |  |  |  | Yes | Final Acceptance Checklist | 932d1b33-b285-48be-818c-9d2b0de2905c
checkpoint-group |  |  | section | Items
checkpoint-status |  |  | checkpoint | Main Door
checkpoint-status |  |  | checkpoint | Riser Door
checkpoint-status |  |  | checkpoint | Bathroom Door
checkpoint-status |  |  | checkpoint | BedRoom Door
checkpoint-status |  |  | checkpoint | Door Stopper
checkpoint-status |  |  | checkpoint | Ceiling Painting
checkpoint-status |  |  | checkpoint | Ceiling Cornice
checkpoint-status |  |  | checkpoint | Pelmet
checkpoint-status |  |  | checkpoint | Bulkhead
checkpoint-status |  |  | checkpoint | Wall Painting
checkpoint-status |  |  | checkpoint | Wall Panels
checkpoint-status |  |  | checkpoint | Wall Paper
checkpoint-status |  |  | checkpoint | Wall Tiles & Grouting
checkpoint-status |  |  | checkpoint | Floor Tiles & Grouting
checkpoint-status |  |  | checkpoint | BedHead
checkpoint-status |  |  | checkpoint | Curtain
checkpoint-status |  |  | checkpoint | Carpet
checkpoint-status |  |  | checkpoint | Vinly Floor
checkpoint-status |  |  | checkpoint | Timber Floor
checkpoint-status |  |  | checkpoint | Bedside Storge Cabinet
checkpoint-status |  |  | checkpoint | Laundry cabinet
checkpoint-status |  |  | checkpoint | Wardrobes
checkpoint-status |  |  | checkpoint | Windows
checkpoint-status |  |  | checkpoint | Sliding Doors
checkpoint-status |  |  | checkpoint | Kithen Cabinet
checkpoint-status |  |  | checkpoint | Skirting
checkpoint-status |  |  | checkpoint | Selant Finishes
checkpoint-status |  |  | checkpoint | Kitchen Top
checkpoint-status |  |  | checkpoint | Cistern Top
checkpoint-status |  |  | checkpoint | Vanity cabinet
checkpoint-status |  |  | checkpoint | Vanity Top
checkpoint-status |  |  | checkpoint | Mirror Cabinet
checkpoint-status |  |  | checkpoint | Shower Enclosure
checkpoint-status |  |  | checkpoint | Threshold/Trims
checkpoint-status |  |  | checkpoint | Access panel
checkpoint-status |  |  | checkpoint | Towel Racks
checkpoint-status |  |  | checkpoint | Paper Holder
checkpoint-status |  |  | checkpoint | Robe Hook
checkpoint-status |  |  | checkpoint | Glass Shevles
checkpoint-status |  |  | checkpoint | Shower Set
checkpoint-status |  |  | checkpoint | WC
checkpoint-status |  |  | checkpoint | Bathtub
checkpoint-status |  |  | checkpoint | Wash Basins
checkpoint-status |  |  | checkpoint | Floor Drain covers
checkpoint-status |  |  | checkpoint | Floor Traps
checkpoint-status |  |  | checkpoint | Kitchen Splash back
checkpoint-status |  |  | checkpoint | MEP final Commisioning
checkpoint-status |  |  | checkpoint | Final steel pain Touch ups
checkpoint-status |  |  | checkpoint | TLC ID Plates
checkpoint-status |  |  | checkpoint | Module Cleaning
checkpoint-status |  |  | checkpoint | Roof water proofing
checkpoint-status |  |  | checkpoint | Module Packing
checkpoint-status |  |  | checkpoint | Internal and external Signoff
checkpoint-group |  |  | section | Signatures
checkpoint-status |  |  | checkpoint | TLC - Inspector Sign off
checkpoint-status |  |  | checkpoint | Any 3rd party Sign off
holdpoint |  |  | signoff | Request Sign Off
checkpoint-status |  |  | checkpoint | BC - Sign off
holdpoint |  |  | signoff | Request Sign Off
checklist-flat |  |  | checklist | HWC System |  |  |  |  | Yes | ICS - HWC System | 96491d45-2de5-4f52-bfd2-8f33cb38817f
checkpoint-status |  |  | checkpoint | Ensure Materials as per Specification/Drawing
checkpoint-status |  |  | checkpoint | Ensure the Pipes Sizes
checkpoint-status |  |  | checkpoint | Install Hot & Cold water service in accordance with drawing design
checkpoint-status |  |  | checkpoint | Connection Valves/Taps(Wherever Required)
checkpoint-status |  |  | checkpoint | Install Sleeves (While Run through Metals)
checkpoint-status |  |  | checkpoint | Secure Hangers, Clips, Brackets
checkpoint-status |  |  | checkpoint | Ensure no cross connection between Hot and Cold services
checkpoint-status |  |  | checkpoint | Test Hot and Cold Water Service As Per The Standard BS EN 806-4
checkpoint-status |  |  | checkpoint | Remove All Residual Water From Pipe Sections
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Internal Finishes |  |  |  |  | Yes | ICS - Internal Finishes | 9802f756-42da-4969-b397-1b910b3e9553
checkpoint-status |  |  | checkpoint | Check for Surafce condition and MEP Clearance
checkpoint-status |  |  | checkpoint | Check Material,Accessories as per approved drawing and material specification
checkpoint-status |  |  | checkpoint | Floor underlay installation check
checkpoint-status |  |  | checkpoint | Approved Floor Finishes, Skirting,Transitional Strip/threshold installation check
checkpoint-status |  |  | checkpoint | Ensure Installation of Steel Backing Plates and Studs for Fixing
checkpoint-status |  |  | checkpoint | Cabinet /Wallpanel/Bed Head Installation Check
checkpoint-status |  |  | checkpoint | Check For Alignment,Plumb,Levelness
checkpoint-status |  |  | checkpoint | Fillers application ( If Required)
checkpoint-status |  |  | checkpoint | Check Installation of Shelves & Accessories
checkpoint-status |  |  | checkpoint | Check Installation of Install Cabinet Door panels/Drawers & Handles
checkpoint-status |  |  | checkpoint | Check Kitchen/Vanity/Cistern Top Stone/ Splash back Installation
checkpoint-status |  |  | checkpoint | Check for Operation,Touch up,Defects and Repairs
checkpoint-status |  |  | checkpoint | Check pelmet Installation
checkpoint-status |  |  | checkpoint | Check Curtain Installation
checkpoint-status |  |  | checkpoint | Check Wall Paper Installation ( If Applicable)
checkpoint-status |  |  | checkpoint | Conduct Final Inspection on the Completed Work
checkpoint-status |  |  | checkpoint | Check the Cleaning & Protection
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Sanitary Wares |  |  |  |  | Yes | ICS - Sanitary Wares | 9cf732b0-2cc7-4726-b2a1-7cf7ffeb6b65
checkpoint-status |  |  | checkpoint | Ensure the materials are approved as per Specification
checkpoint-status |  |  | checkpoint | Ensure Water Closet Installtion
checkpoint-status |  |  | checkpoint | Ensure no leak from Flush Valve of Cistern Tank
checkpoint-status |  |  | checkpoint | Test Water Closet
checkpoint-status |  |  | checkpoint | Ensure Basin Intallation
checkpoint-status |  |  | checkpoint | Test Basin
checkpoint-status |  |  | checkpoint | Ensure Shower Installtion
checkpoint-status |  |  | checkpoint | Test Shower
checkpoint-status |  |  | checkpoint | Ensure Accessories Installation
checkpoint-status |  |  | checkpoint | Remove all Residual Water From Floor Waste/Basin/Taps/Hoses
checkpoint-status |  |  | checkpoint | Ensure all Fittings & Fixtures has been Properly Protected
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Module Structure |  |  |  |  | Yes | ICS - Module Structure | 9f1454c3-794a-4d55-b226-af686fffac32
checkpoint-status |  |  | checkpoint | Inspect - Preparatory Steel works (Shearing,Drilling & Cutting)
checkpoint-status |  |  | checkpoint | Inspect - Blasting works for steel materials (SA-2.5)
checkpoint-status |  |  | checkpoint | Inspect - Painting (D.F.T) works for steel materials (ISO 16276-2 or required Project Painting Specifications)
checkpoint-status |  |  | checkpoint | Inspect - Bottom, Top & Ceiling Frames on JIG (Length & Width and Diagonal Dimensions as per approved Drawing)
checkpoint-status |  |  | checkpoint | Ensure & Check - Partial Frames, Main Columns, Ceiling & Floor Joists
checkpoint-status |  |  | checkpoint | Inspect - Full Welding
checkpoint-status |  |  | checkpoint | Inspect - Painting touch up or Final coat (D.F.T) as per ISO 16276-2 or required Project Painting Specifications
checkpoint-status |  |  | checkpoint | Inspection - Completed Work and Record As Built Dimensions
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Add Document Upload Checklist |  |  |  |  | Yes | Add Document Upload Checklist | a1639ad0-7c63-4d5e-bfaa-5e483ecb861b
checkpoint-status |  |  | checkpoint | Documents complete and attached
checklist-flat |  |  | checklist | Consent Documents - BC Amendment Checklist |  |  |  |  | Yes | Consent Documents - BC Amendment Checklist | a3f97b2e-3e2a-4a1c-a9be-44baccfdf71b
checkpoint-status |  |  | checkpoint | Building consent amendment status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | 1429b77e-8424-41ad-82e4-32bc98f55c02 |  | note | PASS above checkpoint when amendment is approved
text | e11624bd-2acb-4668-8774-31f71266b1e4 |  | textbox | Date of application
text | 6d42f31b-299f-4f8d-a656-ec62d91e911c |  | textbox | Reason for application
text | 0d1b8eca-c9cc-4455-b4c3-f22d1c647729 |  | textbox | Date of approval / acceptance
text | 32d0bdbb-2fe9-41d1-b5ab-addaadfffdaa |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | 62c0e7ee-9a5a-4137-9c56-3185c68cf82f |  | tickbox | Council approval of amendment attached
text | 4aba0ebc-7e4e-4d4e-a5ad-a28f95851233 |  | textbox | Updated building consent number (including amendment)
boolean | 65ea0d45-1124-4e02-9811-dece368f17ac |  | tickbox | Latest building consent including amendment has been attached in the "Latest Building Consent" folder to supersede the previous consent
label | 6c9cfcd8-5bbd-4fb1-be3f-7bdbb2ecd1ed |  | note | Ensure this amendment and relevant changes are communicated to the relevant party
checklist-flat |  |  | checklist | On Site - Waterproofing Checklist |  |  |  |  | Yes | On Site QA - Waterproofing Checklist | a6adaa11-7164-429c-b06d-a48032ec10c2
checkpoint-status |  |  | checkpoint | Preparation / Substrate acceptable
checkpoint-status |  |  | checkpoint | Correct product delivered and checked - approval given to install
checkpoint-status |  |  | checkpoint | General photos/comments during install
checkpoint-status |  |  | checkpoint | Any inspections / observations documented, reviewed and closed out
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise remedial / Request trades QA / signoff
checkpoint-status |  |  | checkpoint | Waterproofing install completed, reviewed and approved to meet required specifications
holdpoint |  |  | signoff | Raise remedial / Request signoff
checklist-flat |  |  | checklist | BC Amendment - |  |  |  |  | Yes | Consent Documents - RC Amendment Checklist | a937b630-9593-4aed-8c28-d25309a03288
checkpoint-status |  |  | checkpoint | Resource consent amendment status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | 9de4bede-6c2f-4028-bfc3-b4fdb47b5220 |  | note | PASS above checkpoint when amendment is approved
text | 05387528-95e0-40f6-ac41-18c7b43a4fe0 |  | textbox | Date of application
text | 2170763a-2cd1-4150-b364-ddc50fcea115 |  | textbox | Reason for application
text | ecdb0210-41af-4d23-9973-1397832f9035 |  | textbox | Date of approval / acceptance
text | 27226071-b601-4cd0-b269-6d1e6e32f828 |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | df3f2986-8cdf-4fd3-ab50-95c36092c562 |  | tickbox | Council approval of amendment attached
text | 75337b45-fdc4-4d34-9f2a-7f6c40548f12 |  | textbox | Updated resource consent number (including amendment)
label | 14b1476c-1d66-4287-893e-f4a464546069 |  | note | Ensure this amendment and relevant changes are communicated to the relevant party
checklist-sectioned |  |  | checklist | Modules/Containers- Receiver Inspection Checklist |  |  |  |  | Yes | Modules/Containers- Receiver Inspection Checklist | abbec274-3db9-4d88-a019-d57bbab290f0
checkpoint-group |  |  | section | Internal/External Packing/Loading Checks
checkpoint-status |  |  | checkpoint | Internal-Check any Wall/Floor/Ceiling linings are cracked or damage while received the modules after shipment
checkpoint-status |  |  | checkpoint | Internal-Check any wet patches or water ingress happened
checkpoint-status |  |  | checkpoint | Internal-Check the internal of module to ensure the floor, cabinet, Kitchens, Vanity, Wardrobes, Linen furnitures,All Internal Area of Exposed Walls and doors are clean and no residual dust and no damages
checkpoint-status |  |  | checkpoint | Internal-Check the sliding door/windows to ensure the door is closed and locked, Door runners are Vaccumed, received the keys and ensure no damages
checkpoint-status |  |  | checkpoint | Internal-Check all interior doors, Fruniture Doors and main door are in closed condition & secured, ensure received the key's or Key card to open
checkpoint-status |  |  | checkpoint | Internal-Ensure Mirror Surfaces are protected & no damages
checkpoint-status |  |  | checkpoint | Internal-Check all loose pack items are lashed inside modules are still secured or displaced during transportations
checkpoint-status |  |  | checkpoint | Internal-Visual Check the Installed Temproary walls are not damaged and cause any water ingress inside the modules
checkpoint-status |  |  | checkpoint | Internal-Confirm Styrofoam had been Applied/Fixed and not damage or displaced
checkpoint-status |  |  | checkpoint | Internal-Ensure Moisture Bags are Placed & Hanged inside the Modules (Do Not Lay on the Floor)
checkpoint-status |  |  | checkpoint | External-Check the fastening straps around modules are still tight
checkpoint-status |  |  | checkpoint | External-Check underneath & Roof of Module is cleaned, No damage on the suraface of wrapping and any water ingress
checkpoint-status |  |  | checkpoint | External-Check corner blocks make sure all stagnant watter (if any) are drainied completely if not please drain
checkpoint-status |  |  | checkpoint | External-Check underside of the Module Rockwool (if any) that got Wet
checkpoint-status |  |  | checkpoint | External-Check Styrofoam for all Windows/Sliding doors are still protected the items and ensure No Damage happen during shipment
checkpoint-status |  |  | checkpoint | External-Ensure Riser and Stair case openings are still fixed with temporary closings, ensure no damages happened
checkpoint-status |  |  | checkpoint | External-Ensure Module identification Number can see on Wrapped Module are still able to see it clearly
checkpoint-status |  |  | checkpoint | TLC-Warehouse/Store Supervisor Sign off
checklist-sectioned |  |  | checklist | MIR: |  |  |  |  | Yes | Add Material Inspection Report | abd575e3-fcb8-4f4f-bc80-a152aeeaba4e
checkpoint-group |  |  | section | MIR Status
checkpoint-no-status |  |  | checkpoint | Status:
button | 461765ae-e476-5c01-9077-fcdfaa117117 |  | button | MIR Status | New, Assigned, To Reject, Inspected, Closed
text | cf2f89d4-7599-5cec-9a6d-cab4611769e4 |  | textbox | Reason for rejection:
checkpoint-group |  |  | section | MIR Details
checkpoint-status |  |  | checkpoint | MIR Details Captured below
text | eb65c7e9-309f-5318-848a-be3ffbef8510 |  | textbox | Project:
text | 83d095f1-fc16-5f16-8607-f5339b982673 |  | textbox | Sub Project:
text | 0b6a76b6-4f9b-55f4-93e6-cc57584f7438 |  | textbox | Discipline:
text | 9556e377-2134-5b60-820b-464b163d128f |  | textbox | PO Number:
text | 9c60e0b9-5bba-5d37-90e0-fe07babb96c7 |  | textbox | Description:
text | 0fd559c2-7214-5a42-be00-ca9a2295d797 |  | textbox | Priority
date | ad4a3269-4c77-5dfc-8394-fae525f55d47 |  | date | Due Date:
checkpoint-no-status |  |  | checkpoint | PO Attachment
checkpoint-no-status |  |  | checkpoint | Delivery Dockets
checkpoint-no-status |  |  | checkpoint | Invoices
checkpoint-no-status |  |  | checkpoint | Packing Lists
checkpoint-no-status |  |  | checkpoint | Material Test Reports
checkpoint-no-status |  |  | checkpoint | Material Test Certificates
checkpoint-no-status |  |  | checkpoint | Conformity Certificates
checkpoint-no-status |  |  | checkpoint | Quality Certificates
checkpoint-no-status |  |  | checkpoint | General Certificates
checkpoint-no-status |  |  | checkpoint | Non-Conformity Reports
checkpoint-no-status |  |  | checkpoint | Safety Data Sheets
checkpoint-no-status |  |  | checkpoint | Technical Data Sheets
checkpoint-no-status |  |  | checkpoint | Material Inspection Photos
checkpoint-no-status |  |  | checkpoint | Other attachments
text | d7584e80-6418-5e4a-9a94-9be3bd02969f |  | textbox | Assignee:
text | 8366300f-4120-5b3f-848d-2898753fd305 |  | textbox | Monitors:
folder-normal |  |  | checklist | BC Number |  |  |  |  | Yes | Consent Documents - New Building Consent Checklist | adbe48fc-6e50-4631-a858-9999471758af
checklist-sectioned |  |  | checklist-sectioned | Building Consent Lodgement Checklist
checklist-flat |  |  | checklist-flat | Latest Building Consent - BC Number
folder-normal |  |  | folder-normal | Building Consent Amendments - BC Number
folder-normal |  |  | folder-normal | Minor Variations - BC Number
checklist-flat |  |  | checklist | Mechanical System |  |  |  |  | Yes | ICS - Mechanical System | b13d895a-b24a-4377-8fd4-b2d99f1fa14c
checkpoint-status |  |  | checkpoint | Verify the Duct Materials are Approved as per drawing/Specification
checkpoint-status |  |  | checkpoint | Ensure all duct work installed as per drawing
checkpoint-status |  |  | checkpoint | Ensure ducting adequately supported by brackets, clips or hangers.
checkpoint-status |  |  | checkpoint | Fire damper installation if applicable
checkpoint-status |  |  | checkpoint | Duct Joint Shall be Sealed
checkpoint-status |  |  | checkpoint | Check exhaust air intake and outlet grill locations
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | No. |  |  |  |  | Yes | Add NCR Corrective Action | b7607d7b-5e52-4243-a086-7fe9635a1133
checkpoint-no-status |  |  | checkpoint | NCR Corrective Action
text | 3472264c-9c56-5362-90dd-b8c4b8110359 |  | textbox | ID:
text | a3c1594e-eb11-5164-b7ae-85437844af3c |  | textbox | Cause Analysis:
text | 502c2aa0-df9f-5fd3-8253-96ac6f1195ad |  | textbox | Corrective Action:
text | e5365ac5-91d7-5d98-b886-13284cd5db61 |  | textbox | Action by who:
label | 30a6a28c-2a3c-509d-bae2-d97ed261362e |  | note | Add additional remarks in comments below
checklist-sectioned |  |  | checklist | Concrete Pour - |  |  |  |  | Yes | On Site QA - Concrete Pour Checklist | bba9fb71-246a-44de-96be-45e3f0cb138b
checkpoint-group |  |  | section | Pour Details
checkpoint-status |  |  | checkpoint | Details of Pour Entered
text | 023e3185-d870-4993-9f9f-8bafae1e7c48 |  | textbox | Area to be poured:
text | 6d533239-100c-426a-b56c-f397f2692232 |  | textbox | Date of pour:
checkpoint-status |  |  | checkpoint | Latest drawings available, checked and referenced
checkpoint-group |  |  | section | Formwork and Embedded Items
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Trades QA / Signoff
checkpoint-status |  |  | checkpoint | Grids and RLs clearly marked for reference
checkpoint-status |  |  | checkpoint | Formwork - location, height, falls and dimensions checked and accurate
checkpoint-status |  |  | checkpoint | Formwork sufficiently fixed and braced
checkpoint-status |  |  | checkpoint | Any rebates/ nibs / cast in items are correctly positioned, sized and appropriately fixed in place
checkpoint-status |  |  | checkpoint | Service penetrations formed correctly and locations checked/correct
checkpoint-status |  |  | checkpoint | All surfaces correctly prepared (e.g. joints to existing concrete, release agent to formwork etc)
checkpoint-status |  |  | checkpoint | Any control joints/ stop ends installed accurately and correctly braced
checkpoint-status |  |  | checkpoint | Any additional formwork photos and observations
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All formwork elements completed and ready for concrete pour ( excess debris removed )
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-group |  |  | section | Reinforcing
checkpoint-status |  |  | checkpoint | Trades QA received, attached, reviewed and approved
holdpoint |  |  | signoff | Raise Remedial / Request Trades QA / Signoff
checkpoint-status |  |  | checkpoint | Size and type correct to specification
checkpoint-status |  |  | checkpoint | Reinforcing spacing and location correct
checkpoint-status |  |  | checkpoint | Specified covers checked/correct
checkpoint-status |  |  | checkpoint | Splice laps checked/correct
checkpoint-status |  |  | checkpoint | Any starter bars are installed correctly (location, size and spacing )
checkpoint-status |  |  | checkpoint | Any additional items installed/ completed (trimmer bars etc) and excess reinforcing removed
checkpoint-status |  |  | checkpoint | Reinforcing installed correctly to specification and ready for concrete to be placed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-group |  |  | section | Pre-Pour Completion (Approval to pour)
checkpoint-status |  |  | checkpoint | Any waterproofing elements have been correctly installed and checked
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Any relevant service requirements completed (locations checked and accurate)
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Engineer inspection completed - any observations / remedial work documented and closed out
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Council inspection completed and attached
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All relevant inspections completed and attached
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Main contractor inspection completed - Approval given to pour concrete
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-group |  |  | section | Concrete Supplier Specifics
checkpoint-no-status |  |  | checkpoint | Concrete Supplier Specifics
button | 9316ee2b-a916-4347-868d-b1d1853ffcf4 |  | button | Test blocks booked | N/A, No,Yes
checkpoint-status |  |  | checkpoint | All concrete dockets photographed/ attached
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-group |  |  | section | Concrete Distribution
checkpoint-no-status |  |  | checkpoint | Concrete Distribution
text | cd8664e7-e763-4ac5-afc0-a575032ff589 |  | textbox | Who is distributing the concrete:
text | a80286e0-e605-4291-979c-c8f85268ed65 |  | textbox | How is the concrete distributed:
checkpoint-status |  |  | checkpoint | General distribution photos, documents and observations attached
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | All concrete distributed correctly (area left clean and tidy)
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-group |  |  | section | Placement Method
checkpoint-status |  |  | checkpoint | Placement methodology confirmed and necessary plant and equipment on site
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Heights and falls checked/confirmed before placement
button | f2402bd2-407f-4076-a954-4854b5d0a199 |  | button | Is the cover correct to specification | No,Yes
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | General photos and observations of concrete placement attached
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Heights and falls checked/ confirmed after placement
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Any curing compound applied correctly
checkpoint-status |  |  | checkpoint | Concrete placement completed - specified level of finish achieved
holdpoint |  |  | signoff | Raise Remedial / Request Trades QA / Signoff
checkpoint-status |  |  | checkpoint | Area left clean and tidy
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-group |  |  | section | Post Pour Checks/Sign Off
checkpoint-status |  |  | checkpoint | Any remedial work completed
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checkpoint-status |  |  | checkpoint | Concrete Pour completed - All final checks and documentation completed and attached
holdpoint |  |  | signoff | Raise remedial / Request Signoff
checklist-sectioned |  |  | checklist | Shipping Container Inspection Checklist |  |  |  |  | Yes | Shipping Container Inspection Checklist | c4694b50-25ec-4454-9521-f62c2216e4bf
checkpoint-group |  |  | section | External Checks
checkpoint-status |  |  | checkpoint | Check Visual Inspection of Container to ensure no Surface Damage or Holes
checkpoint-status |  |  | checkpoint | Ensure the external surface is clean and no dust/sand
checkpoint-status |  |  | checkpoint | Enure there is no Algae growth in the under carriage
checkpoint-status |  |  | checkpoint | Ensure Container Identification Number is Visible in all sides
checkpoint-status |  |  | checkpoint | Ensure Container Licence Plate is available
checkpoint-status |  |  | checkpoint | Ensure the Doors are locked and sealed
checkpoint-status |  |  | checkpoint | Clean the Container with Compressed air/water before loading
checkpoint-status |  |  | checkpoint | Ensure the Contaner is lashed with the truck after loading
checkpoint-group |  |  | section | Internal Checks
checkpoint-status |  |  | checkpoint | Ensure Internal Floor/Walls/Ceiling are clean before loading
checkpoint-status |  |  | checkpoint | Ensure no Pinholes visible for water ingress & Seal (if any)
checkpoint-status |  |  | checkpoint | Enure the Timber Floor is intact without any damages
checkpoint-status |  |  | checkpoint | Ensure all the materials are loaded as per Packing list
checkpoint-status |  |  | checkpoint | Ensure the Materials are protected for any damages
checkpoint-status |  |  | checkpoint | Ensure the materials are lashed with internal hooks
holdpoint |  |  | signoff | Request signoff
checklist-sectioned |  |  | checklist | On Site - Piling Checklist |  |  |  |  | Yes | On Site QA - Piling Checklist | cb82aafd-18fc-4295-8e71-13442bb33e7c
checkpoint-group |  |  | section | Pre Commencement
checkpoint-status |  |  | checkpoint | Piles setout, surveyed and clearly marked
checkpoint-status |  |  | checkpoint | Accurate RL confirmed for piling reference
checkpoint-status |  |  | checkpoint | Acceptable site conditions and access for piling rig
checkpoint-status |  |  | checkpoint | Additional photos/ observations / reports attached
checkpoint-status |  |  | checkpoint | Approval given to commence piling
boolean | d6d2a27c-507c-44c9-8aef-00efa0a2cc55 |  | tickbox | approval given to dig
boolean | a62dce44-ca48-48f5-8fa8-d733a2bcde17 |  | tickbox | relevant services identified and isolated / clearly marked
boolean | 2eadfe1e-21a4-4830-ba32-b4bd8dbc5ebe |  | tickbox | relevant information communicated to piling trade
boolean | 8b07a40f-61fa-40a5-9da3-953cc9d7a20d |  | tickbox | any environmental requirements considered and enacted
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-group |  |  | section | Individual Piling QA
checkpoint-status |  |  | checkpoint | Piling QA completed and attached
holdpoint |  |  | signoff | Raise Remedial / Request trades QA /Signoff
checkpoint-group |  |  | section | Inspections/ Completion and Handover
checkpoint-status |  |  | checkpoint | Relevant inspections completed and attached - any observations recorded and closed out
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Piling spoil removed and work area left clean and tidy
holdpoint |  |  | signoff | Raise remedial / Request signoff
checkpoint-status |  |  | checkpoint | Any additional completion/handover documents completed and attached
checkpoint-status |  |  | checkpoint | All piles completed (locations and heights checked and correct within tolerance)
holdpoint |  |  | signoff | Raise remedial / Request signoff
checklist-sectioned |  |  | checklist | Module Assembly & Erection Inspection Checklist |  |  |  |  | Yes | Module Assembly & Erection Inspection Checklist | cc8d46c3-fea0-48ce-8edd-c0dd427712a4
checkpoint-group |  |  | section | External Checks
checkpoint-status |  |  | checkpoint | Check Module Base level as per acceptable Tolerances
checkpoint-status |  |  | checkpoint | Check Module to module Gaps as per Acceptable Tolerances
checkpoint-status |  |  | checkpoint | Ensure correct Guide Plates/Base Plates installed as per drawing
checkpoint-status |  |  | checkpoint | Ensure Connection plates are installed and bolted
checkpoint-status |  |  | checkpoint | Ensure Riser opening are aligned for connections
checkpoint-status |  |  | checkpoint | Check for additional connection plates for Corridor/Balcony/FaÃ§ade/Staircase/Liftcore are installed
checkpoint-status |  |  | checkpoint | Check Module alignment matching with adjacent module level
checkpoint-group |  |  | section | Internal Checks
checkpoint-status |  |  | checkpoint | Remove Temporary Walls and check for any water leak & Clean if any
checkpoint-status |  |  | checkpoint | Check module Floor is level with connecting module
checkpoint-status |  |  | checkpoint | Check Electrical, Plumbing, mechanical connections are in alignment for connection to adjacent module
checkpoint-status |  |  | checkpoint | Check all Module components packed inside are without damages
checkpoint-status |  |  | checkpoint | Enure all door/windows are locked during lifting/erection
holdpoint |  |  | signoff | Request signoff
checklist-flat |  |  | checklist | Module Water Tightness |  |  |  |  | Yes | ICS - Module Water Tightness | ce5a93c6-4fc3-4fe4-b9d8-6b50df03a248
checkpoint-status |  |  | checkpoint | Ensure the materials are as per approved project specifications
checkpoint-status |  |  | checkpoint | Ensure the surface is clean
checkpoint-status |  |  | checkpoint | Ensure all Corner Blocks perimeter is sealed with weather sealant & Weather Seal Tapes
checkpoint-status |  |  | checkpoint | Ensure all External Wall Joints & Screw Heads are sealed with weather sealant
checkpoint-status |  |  | checkpoint | Ensure all Roof CFC Joints are sealed with weather sealant & Weather Seal Tapes
checkpoint-status |  |  | checkpoint | Ensure all MEP Penetrations, Exhaust, Duct & Vent openings are sealed with weather proof covers & Weather Seal Tapes
checkpoint-status |  |  | checkpoint | Ensure all Temporary Wall/Doors/Staircase Opening CFC Joints are sealed with weather sealant & Weather Seal Tapes
checkpoint-status |  |  | checkpoint | Ensure all Riser Areas CFC Joints are sealed with weather sealant & Weather Seal Tapes
checkpoint-status |  |  | checkpoint | Ensure all Connection Plate area perimeter is sealed with weather sealant & Weather Seal Tapes & CFC Covers(if any)
checkpoint-status |  |  | checkpoint | Final Cleaning/Protection
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Minor Variation - |  |  |  |  | Yes | Consent Documents - Minor Variation Checklist | cfc1a280-8458-4b48-8842-9913ebd1b1ea
checkpoint-status |  |  | checkpoint | Minor variation status (Pass once approved & all information is attached including observations, correspondence & close out evidence)
label | a66fb84a-46bb-439d-8151-9ef3aeba4171 |  | note | PASS above checkpoint when variation is approved
label | 1690e45b-9faf-40fd-8546-ce72dd4d66cc |  | note | If minor variation is a FAIL - document why below and follow appropriate corrective actions
text | a17fd54b-3e89-4a7d-bf48-f672966d21cd |  | textbox | Date of application
text | 71f82fca-b8af-4915-8c14-4a46db0dc64f |  | textbox | Reason for application
text | ef357f2e-9eba-4b34-9a00-63743e5177a8 |  | textbox | Date of approval / acceptance
text | 50d2c0a1-dac1-42ab-a3b8-2ac9a3441cfc |  | textbox | Inspection Type Code (If applicable e.g. Site meeting IME)
boolean | abe8d6aa-d4e0-4784-a7e7-dadb37108773 |  | tickbox | Council approval of minor variation attached
checklist-flat |  |  | checklist | DWV System |  |  |  |  | Yes | ICS - DWV System | d061f7ed-f3c2-41db-b405-6ee856a9fb45
checkpoint-status |  |  | checkpoint | Ensure the Materials are Approved as per the Specification
checkpoint-status |  |  | checkpoint | Ensure the Pre-cut Pipe Penetrations (holes)
checkpoint-status |  |  | checkpoint | Install waste service in accordance with drawing design
checkpoint-status |  |  | checkpoint | All pipework secure and supported with Brackets and Clips
checkpoint-status |  |  | checkpoint | Pipework installed with correct grades and falls
checkpoint-status |  |  | checkpoint | Test DWV As Per BS EN 1610:2015 10kpa-3 min with air or 0,1 m head of water in 1 hour
checkpoint-status |  |  | checkpoint | Cleaning & Protection
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | No. |  |  |  |  | Yes | Add WIR Lines | da8acb0b-4a98-4323-9285-157afc302aff
checkpoint-no-status |  |  | checkpoint | WIR Line
text | e04376fa-7d8f-518e-b34f-0f92c422f982 |  | textbox | Action:
text | 8654aa37-6e7b-5716-a308-a9c43aa36422 |  | textbox | Prod Order:
text | 639f18b9-0b32-5079-8da0-d28325929581 |  | textbox | Order Quantity:
text | 7331952e-2e24-5360-add5-ff36e1de4417 |  | textbox | Total Quantity:
text | 03f51a5e-3c9f-5cd6-abfc-ecb2f0c154c5 |  | textbox | Accepted Quantity:
text | 8b8b8cb7-e17d-5066-9669-8d9e4c9c91e5 |  | textbox | Rejected Quantity:
text | 024b6ad6-3960-5f0f-b380-da1226aae91f |  | textbox | Remaining Order Quantity:
checklist-flat |  |  | checklist | Electrical Work |  |  |  |  | Yes | ICS - Electrical Work | dabb285a-ff9d-4b42-8ae9-f9f0bde519ff
checkpoint-status |  |  | checkpoint | Ensure the Materials are Approves as per Specifications
checkpoint-status |  |  | checkpoint | Ensure the Cable Protection (Cable penetrates through steels)
checkpoint-status |  |  | checkpoint | Check the Cable Run through
checkpoint-status |  |  | checkpoint | Verify the Proximity between power cables and other services (ex..Data Cable, Drain pipe, Hot & Cold Water Pipe, Gas Lines, etc…)
checkpoint-status |  |  | checkpoint | Ensure the Connection Power points, Switch box, ceiling lights, LED lights & Main DB
checkpoint-status |  |  | checkpoint | Ensure the screws are fastened tightly on steel plate support for Power points, Switch box, ceiling lights, LED lights & Main DB
checkpoint-status |  |  | checkpoint | Work Acceptance and Functional Test
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Set Out / Surveying - |  |  |  |  | Yes | On Site QA - Set Out / Surveying Checklist | dc89230e-8487-46a8-8cd9-b83911778404
checkpoint-status |  |  | checkpoint | Any RL's setout are correct, labelled and photographed
checkpoint-status |  |  | checkpoint | Any grid setout are correct, labelled and photographed
checkpoint-status |  |  | checkpoint | Any other relevant setout/ survey documentation attached
checkpoint-status |  |  | checkpoint | Survey work completed, checked and accurate
holdpoint |  |  | signoff | Request Surveyors documentation / signoff
checklist-sectioned |  |  | checklist | NCR Number: |  |  |  |  | Yes | Offsite QA - Non-Conformance Report | e5d132f3-7d35-4815-a80b-a2b82bb9171d
checkpoint-group |  |  | section | Identification
checkpoint-status |  |  | checkpoint | Identification Details Entered
text | db3ae9c4-688d-4fa9-94a2-130decb0bd62 |  | textbox | NCR - Ref. Number:
text | 9d5adb8c-6b1a-47f8-a8dd-b39db3076883 |  | textbox | Date:
text | e18a0bca-3689-416d-9267-0666661b4925 |  | textbox | Originator Name:
text | 0dd3876e-db6b-44d8-9c54-2f23da2cce90 |  | textbox | Client / Supplier:
text | 28b58893-0feb-462e-af24-d252ac21c6cd |  | textbox | Project:
text | 31200081-0c7f-49cb-9924-4e2797df8007 |  | textbox | PO Number / Job Number:
text | e5c21520-1c6a-4010-82f8-0bc2221006fa |  | textbox | Part Description:
text | 6a5da622-818e-4253-a244-ed72bc316d79 |  | textbox | Part ID:
text | 1751fdf4-4f47-4fd3-b5be-0001b6de7860 |  | textbox | Quantity:
text | 386bb5f6-5e04-472f-a177-cacd83099d70 |  | textbox | Drawing No (If Req.):
select | c118e886-5d2c-4140-aaef-91fad3deab5e |  | dropdown | Found during what activity: | Final inspection, In-process inspection, Other,Incoming inspection
text | 9128fbbc-ddd5-4a20-9cf0-f829fa41b50a |  | textbox | Description of non-conformance
text | afc4f67e-9165-4d11-b2d8-c1f13382b6bd |  | textbox | Corrective and Preventative Action taken to prevent misuse
checkpoint-group |  |  | section | Disposition and Close Out
checkpoint-status |  |  | checkpoint | Disposition / Status of NCR (PASS if Use-as-is, FAIL for others)
radio | b1bbcd86-a53d-4b1f-8cfc-27feb648a24d |  | radio | Disposition | Reject, Repair, Return to Supplier, Rework,Use-as-is
text | 166f9eb2-4bd9-4da4-ad41-22a9d0fc4bb2 |  | textbox | Production Engineer:
text | 1d50048a-b07a-435e-8d46-0e0cfbe433c9 |  | textbox | Name:
text | e9f28f1c-ad98-4d82-a7cb-beb89f52c97a |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Approval of Use-as-is
boolean | 0df26a06-d4c5-419c-ac71-bc2b4b2e2cf0 |  | tickbox | Non-critical NC
boolean | becc6f72-5ac7-4ca9-a3b7-c6abc3a78d78 |  | tickbox | Critical NC
checkpoint-status |  |  | checkpoint | Department Engineer/Officer
text | 65294bd2-358e-4874-95e0-1fb17fa74ea7 |  | textbox | Name:
text | 739bc361-eb72-41cf-9d01-130bc1ca4867 |  | textbox | Date:
checkpoint-status |  |  | checkpoint | HOD
text | c368e137-275c-49d7-81f4-e53983e19739 |  | textbox | Name:
text | ce06c4b7-4f3f-44d5-a34a-e6143872cccd |  | textbox | Date:
checkpoint-status |  |  | checkpoint | Final Approval
text | 545dc5b9-a187-4f44-9116-870ac56ae246 |  | textbox | Quality Inspector Name:
text | 20496999-9c64-4f78-8865-64e46d9a64d5 |  | textbox | Date:
checklist-flat |  |  | checklist | Glazing Works |  |  |  |  | Yes | ICS - Glazing Works | e7e52cba-b44d-4aa0-aac6-2df8e2c74c6f
checkpoint-status |  |  | checkpoint | Ensure the Type, Size and thickness, Marking of materials, and any physical damages/defective as per approved drawing.
checkpoint-status |  |  | checkpoint | Ensure setting out dimensions
checkpoint-status |  |  | checkpoint | Check- Glass fixing with necessary accessories
checkpoint-status |  |  | checkpoint | Check- Sealant finishes where ever applicable
checkpoint-status |  |  | checkpoint | Ensure setting out dimensions required
checkpoint-status |  |  | checkpoint | Check Mirror Installation as per approved drawing
checkpoint-status |  |  | checkpoint | Final Inspection and Protection work
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Windows |  |  |  |  | Yes | ICS - Windows | ea77535e-6642-4817-8328-ab19bc80bbc6
checkpoint-status |  |  | checkpoint | Setting out reference line in relation to wall alignment and Sufarce condition
checkpoint-status |  |  | checkpoint | Check Materials, Dimensions, Markings are as per approved drawings
checkpoint-status |  |  | checkpoint | Window Casing Installation (If Required)
checkpoint-status |  |  | checkpoint | Check the Dimensions of Wall Openings are as per approved drawings
checkpoint-status |  |  | checkpoint | Check Vapour barrier, EPDM Membrane,Sill tape /Flashing tapes as per Approved Drawing
checkpoint-status |  |  | checkpoint | PreFabricated Windows Frame Installation
checkpoint-status |  |  | checkpoint | Check Frame alignment and plumb
checkpoint-status |  |  | checkpoint | Check Accessories,Flashing Installation
checkpoint-status |  |  | checkpoint | Check Gap Fillers, Sealant finishes
checkpoint-status |  |  | checkpoint | Check the Water Tightness test and Final check
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Doors |  |  |  |  | Yes | ICS - Doors | efdcd821-9b54-45ea-9f0d-96b1156834f9
checkpoint-no-status |  |  | checkpoint | Door Type
text | 8ae8405b-4f8e-50a7-99fe-7df7b9fcc67b |  | textbox | Door Type
checkpoint-status |  |  | checkpoint | Setting out/opening reference line in relation to wall alignment
checkpoint-status |  |  | checkpoint | Ensure the dimensions of the Frames, Door panel, Ironmongeries, and Architraves are as per approved drawing.
checkpoint-status |  |  | checkpoint | Door Frame Installation
checkpoint-status |  |  | checkpoint | Check the Frame alignment and plumb
checkpoint-status |  |  | checkpoint | Door Panel,Stopper Installation and Alignment Check
checkpoint-status |  |  | checkpoint | Ironmongeries, Door Seal Installation
checkpoint-status |  |  | checkpoint | Frame and Wall Gap Filler Installation
checkpoint-status |  |  | checkpoint | Architrave Installations
checkpoint-status |  |  | checkpoint | Check For operation, Defects, Patch nail holes and Repair Works (If any)
checkpoint-status |  |  | checkpoint | Final Inspection & Protection Work
checkpoint-status |  |  | checkpoint | TLC Inspector Name
holdpoint |  |  | signoff | Add Signature / Request Sign Off
checklist-flat |  |  | checklist | Building Compliance - Council Inspection Checklist |  |  |  |  | Yes | Building Compliance - Council Inspection Checklist | f4f476b3-f4fb-49c6-9d84-851149b39910
checkpoint-status |  |  | checkpoint | Inspection completed, attached and any relevant observations closed out (Pass once all information is attached including observations with evidence of closeout)
text | 28b93d55-bad7-45df-9eef-37a95a2e9aa2 |  | textbox | Date of Inspection:
text | c93679c3-7bd3-4d8a-991c-da5f2925de3a |  | textbox | Type of Inspection:
text | 61f3784d-aa81-4905-9d78-40da0178f9e3 |  | textbox | Area inspection relates to
text | 9c5c5101-48cb-4340-82b6-372b01c53227 |  | textbox | Inspection Outcome
boolean | 7582f119-7eea-43fa-ac99-a0dd5fb916e2 |  | tickbox | Council Inspection attached
holdpoint |  |  | signoff | Request Signoff
checkpoint-status |  |  | checkpoint | All Relevant Observation Closeout evidence attached here if applicable (Pass once completed)
text | ca7fd03f-13b5-4343-b5bb-76cb3a94800b |  | textbox | Outstanding Information Required
checklist-sectioned |  |  | checklist | Module Packing/Loading Inspection Checklist |  |  |  |  | Yes | Module Packing/Loading Inspection Checklist | ffa7cace-0bd4-4964-ae5b-ddae487069bc
checkpoint-group |  |  | section | Internal Checks
checkpoint-status |  |  | checkpoint | Check the internal of module to ensure the floor, cabinet, furnitures and doors are clean and no residual dust
checkpoint-status |  |  | checkpoint | Check the sliding door to ensure the door is closed and locked. Place the key inside with plastic strap key chain
checkpoint-status |  |  | checkpoint | Check the protection for all items required protection against damage
checkpoint-status |  |  | checkpoint | Check all interior door and main door are in closed condition
checkpoint-status |  |  | checkpoint | Check all loose pack items are lashed inside modules and protected against damage
checkpoint-status |  |  | checkpoint | Check the application of protective membrane wherever required
checkpoint-status |  |  | checkpoint | Check the Installation of Temporaray Exposed Walls
checkpoint-group |  |  | section | External Checks
checkpoint-status |  |  | checkpoint | Visual checks to ensure there is no obvious damage on wrapping of module
checkpoint-status |  |  | checkpoint | Check that all exterior surfaces of wrapping is clean
checkpoint-status |  |  | checkpoint | Check underneat of Module is cleaned with compressed air and make sure no Dust is present
checkpoint-status |  |  | checkpoint | Check corner blocks make sure are clean with air compressor
checkpoint-status |  |  | checkpoint | Check the fastening straps around modules are tight
checkpoint-status |  |  | checkpoint | Check Polystyrene protection for all items required protection against damage ( Windows/Sliding Doors)
checkpoint-status |  |  | checkpoint | Ensure Riser and Stair case openings are fixed with temporary covers
checkpoint-status |  |  | checkpoint | Ensure Hazard Markings and labelling of Access Openings
checkpoint-status |  |  | checkpoint | Final check of shrink wrapping for the touch-up welding
checkpoint-status |  |  | checkpoint | Ensure Module identification Number is Available
holdpoint |  |  | signoff | Request signoff