## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | 204.3 Earthworks and Subgrade Acceptance ITP | itp |  |  |  |  | 204.3 Earthworks and Subgrade Acceptance ITP
checkpoint | 1 - Survey Set Out
label | Acceptance Criteria - Clearly mark limits of works including chainage, offsets, cut/fill level etc. as required
checkpoint | 2 - Material Property Testing - Type B
label | Spec. Reference - 204.04 (c), 204.141, 204.06 (c)
label | Acceptance Criteria - Material to be tested as per Scale B.
label | ○ One test to show compliance. Visual inspection required to ensure materials are consistent day to day.
label | ○ 1 Lot test to determine CBR and Swell
label | ○ CBR > 5%
label | ○ Swell < 5% (IDEALLY LESS THAN 2.5%)
label | ○ LL – NA (no table 204.141 data)
label | ○ PI - NA (no table 204.141 data)
label | ○ Maximum Particle Dimension *(visual test small than 150mm particles)
label | Witness / Hold Point - H
label | Inspection & Verified by: Client - RRV
holdpoint | HOLD POINT
checkpoint | 3 - In-situ Cut Floor Subgrade Swell
label | Spec. Reference - 204.06(e)
label | Acceptance Criteria - Material within 400mm below cut floor shall have a swell <2.5%
checkpoint | 4 - Material – Topsoil
label | Spec. Reference - 204.04, 204.05
label | Acceptance Criteria - Strip and store topsoil on site to be re-spread at end of works. Ensure material is protected and not able to be eroded. Confirm depth of stripping with superintendent.
label | Witness / Hold Point - H
label | Frequency - Note: Single hold point released on 1st LOT unless material changes with visual inspection
label | Inspection & Verified by: Client - RRV
holdpoint | HOLD POINT
checkpoint | 5 - Unsuitable Material
label | Spec. Reference - 204.07
label | Acceptance Criteria - i. contractor is responsible for rip work, water, compact top 150mm layer.
label | ii. Unsuitable material greater than 150mm depth, to be treated upon agreement.
label | ○ Where unsuitable material is encountered proposed treatment to be submitted for review.
label | Witness / Hold Point - H
label | Inspection & Verified by: Client - RRV
holdpoint | HOLD POINT
checkpoint | 6 - Groundwater
label | Spec. Reference - 204.06(h)
label | Acceptance Criteria - Where groundwater is encountered, notification and proposed action to be submitted for review. Approvals from relevant authorities required for treatment/disposal of groundwater.
label | Witness / Hold Point - H
label | Inspection & Verified by: Client - RRV
holdpoint | HOLD POINT
checkpoint | 7 - Schedule for Tolerances, Material Properties and Compaction Testing
label | Spec. Reference - 204.16
label | Acceptance Criteria - Table 204.161
label | ○ Road Name: Sturt Highway and Calder Highway
label | ○ Chainage/Location: Within Limits of Works
label | – – – – – – – – – – – – – – –
label | Table 204.161 Schedule for Surface Tolerance, Material Properties and Compaction Testing
label | – – – – – – – – – – – – – – –
label | Road Name ¦¦ Chainage / Location ¦¦ Scale of Surface Level Measurement (A, B or C) ¦¦ Scale of Material Property Testing (A or B) ¦¦ Scale of Compaction (A, B, or C)
label | All ¦¦ Within Limits of Works ¦¦ A ¦¦ B ¦¦ A
label | – – – – – – – – – – – – – – –
label | Note: Where no level of testing is nominated, Scale A applies
checkpoint | 8 - Compaction – Cut Floor
label | Spec. Reference - 204.131
label | Acceptance Criteria - Table 204.131 – Scale A
label | ○ Testing of cut floor areas. Rip areas 150mm deep and compact.
label | ○ Compaction = 99% STD
label | ○ Lot size = 1 day production (or 10,000m2)
label | ○ Testing frequency = Every 2nd lot
checkpoint | 9 - Compaction Testing – Type B Fill
label | Spec. Reference - 204.131
label | Acceptance Criteria - Table 204.131 – Scale A
label | ○ Testing of placed Fill. Max 200mm deep layers, average 150mm deep and compact.
label | ○ Compaction = 99% STD
label | ○ Lot size = 1 day production (or 10,000m2)
label | ○ Testing frequency = Every 2nd lot
checkpoint | 10 - Surface Level Measurement
label | Spec. Reference - 204.031
label | Acceptance Criteria - Scale A – GPS or TOTAL STATION PICK UP
label | ○ 80 Random pick up points per lot
label | ○ Average +5 to -15mm
label | ○ Standard deviation maximum 12mm
checkpoint | 11 - Test Rolling – Approval to Place Subsequent Layer
label | Spec. Reference - 204.12
label | Acceptance Criteria - Place of fill on prepared surface – HP
label | ○ Proof Roll prior to placement of subsequent layers.
label | Witness / Hold Point - H
label | Inspection & Verified by: Client - RRV
holdpoint | HOLD POINT
checkpoint | 12 - Maintenance of Final Earthwork Surface
label | Spec. Reference - 204.15
label | Acceptance Criteria - Material within 150mm of subgrade surface to be maintained at not less than 70% of OMC prior to placement of any pavement layer.