## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | 701.2 Stormwater Drainage ITP | itp |  |  |  |  | 701.2 Stormwater Drainage ITP
checkpoint | 1 - In-Situ Pits
label | Spec. Reference - 705
label | Acceptance Criteria - F92 Mesh installed in accordance with Standard Drawings.
checkpoint | 2 - In-Situ Pits
label | Spec. Reference - 705
label | Acceptance Criteria - Concrete used to construct pits is 25 MPa concrete as per Standard Drawings and specification.
checkpoint | 3 - In-Situ Pits
label | Spec. Reference - 705
label | Acceptance Criteria - Galvanised steel or plastic-coated steel step irons installed in pits greater than 1 meter in depth.
checkpoint | 4 - In-Situ Pits
label | Spec. Reference - 705
label | Acceptance Criteria - Correct pit lid class in accordance with Standard Drawings and specification.
checkpoint | 5 - Bedding
label | Spec. Reference - 701.11
label | Acceptance Criteria - Bedding depth at least 100mm, Bedding class 3 crushed rock.
checkpoint | 6 - Laying
label | Spec. Reference - 701.12
label | Acceptance Criteria - Socket ends of pipe section facing upstream and fully entered. Rubber ring correctly set.
checkpoint | 7 - Backfilling
label | Spec. Reference - 701.15
label | Acceptance Criteria - Class 3 Crushed Rock backfill used at detailed on long sections.
label | ○ Compaction ≥ 97% standard
textbox | ○ Test Certificate No.
label | ○ Minimum testing frequency of 20% of all LOTS.
label | ○ LOT is defined as from one pit to another for each layer. Typically, 1 LOT between each pit assuming 1m depth of backfill.
checkpoint | 8 - Final Acceptance
label | Spec. Reference - 701
label | Acceptance Criteria - Inspection and acceptance of finished pits and pipes.
label | Witness / Hold Point - H
holdpoint | HOLD POINT