## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | 703.1 Kerb & Channel ITP | itp |  |  |  |  | 703.1 Kerb & Channel ITP
checkpoint | 1 - Survey Set Out
label | Spec. Reference - 703.15, 703.14
label | Acceptance Criteria - Superintendent to inspect and confirm set out.
label | Tolerances:
label | ○ -0 to +10mm Line & Level
label | ○ ≤5mm deviation from 3m straight edge
label | Verification / Record - Superintendent
label | Witness / Hold Point - H
holdpoint | HOLD POINT
checkpoint | 2 - Temperature
label | Spec. Reference - 703.09
label | Acceptance Criteria - Place concrete only between air temperature of 5°C to 35°C
checkpoint | 3 - Bedding
label | Spec. Reference - 703.19
label | Acceptance Criteria - Bedding to design details but not less than 75mm compacted thickness. Bedding moist prior to concreting.
checkpoint | 4 - Surface Finish
label | Spec. Reference - 703.23
label | Acceptance Criteria - Steel trowel finish. Slurry render placed within 30minutes of machine extrusion.
checkpoint | 5 - Joints
label | Spec. Reference - 703.24
label | Acceptance Criteria - Transverse joints to be at regular intervals not exceeding 2.5m. Made with guillotine cutting between 40% to 70% of depth & tool finished to 5mm wide and 20mm depth.
checkpoint | 6 - Conduit Markings
label | Spec. Reference - 703.26
label | Acceptance Criteria - Mark position of all conduit crossings with a tool into fresh concrete.
checkpoint | 7 - Cracking of Concrete
label | Spec. Reference - 703.28
label | Acceptance Criteria - No surface cracks greater than .2mm, Cracked sections shall be removed to min length of 1m and new sections dowelled.