## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP0007 – Pavement Type 5 PT05 Proposed Crossover | itp |  |  |  | Yes | ITP0007 – Pavement Type 5 PT05 Proposed Crossover
section | 1. Subgrade
checkpoint | 1.1 - Test roll subgrade
label | METHOD - T
label | REFERENCE - S.D.X6
label | CRITERIA - Subgrade to withstand test rolling NA according to S.D.X6
checkpoint | 1.2 - Testing of subgrade level
label | METHOD - T
label | REFERENCE - S.D.X6
label | CRITERIA - Subgrade Compaction NA according to S.D.X.10
label | VALUE - NA
label | VALUE - Subgrade material – crushed rock / clay
checkpoint | 1.3 - Level of sub-grade
label | METHOD - M
label | REFERENCE - S.D.X6
label | CRITERIA - Earthworks shall be finished to conform to the levels, lines, grades and cross-sections specified or shown on the drawings
label | • Width: ± 50mm from right angles to the design line.
label | VALUE - {Value}
label | • Level: mean deviation from design no more than +15 to -30mm, max. below the specified level
label | VALUE - {Value}
label | • Thickness: Not more than 15mm less than the specified thickness.
label | VALUE - {Value}
label | • Shape: No point on the surface of the pavement layer shall vary by more than 8mm from a 3m straight edge or 10mm from a 6m straight edge.
label | VALUE - {Value}
section | 2. Base Layer
checkpoint | 2.1 - Compaction
label | METHOD - T
label | REFERENCE - S.D.X6
label | CRITERIA - No compaction testing required for subgrade according to S.D.X10
label | VALUE - NA
checkpoint | 2.2 - Conformity with drawings -
label | METHOD - V
label | REFERENCE - S.D.X6
label | CRITERIA - Material: 75MM THICK CLASS 3 20MM FINE CRUSHED CONCRETE RECYCLED
label | VALUE - 75MM THICK CLASS 3 20MM FINE CRUSHED ROCK
label | • Thickness: Not more or less than the specified thickness. 75MM
label | VALUE - 75MM
label | • Width: +/- 50mm from right angles to the design line.
label | VALUE - {Value}
label | • Level: Mean deviation from design no more than +6 to -10mm, max. standard deviation 10.
label | VALUE - {Value}
label | • Shape: No point on the surface of the pavement layer shall vary by more than 8mm from a 3m straight edge or 10mm from a 6m straight edge.
label | VALUE - {Value}
section | 3. Concrete Layer
checkpoint | 3.1 - Concrete Pour
label | METHOD - T
label | REFERENCE - S.D.X6
label | CRITERIA - Concrete pour 32Mpa 14mm aggregate 80mm slump – 200mm thick, with dowelled expansion joints every 12 meter max centres.
label | • Saw cut / tools joints every 1.5 max centres each way.
label | • No Colour oxide as specified by council inspection team to best match environment and existing local infrastructure
section | Reinforcement
checkpoint | 1.1 - Nominal cover of 40mm cover top and bottom unless noted otherwise
label | METHOD - V
label | REFERENCE - S.D.X6
label | CRITERIA - Check cover requirements as per IFC drawings & concrete specification document.
label | VALUE - {Value}
checkpoint | 1.2 - Size, spacing & location
label | METHOD - V
label | REFERENCE - S.D.X6
label | CRITERIA - X2 layers of SL62 – 40mm top and bottom
label | • Dowel placement as per S.D.X6
label | VALUE - {Value}
checkpoint | 1.3 - Rigidity
label | REFERENCE - S.D.X6
label | CRITERIA - Reinforcement is adequately tied to prevent movement during pouring. Fixing to be as per standard.
label | VALUE - {Value}
checkpoint | 1.4 - Visual check
label | REFERENCE - S.D.X6
label | CRITERIA - Reinforcement as per IFC drawings
label | VALUE - {Value}
section | Concrete Properties
checkpoint | Concrete properties:
textbox | Concrete mix:
textbox | Supplier:
dropdown | Testing required to AS1379 | Yes,No,N/A
textbox | Concrete specification document:
dropdown | Mix Design Approved | Yes,No,N/A
textbox | Approved By:
dropdown | Method of Pour: | Line Pump,Boom Pump,Kibble,Chute,Tremie
section | Final Sign Off
checkpoint | Appia Foreman
textbox | Name:
textbox | Date Completed:
signoff | Signature
checkpoint | Appia Engineer
textbox | Name:
textbox | Date Completed:
signoff | Signature
checkpoint | Client Rep.
textbox | Name:
textbox | Date Completed:
signoff | Signature
checkpoint | Other Party {Company}
textbox | Name:
textbox | Date Completed:
signoff | Signature
section | Post pour
checkpoint | 4.1 - Curing
label | METHOD - V
label | REFERENCE - {Dwg. Number}
label | CRITERIA - Curing carried out as per IFC drawings / concrete specification
label | VALUE - {Value}
checkpoint | 4.2 - Formwork stripped
label | METHOD - V
label | REFERENCE - {Dwg. Number}
label | CRITERIA - Formwork stripped in accordance with specified times on IFC drawings / specifications
label | VALUE - {Value}
checkpoint | 4.3 - Surface defect repair
label | METHOD - V
label | CRITERIA - Repair grout to be higher strength than substrate concrete
label | VALUE - {Value}
checkpoint | 4.4 - All areas are clean from slurry
label | METHOD - V
label | CRITERIA - Surfaces to be cleaned after pour if required
label | VALUE - {Value}