## Sheet1
type | name | values | prefix | postfix | usage count
checklist-flat | Park and Ride - Green Roof Sarnafil Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
checkpoint | Attach TDS for application
checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
checkpoint | Adequate fall in substrate?
label | If any of these checkpoints fail information and required action by builder provided in comments below
checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
checkpoint | Installation of Type 8 profile on upturn?
checkpoint | Adhesive installed to manufacturer's specification?
checkpoint | Record (Photo) batch number and date of manufacture of adhesive
checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
checkpoint | Siphonic drains detailed to manufacturers specification?
checkpoint | Installation of Type 5 profile to junction?
checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
checkpoint | Installation of Dilatec tape detail to existing P-1200 membrane?
checkpoint | Area completed to manufacturer's specification? - photos attached below
checklist-flat | Park and Ride - Busway Sarnafil Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
checkpoint | Attach TDS for application
checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
checkpoint | Adequate fall in substrate?
label | If any of these checkpoints fail information and required action by builder provided in comments below
checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane junctions able to accept Type 5 profile?
checkpoint | Installation of Type 6 profile for junction with Watertite membrane?
checkpoint | Installation of Type 8 profile on upturn?
checkpoint | Adhesive installed to manufacturer's specification?
checkpoint | Record (Photo) batch number and date of manufacture of adhesive
checkpoint | Installation of sheet membrane to floor areas (min. 50mm overlaps)?
checkpoint | Column bases (24) detailed to manufacturers specification?
checkpoint | Installation of Type 5 profile to junction?
checkpoint | Installation of sheet membrane to perimeters, incl. compatible sealant as required (profiles welded)?
checkpoint | Area completed to manufacturer's specification? - photos attached below
checklist-flat | Park and Ride - Watertite Membrane Junction Installation
checkpoint | Scope Description (from Bravada SOW) and item numbers
text | SOW description entered
checkpoint | Attach TDS for application (Download from Simpro)
checkpoint | Substrate washed / cleaned & assessed for surface uniformity (photos attached below)
checkpoint | Substrate temperature is not less than 10*C and no greater then 35*C
checkpoint | Substrate free from pooling or ponding water (Moisture gauge photo attached below)
label | If any of these checkpoints fail information and required action by builder provided in comments below
checkpoint | Saw cuts (15mm deep x 5 mm wide) at Watertite membrane (Watertite side) junctions able to accept Type 5 profile?
checkpoint | Installation of Type 5 profile to junction?
checkpoint | Adhesive installed to manufacturer's specification?
checkpoint | Record (Photo) batch number and date of manufacture of adhesive
checkpoint | Installation of sheet membrane (min. 50mm overlaps) to ?
checkpoint | Area completed to manufacturer's specification? - photos attached below