## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Capping Beams ITP |  |  |  |  | Yes | Capping Beams ITP | 306b077f-ec37-4990-acf7-3ab2a871172e
checkpoint-status |  |  | checkpoint | Drawing & Reference
text | dcb67986-883f-54b9-8ea4-0e3ad079dcc4 |  | textbox | Drawing & Revision Number(s)
text | c79dc813-4d38-518b-929e-3ee188c64c64 |  | textbox | Reference (Use Gridlines / Pile Numbers, etc.)
label | 55464b24-b94e-580c-baa4-4029d51d9e70 |  | note | Surveyor to Check Position of Capping beam
text | d6e8d316-8ef0-5118-9546-7f14a920ac53 |  | textbox | Blinding RL
text | 08f39a1f-1c85-5746-bde0-31876429293a |  | textbox | Top of Capping Beam RL
checkpoint-status |  |  | checkpoint | Reo Placement
text | b2dd85c2-1276-59df-b46a-822014cc1e9c |  | textbox | Pile Reo Length
text | 647c4e82-752a-539a-b0a7-7e864c360a50 |  | textbox | Reo Size/Configuration as per schedule
label | 2f803421-0c64-5d80-819e-3fde6cef0653 |  | note | Cover: 50mm
label | 819ea7a0-3cd7-5e96-86ea-4d92ffd979f2 |  | note | Photos attached
label | e4329f74-392f-5f93-b813-c03703d6795b |  | note | Engineers Inspection - sign off attached
checkpoint-status |  |  | checkpoint | Commencement of pour
label | b2ff64f2-946f-54e8-8ec2-a0960866ba66 |  | note | OK to Pour. Shotcrete methodology attached
checkpoint-status |  |  | checkpoint | Concrete
text | df23c5a2-a85d-5ac7-96f9-a26b42bae74f |  | textbox | Concrete Strength
label | 65ba075f-53ab-5c58-859b-f67a0387dabf |  | note | Concrete dockets/test Docket attached
checkpoint-status |  |  | checkpoint | Signed off / Handed Over
checklist-flat |  |  | checklist | Piling Records ITP |  |  |  |  | Yes | Piling Records ITP | 4a6a3147-952f-421a-ba31-d62b28092ff0
checkpoint-status |  |  | checkpoint | Pile Drilling Sequence
text | 5abcbc6d-ab80-531e-aedd-cfd675249324 |  | textbox | Platform Level (RL m)
text | 48db60e2-2167-588c-9ff3-ea6bb070afea |  | textbox | Diameter (mm)
text | 34d680e8-8d70-575b-8786-0e709643e2e7 |  | textbox | Concrete Grade (MPa)
text | 4abfbf4d-8ba5-5c0c-b6c5-430fef372adc |  | textbox | Drill Depth (m)
text | e6009447-2dd4-5647-a8cc-57a742b3bc44 |  | textbox | Socket Length (m)
text | 1e81b87e-8ac6-5b20-a47a-fd4a65559a53 |  | textbox | Top of Concrete (RL m)
text | 8494ed0f-b878-5150-95b0-c8ae4e001e1b |  | textbox | Concrete Volume (m3)
checkpoint-status |  |  | checkpoint | Reinforcement - Cage
text | af594b56-7f13-5505-9273-fe75e99f0a27 |  | textbox | Top of Cage (RL m)
text | 3846ea79-0638-5d38-ba41-b1e85615b245 |  | textbox | Bars xNyy
text | acd47933-653e-573f-a7af-551e79fd9427 |  | textbox | Spiral Size (mm)
text | 4bd59c79-0107-5c78-8f4e-81ee9c5393e0 |  | textbox | Spiral Pitch (mm)
text | 92b41fa0-ed39-56be-919f-b1d7e21a397c |  | textbox | Length (m)
checkpoint-status |  |  | checkpoint | Reinforcement - Bundled Bars
text | 2c06f8d2-b9e1-5929-83fc-e943c136e0f9 |  | textbox | Bars xNyy
text | 5f73f6d8-e2f6-5946-8a38-f0c274de557a |  | textbox | Length (m)
checkpoint-status |  |  | checkpoint | Final
text | 74dd4368-d0d6-540c-a070-772da8bdfb8f |  | textbox | Verticality (mm / m)
text | 143f86eb-90e7-5475-8ce1-2ee082e96c1d |  | textbox | Offsets (mm / direction)
button | 8f0717ed-01e7-5e96-a51b-d6e6e836b9e3 |  | button | Concrete Test | Yes,No
text | a99ac1c6-e3ee-5579-ab7a-598a07f21782 |  | textbox | Concrete Test Result
checkpoint-status |  |  | checkpoint | Keller Superviser Sign Off / Handover
checkpoint-status |  |  | checkpoint | Delta Group Sign Off
checklist-flat |  |  | checklist | Shotcrete Walls ITP |  |  |  |  | Yes | Shotcrete Walls ITP | 94593d3a-8f73-432a-98ea-04581983e770
checkpoint-status |  |  | checkpoint | Concrete mix design confirmed
checkpoint-status |  |  | checkpoint | Soil cleaned off piles and back of the wall
checkpoint-status |  |  | checkpoint | Reinforcement installed as per drawings and specifications
checkpoint-status |  |  | checkpoint | Reinforcement drilled and epoxied (correct epoxy being used and embedment)
checkpoint-status |  |  | checkpoint | Cover to reinforcement as per specifications
checkpoint-status |  |  | checkpoint | CHS Confirmed as per drawings
text | daef8c68-7013-5fe3-95e0-15bba0440d07 |  | textbox | Thickness
text | 0dcb560e-ba0f-544a-b03a-6ffc65cf4249 |  | textbox | Size Gauge
text | 2759565a-1148-5065-873b-82d297c18fd2 |  | textbox | Length
checkpoint-status |  |  | checkpoint | Water Proofing installed
checkpoint-status |  |  | checkpoint | Engineer inspection completed or photos sent
label | 220a4eab-3a96-577e-b842-e855dd6ef12a |  | note | Engineer sign off attached
checkpoint-status |  |  | checkpoint | Concrete mix design checked upon delivery of concrete
label | 8beebf6b-db9c-5a89-a76a-b54c98187475 |  | note | Delivery docket attached
checkpoint-status |  |  | checkpoint | Wall trowelled, and finish completed as per architectural (or architectural sample)
checkpoint-status |  |  | checkpoint | Slab Starters for B1
checklist-flat |  |  | checklist | Rafts ITP |  |  |  |  | Yes | Rafts ITP | d06754c4-a832-488b-90b5-56f187572967
checkpoint-status |  |  | checkpoint | Drawing & Reference
text | eba9f783-184c-57ff-8e59-437ebffafa53 |  | textbox | Drawing & Revision Number(s)
text | 88fa6943-1fb2-5da5-859e-c5176d1cf06a |  | textbox | Reference (Use Gridlines / Pile Numbers, etc.)
label | 29189566-f81e-549f-b0d6-ff5d2852c7cb |  | note | Surveyor to set out pads and starter positions - Check position
text | 53a4a66f-be5c-5ed7-8ea9-e5a11a42be2c |  | textbox | Top blinding
text | 5cd4fb87-2d09-5301-a744-3da133bcacaa |  | textbox | Top of pad
checkpoint-status |  |  | checkpoint | Reo Placement
text | 2e99e52b-2c39-5f1a-8ddc-d446244791dd |  | textbox | Pile Reo Length
text | 100f8178-6348-56c3-a5ae-07422c921228 |  | textbox | Reo Size/Configuration as per schedule
label | eba544e0-2f65-5c9c-b905-a327ba8c23e2 |  | note | Cover: 50mm
label | b072b188-2f58-5169-bef8-b0c9c43688dc |  | note | Photos attached
label | a34823f3-e22c-5a70-b6ab-f16d3003d39a |  | note | Engineers Inspection - sign off + evidence of close out attached
checkpoint-status |  |  | checkpoint | Commencement of pour
checkpoint-status |  |  | checkpoint | Concrete
text | 32f7ed96-e4ae-5c17-b259-fc1ec7efc834 |  | textbox | Concrete Strength
label | 6121ca96-c026-50a1-8a9d-a922ed1844a8 |  | note | Concrete dockets/test Docket attached
checkpoint-status |  |  | checkpoint | Signed off / Handed Over
checklist-flat |  |  | checklist | Document / Photo Upload Checklist |  |  |  |  | Yes | Document / Photo Upload Checklist | e71abfef-81bb-4373-8f47-f87a9175f957
checkpoint-status |  |  | checkpoint | Photo / Doc Uploaded below
checklist-flat |  |  | checklist | Pad Footing - Crane Base ITP |  |  |  |  | Yes | Pad Footing - Crane Base ITP | f403e2f7-0083-4338-9288-50eaa935dded
checkpoint-status |  |  | checkpoint | Drawing & Reference
text | 1581538e-02a6-5250-9635-be671698822d |  | textbox | Drawing & Revision Number(s)
text | 5243e55a-1f8a-57f7-872e-e163bd45bafb |  | textbox | Reference (Use Gridlines / Pile Numbers, etc.)
label | dccc2a23-3d1c-5483-ac5b-d20eb712e04f |  | note | Surveyor to set out pads and starter positions - Check position
text | 2e50d870-81d5-58bb-8205-2fdd78fc7c92 |  | textbox | Top blinding
text | 8cfc3550-05d9-5399-8594-d8d024c9a7fc |  | textbox | Top of pad
checkpoint-status |  |  | checkpoint | Reo Placement
text | 0a3b47e7-0b11-55f8-93b3-9ad53c82035f |  | textbox | Pile Reo Length
text | b4012c17-c7c0-5809-99c6-dbe8ff5a04df |  | textbox | Reo Size/Configuration as per schedule
label | 33b352f2-10c9-5d93-a8c4-2244c19ea68c |  | note | Cover: 50mm
label | 44cacbd7-0422-589c-84b4-da229d6df334 |  | note | Photos attached
label | 4ac05552-d678-5c85-ae1e-8ca162e61b65 |  | note | Engineers Inspection - sign off + evidence of close out attached
checkpoint-status |  |  | checkpoint | Commencement of pour
checkpoint-status |  |  | checkpoint | Concrete
text | d1498eaa-aece-5c62-9219-00eec5087882 |  | textbox | Concrete Strength
label | 92ab528d-cdef-52ec-af92-6feb96f5f76c |  | note | Concrete dockets/test Docket attached
checkpoint-status |  |  | checkpoint | Signed off / Handed Over