## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | CFA Piles ITP | itp |  |  |  |  | CFA Piles ITP
section | APPROVALS AND OTHER PRELIMINARY REQUIREMENTS
checkpoint | 1.1 - Procedure
label | FREQUENCY - Each
label | RESPONSIBILITY - PM
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Client Approval
label | REQUIRED INSPECTION - H
label | RECORD - Correspondence
holdpoint | HOLD POINT
checkpoint | 1.2 - Current IFC Drawings
label | FREQUENCY - All Site Areas
label | RESPONSIBILITY - PM
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - N/A
label | REQUIRED INSPECTION - H
label | RECORD - Drawing Register
holdpoint | HOLD POINT
checkpoint | 1.3 - Underground Services Location Checklist
label | FREQUENCY - All Site Areas
label | RESPONSIBILITY - PM
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Clear Services at Location
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-036 - Underground Services Location Checklist
holdpoint | HOLD POINT
checkpoint | 1.4 - Working Platform Certification
label | FREQUENCY - All Site Areas
label | RESPONSIBILITY - PM
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Satisfies min plant bearing pressure requirement
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-047 - Signed Working Platform Certificate
holdpoint | HOLD POINT
checkpoint | 1.5 - Plant and equipment check
label | FREQUENCY - Pre-commence
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Completed document
label | REQUIRED INSPECTION - H
label | RECORD - Plant Inspection Record Sheets
holdpoint | HOLD POINT
section | MATERIAL RECEIVING / DOCUMENT INSPECTION
checkpoint | 2.1 - Concrete Testing
label | FREQUENCY - 1 per 50m3 /grade/day
label | RESPONSIBILITY - Pump Operator
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - 28 day strength matches design
label | REQUIRED INSPECTION - W
label | RECORD - KA-FRM-075 - CFA Concrete Record
checkpoint | 2.2 - Concrete Grade and Workability
label | FREQUENCY - Each delivery
label | RESPONSIBILITY - Pump Operator
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Docket records correct grade to match design/ schedule, flowability looks acceptable
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-075 - CFA Concrete Record
holdpoint | HOLD POINT
checkpoint | 2.3 - Steel Delivery Dockets
label | FREQUENCY - Each delivery
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Docket records correct to steel design, fabrication checked as acceptable
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-075 - CFA Concrete Record
holdpoint | HOLD POINT
section | IN-PROCESS RECORDS
checkpoint | 3.1 - Check auger position from pile offset pegs
label | FREQUENCY - Each
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - 0-40mm
label | REQUIRED INSPECTION - S
label | RECORD - KA-FRM-076 - CFA Pile Record
checkpoint | 3.2 - Prime pump line and note pump strokes
label | FREQUENCY - after priming pump
label | RESPONSIBILITY - Pump Operator
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Note
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-075 - CFA Concrete Record
holdpoint | HOLD POINT
checkpoint | 3.3 - Pile Verticality
label | FREQUENCY - Each pile
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - 1:50
label | REQUIRED INSPECTION - S
label | RECORD - KA-FRM-076 - CFA Pile Record
checkpoint | 3.4 - Drill down 1.5 - 3.0m, re-check auger position from pile offset pegs
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - 0-40mm
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-076 - CFA Pile Record
holdpoint | HOLD POINT
checkpoint | 3.5 - Drill to depth record depth and socket length
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Length and socket matches Design/Schedule
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-076 - CFA Pile Record
holdpoint | HOLD POINT
checkpoint | 3.6 - Drill to depth record depth and socket length
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Rig Operator
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Length and socket matches Design/Schedule
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-093 - CFA Rig Operator Daily Record
holdpoint | HOLD POINT
checkpoint | 3.7 - Measure Pump Strokes
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Pump Operator
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - pump strokes accords with thoertical volume
label | REQUIRED INSPECTION - S
label | RECORD - KA-FRM-075 - CFA Concrete Record
checkpoint | 3.8 - Concrete Volumes
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Pump Operator
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - volumes nominally NOT less than 5% of theoretical
label | REQUIRED INSPECTION - S
label | RECORD - KA-FRM-075 - CFA Concrete Record
checkpoint | 3.9 - Concrete Volumes
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Rig Operator
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - volumes nominally NOT less than 5% of theoretical
label | REQUIRED INSPECTION - S
label | RECORD - KA-FRM-093 - CFA Rig Operator Daily Record
checkpoint | 3.10 - Concrete Volumes
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - volumes nominally NOT less than 5% of theoretical
label | REQUIRED INSPECTION - S
label | RECORD - KA-FRM-076 - CFA Pile Record
checkpoint | 3.11 - Reinforcement cage
label | FREQUENCY - Each Pile
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Cage and splice matches design/ Pile Schedule
label | REQUIRED INSPECTION - H
label | RECORD - KA-FRM-076 - CFA Pile Record
holdpoint | HOLD POINT
checkpoint | 3.12 - Pile As Built Data to submit to KF Project Engineer for review
label | FREQUENCY - twice weekly for latest completed piles
label | RESPONSIBILITY - Project Engineer
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - +/-75mm
label | REQUIRED INSPECTION - R
label | RECORD - Pile Schedule
checkpoint | 3.13 - Completion of Daily Site Diary
label | FREQUENCY - Daily
label | RESPONSIBILITY - Supervisor / Foreman
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Completed document
label | REQUIRED INSPECTION - R
label | RECORD - KA-FRM-053 - Daily Site Diary
checkpoint | 3.14 - PDA Testing
label | FREQUENCY - Per specification
label | RESPONSIBILITY - Project Engineer
label | CONTROLLING DOCUMENT - KA-PRO-057 - High Strain Dynamic Pile Test PDA
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Design load criteria met
label | REQUIRED INSPECTION - R
label | RECORD - KA-FRM-127 - Dynamic Load Test Field Data Sheet
checkpoint | 3.15 - Integrity Testing
label | FREQUENCY - Per specification
label | RESPONSIBILITY - Project Engineer
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Pile free of defects
label | REQUIRED INSPECTION - R
label | RECORD - Integrity Test Report
section | COMPLETION AND HANDOVER
checkpoint | 5.1 - Pile Records to client
label | FREQUENCY - Progressively
label | RESPONSIBILITY - Project Engineer
label | CONTROLLING DOCUMENT - KA-PRO-102 - CFA Piles
label | ACCEPTANCE CRITERIA (SPECIFICATION REQUIREMENT) - Piles constructed to design
label | REQUIRED INSPECTION - R
label | RECORD - KA-FRM-076 - CFA Pile Record