## ITP-115 Mechanical
QUALITY MANAGEMENT SYSTEM
INSPECTION AND TEST PLAN
PROJECT: |  |  | Bourke Street Zetland | Inspector |  | Authorised by Client: | [25 empty] | Prepared by: Daniel Wade
BUILDER: |  |  | Binah | X: Inspection | Pre-Con | Revision: |  | A | Ref :
ITP No. |  |  | ITP-J282 | H: Hold Point | Rough-in | Date:
Construction Process: |  |  | MECH | W: Witness Point | Fit-off | Supervisor Name |  |  | Daniel Wade
Criteria | Pre-Con | Pre-Con | Pre-Con | Pre-Con |  | Rough-in |  | Rough-in | Rough-in | Rough-in | Rough-in | Rough-in |  |  | Rough-in | Rough-in |  | Fit-off | Fit-off | Fit-off | Fit-off | Fit-off | Fit-off |  | Fit-off | Fit-off | Fit-off | Fit-off
Apt No | Unit No. | Safety Induction | Drawings Approved | Site Inspection | Hold Point, Sup Sign & Date | Check Material | Install FCUs | Install Fans | Install Pipework | Install Cabling, Controls Etc | Install Flexible Ducts | Install Drains and test | Fire Boxes/Collars/Dampers Installed, Photos Taken | Install Flat Pack Duct | Access Panels Marked | Pressure Testing | Hold Point, Sup Sign & Date | Check Pressure | Install Condensers | Terminate Drain | Terminate Power and Controller | Install Grilles | Pressure test | Vacuum system | Access To Equipment Checked | Commission | Model No | Serial No. | Subcontractor Sign-off Supervisor/Date | Head Contract Sign-off | Client Sign-off | Notes
Builder/Client Inspection Points | × | × | × | × | [11 empty] | ×
Ground Floor
G.01 | AC-G.01-L | [25 empty] | MMD-UP0181SPHY-E
| AC-G.01-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-G.01 | [25 empty] | MCY-MHP0404HS-A
G.02 | AC-G.02-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.02-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-G.02 | [25 empty] | MCY-MHP0404HS-A
G.03 | AC-G.03-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.03-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-G.03 | [25 empty] | MCY-MHP0404HS-A
G.04 | AC-G.04-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.04-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-G.04 | [25 empty] | MCY-MHP0404HS-A
G.05 | AC-G.05-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.05-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-G.05 | [25 empty] | MCY-MHP0404HS-A
G.06 | AC-G.06-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.06-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-G.06 | [25 empty] | MCY-MHP0404HS-A
G.07 | AC-G.07-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.07-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-G.07 | [25 empty] | MCY-MHP0404HS-A
G.08 | AC-G.08-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.08-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-G.08 | [25 empty] | MCY-MHP0404HS-A
G.09 | AC-G.09-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.09-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-G.09 | [25 empty] | MCY-MHP0404HS-A
G.10 | AC-G.10-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.10-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-G.10 | [25 empty] | MCY-MHP0404HS-A
G.11 | AC-G.11-L | [25 empty] | MMD-UP0181SPHY-E
| AC-G.11-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-G.11 | [25 empty] | MCY-MHP0404HS-A
G.12 | AC-G.12-L | [25 empty] | MMD-UP0181SPHY-E
| AC-G.12-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-G.12 | [25 empty] | MCY-MHP0404HS-A
G.13 | AC-G.13-L | [25 empty] | MMD-UP0181SPHY-E
| AC-G.13-B1 | [25 empty] | MMD-UP0091SPHY-E
| CU-G.13 | [25 empty] | MCY-MHP0404HS-A
G.14 | AC-G.14-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.14-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-G.14 | [25 empty] | MCY-MHP0404HS-A
G.15 | AC-G.15-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.15-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-G.15 | [25 empty] | MCY-MHP0404HS-A
G.16 | AC-G.16-L | [25 empty] | MMD-UP0241SPHY-E
| AC-G.16-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-G.16 | [25 empty] | MCY-MHP0404HS-A
G.17 | AC-G.17-L | [25 empty] | MMD-UP0181SPHY-E
| AC-G.17-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-G.17 | [25 empty] | MCY-MHP0404HS-A
G.02 | FCU LIVING | [25 empty] | K 150 EC SILEO
| FCU MASTER | [25 empty] | BEC150HP
Level 1
1.01 | AC-1.01-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.01-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.01 | [25 empty] | MCY-MHP0404HS-A
1.02 | AC-1.02-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.02-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-1.02 | [25 empty] | MCY-MHP0404HS-A
1.03 | AC-1.03-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.03-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-1.03 | [25 empty] | MCY-MHP0404HS-A
1.04 | AC-1.04-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.04-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.04 | [25 empty] | MCY-MHP0404HS-A
1.05 | AC-1.05-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.05-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.05 | [25 empty] | MCY-MHP0404HS-A
1.06 | AC-1.06-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.06-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-1.06 | [25 empty] | MCY-MHP0404HS-A
1.07 | AC-1.07-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.07-B1 | [25 empty] | MMD-UP0151SPHY-E
| CU-1.07 | [25 empty] | MCY-MHP0404HS-A
1.08 | AC-1.08-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.08-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.08 | [25 empty] | MCY-MHP0404HS-A
1.09 | AC-1.09-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.09-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.09 | [25 empty] | MCY-MHP0404HS-A
1.1 | AC-1.10-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.10-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.10 | [25 empty] | MCY-MHP0404HS-A
1.11 | AC-1.11-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.11-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-1.11 | [25 empty] | MCY-MHP0404HS-A
1.12 | AC-1.12-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.12-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-1.12 | [25 empty] | MCY-MHP0404HS-A
1.13 | AC-1.13-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.13-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-1.13 | [25 empty] | MCY-MHP0404HS-A
1.14 | AC-1.14-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.14-B1 | [25 empty] | MMD-UP0091SPHY-E
| CU-1.14 | [25 empty] | MCY-MHP0404HS-A
1.15 | AC-1.15-L1 | [25 empty] | MMD-UP0091SPHY-E
| AC-1.15-L2 | [25 empty] | MMD-UP0091SPHY-E
| AC-1.15-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.15 | [25 empty] | MCY-MHP0404HS-A
1.16 | AC-1.16-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.16-B1 | [25 empty] | MMD-UP0151SPHY-E
| CU-1.16 | [25 empty] | MCY-MHP0404HS-A
1.17 | AC-1.17-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.17-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-1.17 | [25 empty] | MCY-MHP0404HS-A
1.18 | AC-1.18-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.18-B1 | [25 empty] | MMD-UP0071SPHY-E
| CU-1.18 | [25 empty] | MCY-MHP0404HS-A
1.19 | AC-1.19-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.19-B1 | [25 empty] | MMD-UP0091SPHY-E
| CU-1.19 | [25 empty] | MCY-MHP0404HS-A
1.2 | AC-1.20-L | [25 empty] | MMD-UP0241SPHY-E
| AC-1.20-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-1.20 | [25 empty] | MCY-MHP0404HS-A
1.21 | AC-1.21-L | [25 empty] | MMD-UP0271SPHY-E
| AC-1.21-B1 | [25 empty] | MMD-UP0091SPHY-E
| CU-1.21 | [25 empty] | MCY-MHP0404HS-A
1.22 | AC-1.22-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.22-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-1.22 | [25 empty] | MCY-MHP0404HS-A
1.23 | AC-1.23-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.23-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-1.23 | [25 empty] | MCY-MHP0404HS-A
1.24 | AC-1.24-L | [25 empty] | MMD-UP0181SPHY-E
| AC-1.24-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-1.24 | [25 empty] | MCY-MHP0404HS-A
Level 2
2.01 | AC-2.01-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.01-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.01 | [25 empty] | MCY-MHP0404HS-A
2.02 | AC-2.02-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.02-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-2.02 | [25 empty] | MCY-MHP0404HS-A
2.03 | AC-2.03-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.03-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-2.03 | [25 empty] | MCY-MHP0404HS-A
2.04 | AC-2.04-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.04-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.04 | [25 empty] | MCY-MHP0404HS-A
2.05 | AC-2.05-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.05-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.05 | [25 empty] | MCY-MHP0404HS-A
2.06 | AC-2.06-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.06-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-2.06 | [25 empty] | MCY-MHP0404HS-A
2.07 | AC-2.07-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.07-B1 | [25 empty] | MMD-UP0151SPHY-E
| CU-2.07 | [25 empty] | MCY-MHP0404HS-A
2.08 | AC-2.08-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.08-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.08 | [25 empty] | MCY-MHP0404HS-A
2.09 | AC-2.09-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.09-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.09 | [25 empty] | MCY-MHP0404HS-A
2.1 | AC-2.10-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.10-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.10 | [25 empty] | MCY-MHP0404HS-A
2.11 | AC-2.11-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.11-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.11 | [25 empty] | MCY-MHP0404HS-A
2.12 | AC-2.12-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.12-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.12 | [25 empty] | MCY-MHP0404HS-A
2.13 | AC-2.13-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.13-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.13 | [25 empty] | MCY-MHP0404HS-A
2.14 | AC-2.14-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.14-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.14 | [25 empty] | MCY-MHP0404HS-A
2.15 | AC-2.15-L1 | [25 empty] | MMD-UP0091SPHY-E
| AC-2.15-L2 | [25 empty] | MMD-UP0091SPHY-E
| AC-2.15-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.15 | [25 empty] | MCY-MHP0404HS-A
2.16 | AC-2.16-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.16-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.16 | [25 empty] | MCY-MHP0404HS-A
2.17 | AC-2.17-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.17-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.17 | [25 empty] | MCY-MHP0404HS-A
2.18 | AC-2.18-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.18-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.18 | [25 empty] | MCY-MHP0404HS-A
2.19 | AC-2.19-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.19-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.19 | [25 empty] | MCY-MHP0404HS-A
2.2 | AC-2.20-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.20-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.20 | [25 empty] | MCY-MHP0404HS-A
2.21 | AC-2.21-L | [25 empty] | MMD-UP0241SPHY-E
| AC-2.21-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-2.21 | [25 empty] | MCY-MHP0404HS-A
2.22 | AC-2.22-L | [25 empty] | MMD-UP0271SPHY-E
| AC-2.22-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.22 | [25 empty] | MCY-MHP0404HS-A
2.23 | AC-2.23-L | [25 empty] | MMD-UP0151SPHY-E
| AC-2.23-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-2.23 | [25 empty] | MCY-MHP0404HS-A
2.24 | AC-2.24-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.24-B1 | [25 empty] | MMD-UP0121SPHY-E
| CU-2.24 | [25 empty] | MCY-MHP0404HS-A
2.25 | AC-2.25-L | [25 empty] | MMD-UP0181SPHY-E
| AC-2.25-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-2.25 | [25 empty] | MCY-MHP0404HS-A
Level 3
Level 2
3.01 | AC-3.01-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.01-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.01 | [25 empty] | MCY-MHP0404HS-A
3.02 | AC-3.02-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.02-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.02 | [25 empty] | MCY-MHP0404HS-A
3.03 | AC-3.03-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.03-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.03 | [25 empty] | MCY-MHP0404HS-A
3.04 | AC-3.04-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.04-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.04 | [25 empty] | MCY-MHP0404HS-A
3.05 | AC-3.05-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.05-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.05 | [25 empty] | MCY-MHP0404HS-A
3.06 | AC-3.06-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.06-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.06 | [25 empty] | MCY-MHP0404HS-A
3.07 | AC-3.07-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.07-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.07 | [25 empty] | MCY-MHP0404HS-A
3.08 | AC-3.08-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.08-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.08 | [25 empty] | MCY-MHP0404HS-A
3.09 | AC-3.09-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.09-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.09 | [25 empty] | MCY-MHP0404HS-A
3.1 | AC-3.10-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.10-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.10 | [25 empty] | MCY-MHP0404HS-A
3.11 | AC-3.11-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.11-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.11 | [25 empty] | MCY-MHP0404HS-A
3.12 | AC-3.12-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.12-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.12 | [25 empty] | MCY-MHP0404HS-A
3.13 | AC-3.13-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.13-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.13 | [25 empty] | MCY-MHP0404HS-A
3.14 | AC-3.14-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.14-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.14 | [25 empty] | MCY-MHP0404HS-A
3.15 | AC-3.15-L1 | [25 empty] | MMD-UP0091SPHY-E
| AC-3.15-L2 | [25 empty] | MMD-UP0091SPHY-E
| AC-3.15-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.15 | [25 empty] | MCY-MHP0404HS-A
3.16 | AC-3.16-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.16-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.16 | [25 empty] | MCY-MHP0404HS-A
3.17 | AC-3.17-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.17-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.17 | [25 empty] | MCY-MHP0404HS-A
3.18 | AC-3.18-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.18-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.18 | [25 empty] | MCY-MHP0404HS-A
3.19 | AC-3.19-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.19-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.19 | [25 empty] | MCY-MHP0404HS-A
3.2 | AC-3.20-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.20-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.20 | [25 empty] | MCY-MHP0404HS-A
3.21 | AC-3.21-L | [25 empty] | MMD-UP0241SPHY-E
| AC-3.21-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.21 | [25 empty] | MCY-MHP0404HS-A
3.22 | AC-3.22-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.22-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.22 | [25 empty] | MCY-MHP0404HS-A
3.23 | AC-3.23-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.23-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.23 | [25 empty] | MCY-MHP0404HS-A
3.24 | AC-3.24-L | [25 empty] | MMD-UP0181SPHY-E
| AC-3.24-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-3.24 | [25 empty] | MCY-MHP0404HS-A
Level 4
4.01 | AC-4.01-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.01-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.01 | [25 empty] | MCY-MHP0404HS-A
4.02 | AC-4.02-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.02-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.02 | [25 empty] | MCY-MHP0404HS-A
4.03 | AC-4.03-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.03-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.03 | [25 empty] | MCY-MHP0404HS-A
4.04 | AC-4.04-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.04-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.04 | [25 empty] | MCY-MHP0404HS-A
4.05 | AC-4.05-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.05-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.05 | [25 empty] | MCY-MHP0404HS-A
4.06 | AC-4.06-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.06-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.06 | [25 empty] | MCY-MHP0404HS-A
4.07 | AC-4.07-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.07-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.07 | [25 empty] | MCY-MHP0404HS-A
4.08 | AC-4.08-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.08-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.08 | [25 empty] | MCY-MHP0404HS-A
4.09 | AC-4.09-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.09-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.09 | [25 empty] | MCY-MHP0404HS-A
4.1 | AC-4.10-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.10-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.10 | [25 empty] | MCY-MHP0404HS-A
4.11 | AC-4.11-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.11-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.11 | [25 empty] | MCY-MHP0404HS-A
4.12 | AC-4.12-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.12-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.12 | [25 empty] | MCY-MHP0404HS-A
4.13 | AC-4.13-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.13-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.13 | [25 empty] | MCY-MHP0404HS-A
4.14 | AC-4.14-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.14-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.14 | [25 empty] | MCY-MHP0404HS-A
4.15 | AC-4.15-L1 | [25 empty] | MMD-UP0091SPHY-E
| AC-4.15-L2 | [25 empty] | MMD-UP0091SPHY-E
| AC-4.15-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.15 | [25 empty] | MCY-MHP0404HS-A
4.16 | AC-4.16-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.16-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.16 | [25 empty] | MCY-MHP0404HS-A
4.17 | AC-4.17-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.17-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.17 | [25 empty] | MCY-MHP0404HS-A
4.18 | AC-4.18-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.18-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.18 | [25 empty] | MCY-MHP0404HS-A
4.19 | AC-4.19-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.19-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.19 | [25 empty] | MCY-MHP0404HS-A
4.2 | AC-4.20-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.20-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.20 | [25 empty] | MCY-MHP0404HS-A
4.21 | AC-4.21-L | [25 empty] | MMD-UP0241SPHY-E
| AC-4.21-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.21 | [25 empty] | MCY-MHP0404HS-A
4.22 | AC-4.22-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.22-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.22 | [25 empty] | MCY-MHP0404HS-A
4.23 | AC-4.23-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.23-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.23 | [25 empty] | MCY-MHP0404HS-A
4.24 | AC-4.24-L | [25 empty] | MMD-UP0181SPHY-E
| AC-4.24-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-4.24 | [25 empty] | MCY-MHP0404HS-A
Level 5
5.01 | AC-5.01-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.01-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.01 | [25 empty] | MCY-MHP0404HS-A
5.02 | AC-5.02-L | [25 empty] | MMD-UP0301BHP-E
| AC-5.02-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.02 | [25 empty] | MCY-MHP0404HS-A
5.03 | AC-5.03-L | [25 empty] | MMD-UP0271BHP-E
| AC-5.03-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.03 | [25 empty] | MCY-MHP0404HS-A
5.04 | AC-5.04-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.04-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.04 | [25 empty] | MCY-MHP0404HS-A
5.05 | AC-5.05-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.05-B1 | [25 empty] | MMD-UP0151SPHY-E
| CU-5.05 | [25 empty] | MCY-MHP0404HS-A
5.06 | AC-5.06-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.06-B1 | [25 empty] | MMD-UP0151SPHY-E
| CU-5.06 | [25 empty] | MCY-MHP0404HS-A
5.07 | AC-5.07-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.07-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.07 | [25 empty] | MCY-MHP0404HS-A
5.08 | AC-5.08-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.08-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.08 | [25 empty] | MCY-MHP0404HS-A
5.09 | AC-5.09-L | [25 empty] | MMD-UP0271BHP-E
| AC-5.09-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.09 | [25 empty] | MCY-MHP0404HS-A
5.1 | AC-5.10-L | [25 empty] | MMD-UP0361BHP-E
| AC-5.10-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.10 | [25 empty] | MCY-MHP0404HS-A
5.11 | AC-5.11-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.11-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.11 | [25 empty] | MCY-MHP0404HS-A
5.12 | AC-5.12-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.12-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.12 | [25 empty] | MCY-MHP0404HS-A
5.13 | AC-5.13-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.13-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.13 | [25 empty] | MCY-MHP0404HS-A
5.14 | AC-5.14-L1 | [25 empty] | MMD-UP0121SPHY-E
| AC-5.14-L2 | [25 empty] | MMD-UP0121SPHY-E
| AC-5.14-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.14 | [25 empty] | MCY-MHP0404HS-A
5.15 | AC-5.15-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.15-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.15 | [25 empty] | MCY-MHP0404HS-A
5.16 | AC-5.16-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.16-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.16 | [25 empty] | MCY-MHP0404HS-A
5.17 | AC-5.17-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.17-B1 | [25 empty] | MMD-UP0091SPHY-E
| CU-5.17 | [25 empty] | MCY-MHP0404HS-A
5.18 | AC-5.18-L | [25 empty] | MMD-UP0181SPHY-E
| AC-5.18-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.18 | [25 empty] | MCY-MHP0404HS-A
5.19 | AC-5.19-L | [25 empty] | MMD-UP0301BHP-E
| AC-5.19-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.19 | [25 empty] | MCY-MHP0404HS-A
5.2 | AC-5.20-L | [25 empty] | MMD-UP0361BHP-E
| AC-5.20-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.20 | [25 empty] | MCY-MHP0504HS-A
5.21 | AC-5.21-L | [25 empty] | MMD-UP0241SPHY-E
| AC-5.21-B1 | [25 empty] | MMD-UP0051SPHY-E
| CU-5.21 | [25 empty] | MCY-MHP0404HS-A

## Checklist ITP-115 Mechanical
QUALITY MANAGEMENT SYSTEM
INSPECTION and TEST PLAN - CHECKLIST
MECH
Contract: | Bourke Street Zetland | Lot No.: |  |  |  | Lot Opened:
Client: | Binah | Location: |  |  |  | Lot Closed:
Checklist Ref.: | ITP-J282 |  |  |  |  | Signed (HB):
Comments: |  | (Delays/Disruption,Improvements,Other) |  |  |  | No. of Pages: |  | 1
No. | Process | Spec/Std/Dwg | Acceptance Criteria | Pass | Fail | CAR Ref: | Initial(ITP) | Date
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF!
Note: Ensure all Test Certificates are attached to the ITP