## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
d755d53e-bd0e-4f0d-a69e-25918f5933a7 | checklist | ITP - Route 377 Bus Stop Extension - Enabling Works - Footpath, Kerb and channel | itp | ITP - Enabling Works - Footpath, Kerb and channel |  | 65af7f3e-60ea-4298-af8c-d6196f89a02b
bb7db6c1-1020-4ae9-8078-84fc9051eb8f | section | Site Set Out
daf0537d-5c6e-401a-b2bb-a5f17b051f4a | checkpoint | 1 - Site Set out
12c69baf-75dc-57a9-8dc3-c2acb08c7c7e | note | VERIFICATION ACTIVITY: Surveyor
016f3409-0b58-50c7-b518-c575713b1b8f | note | METHODS OR REFERENCE: Surveyor
c4052a76-4228-5a18-86dc-26c7cdef28b0 | note | FREQUENCY: Every Site
8e4697ed-be8c-5d29-8bf7-b4b16909c286 | note | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers.
5b94c2ef-8ad2-559d-bb50-4b87329d5c61 | note | HOLD POINT: Mandatory HOLD POINT -
a352f017-5675-5c59-9718-038675f47a71 | note | RECORDS: Onsite records/photos
bece4d45-408c-5561-894a-ffe6bf0563d1 | note | ONSITE RESPONSIBILITY: Site Engineer
db018d99-0db7-4b88-88e9-898737d404a0 | signoff | AUTHORITY HOLDPOINT
068a17f6-a756-4f54-9b3d-0c4124dabb52 | section | Materials
cd32164f-54d5-44b1-b7cf-4b96ef657307 | checkpoint | 2 - Kassel Kerb & Channel
ed862d3d-0720-55e2-8bb7-f952fd7f7d07 | note | VERIFICATION ACTIVITY: QA FORM
8d1c4c8f-8e16-56fe-8085-d51e514e0ee4 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0030 &KC0031
66bc20df-70e8-5f20-af22-b7e11a6d7b48 | note | FREQUENCY: Every Site
f96610ea-d6b7-5df3-9fe0-813b65cd888c | note | ACCEPTANCE CRITERIA: Kassel kerb and channel including 1m transitions at both ends as per standard.
d90ce978-906a-5a1b-aba0-3a3426f841e9 | note | ○ Half channel at 3% cross fall.
9a9db1d6-c9ef-5092-9025-3567d5494d42 | note | HOLD POINT: Inprocess Inspection
3782c374-50af-52f8-b7fd-b5bf9c7b784b | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
9681a9fe-6ba6-5e3e-b1bb-39148f369d4d | note | ONSITE RESPONSIBILITY: Site Engineer
1181ce1d-4efa-44eb-aa85-6adb10531d14 | checkpoint | 2.1 - Bedding
e14139eb-2ffd-5803-ac02-937ddc14634c | note | VERIFICATION ACTIVITY: QA Form
7dbc6191-e28a-57ed-beb2-e2421093f23d | note | METHODS OR REFERENCE: TDM Technical Standard - KC0002
ea8f8ba4-f4f4-59f3-9672-a31b3907334c | note | FREQUENCY: Every Site
20521db6-18b3-58b7-96ca-ce24db048af4 | note | ACCEPTANCE CRITERIA: GAP65 subbase in roads (CBR>5)
fb7224ad-f32f-560b-9f13-a9989ee65678 | note | ○ Concrete subbase must be 20MPa
b9b0dbc7-e91b-59de-ada6-abde320b261b | note | HOLD POINT: Inprocess Inspection
831e8a6a-9539-5926-908f-f34c4c536465 | note | RECORDS: FH concrete QA sheet, photos. Concrete Plant Docket
c7f732cc-6494-580a-9cb5-89b5aa6c9a0a | note | ONSITE RESPONSIBILITY:
ae90533e-d8c2-433e-ab33-db749767bc3a | checkpoint | 3 - Channel Level
d00cfe0b-0ce4-5c13-87e3-7b9c4724128a | note | VERIFICATION ACTIVITY: QA FORM
e658f375-406c-5976-a72b-b9589c6be0c8 | note | METHODS OR REFERENCE: TDM Technical Standards - KC0001
2587bdc5-e3be-5eaa-aedd-8978af6284a6 | note | FREQUENCY: Every Site
1d6f581c-c395-59db-adf4-33dc38ca6724 | note | ACCEPTANCE CRITERIA: Channels must be laid to flow water in the direction of the nearest cesspit in a manner such that no water ponds and match existing road level
d2754491-f297-5f01-a85e-40fb97ddd8c2 | note | HOLD POINT: Inprocess Inspection
5429eaca-0ba4-5a61-95a9-5db6bb08d985 | note | RECORDS: FH concrete QA sheet, Photos
2ebc91bf-dfe7-512e-a464-ab4ef96c8e83 | note | ONSITE RESPONSIBILITY: Site Engineer
66928d95-a144-4b72-8c9a-5bfa75a9e82e | section | CIVIL WORKS
9ba35c1c-d3f5-42cd-b684-a45de4a2db58 | checkpoint | 4 - Concrete Footpaths / Pram Crossing
b9ae362c-b088-5051-bdd2-df0ea43cf588 | note | VERIFICATION ACTIVITY: QA FORM
bf0df385-16c8-5cf0-a0c1-5641a08fab59 | note | METHODS OR REFERENCE: TDM Technical Standards - FP0001
20ef3cf5-1c72-5158-9fb8-9759a0ece256 | note | FREQUENCY: 10m Intervals
83513b49-1170-589d-aed3-164f994f366f | note | ACCEPTANCE CRITERIA: Basecourse - 100mm min. thickness GAP40
9e57c9d4-1f09-5556-b121-29347248ef88 | note | ○ Clegg CIV > 12
7b9f1187-d04d-5432-8443-c68732a9cc60 | note | ○ Surfacing - Concrete 100mm and 20 MPa @ 28 days. 4kg/m3 blackoxide with broom finish
71d07b76-2072-5658-8183-a1f59f66e2e4 | note | ○ Pram crossing
29d7eb14-ac8a-54c8-aebe-bdf005fe0ad7 | note | ○ MAX gradient to be 1:12
cc9ca11d-d132-5152-96f3-814707460dc7 | note | ○ 4kg/m3 blackoxide with broom finish
dc0fd77e-ba07-5473-97e0-375d054c4b1c | note | HOLD POINT: Inprocess Inspection
30c1e0d6-577e-5c25-9089-c172c9c7e5ad | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
0fa3237e-49be-5e06-8128-17359420122a | note | ONSITE RESPONSIBILITY: Site Engineer
865b5169-5a6e-47ab-8ea1-738c6281a15f | checkpoint | 5 - Tactile Pavers (1)
fb4208f6-c06e-593b-9678-77626af5b064 | note | VERIFICATION ACTIVITY: Visual
98d6ea7a-e733-5917-9607-866b53f161ed | note | METHODS OR REFERENCE: TDM Technical Standards - FP0006 (Pram Crossing)
1095f805-6e86-5bd2-abb3-0940b41e5309 | note | ○ TDM Technical Standards - FP0010 (Footpath)
1b2312d0-8aaf-5471-807a-3fa9da435ccc | note | ○ TDM Technical Standards - IS0002 (Traffic Island Pavers)
7abda895-43af-5d6f-ba54-6c2ebf16593d | note | FREQUENCY: Every Site
dcf238a8-aec5-5c31-8448-8411ed4b6721 | note | ACCEPTANCE CRITERIA: Warning TGSI tiles should have 150mm concrete slab underneath
ac22b8f3-4346-5d7e-a324-12751afbb597 | note | ○ Must comply to TDM standard
3e18e791-f607-5700-bbee-67df8ade2936 | note | ○ FP0006 &FP0010
a2de8245-d3fe-5c76-9953-89b99385f9c5 | note | ○ Traffic Island pavers must comply to TDM standard - IS0002
3042951e-bbb6-5943-8797-3fe0fb8bfff6 | note | HOLD POINT: Inprocess Inspection, Measurement
3a0e9cd7-201a-55a7-87d7-61ffa530e127 | note | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
9059ae63-8fc2-5f11-ae33-5cfdd6e82bf3 | note | ONSITE RESPONSIBILITY: Site Engineer
75a998d8-2c18-4fc4-bd89-fa4c81ebf405 | checkpoint | 5 - Tactile Pavers (2)
c6d9f4e7-f19d-516a-91a9-eb8422b04760 | note | VERIFICATION ACTIVITY: Visual
ee3df88f-7e81-5265-b6b6-6c209d69ea74 | note | METHODS OR REFERENCE: NZTA RTS Guidelines for facilities for blind and vision impared pedestrians
3e5dbe76-8985-5ef1-96d8-a0b9de7d2712 | note | ○ AS/NZS 1428.4:2009 DESIGN FOR ACCESS AND MOBILITY
e1a5a753-e1a0-533d-8f4e-c5ca2700d36b | note | FREQUENCY: Every Site
f32035af-5904-5cec-a0ef-4c36d5f08a3a | note | ACCEPTANCE CRITERIA: Tactile to be yellow concrete paver slab type. Tactile indicators shall be aligned such as warning tiles are perpendicular to the line of crossing.
ef5c0920-703a-5bb1-8b8f-f0cafbe08e08 | note | HOLD POINT: Inprocess Inspection
95b39ef1-127d-5f01-b552-c0ca1ab2b8a8 | note | RECORDS: Photos
6ecf5294-9da9-563f-9c6d-a8fd8e6fedd1 | note | ONSITE RESPONSIBILITY: Site Engineer
5337fdc8-ebf2-4fd9-bcd6-1495ebb12ecf | checkpoint | 6 - Grass Berms
9d3eb810-f5f3-5111-a8d9-5266b9598ca9 | note | VERIFICATION ACTIVITY: Visual
86ca29ac-3c4c-5e40-b281-be55f950ddba | note | METHODS OR REFERENCE: ATCOP Section 12 Footpaths and Pedestrian Facilities
0111f1c5-d40a-57e1-8ef7-8b2d5637196d | note | FREQUENCY: Every Site
cfeb8c4a-e0a5-5130-9621-f3fcd994884d | note | ACCEPTANCE CRITERIA: 100mm thick layer of compacted approved quality topsoil, free of weeds and stones.
58e02296-0bf3-5ab7-ae78-5df7beaa04f8 | note | HOLD POINT: Inprocess Inspection
b596a681-235d-5b4b-806e-d482375bada7 | note | RECORDS: Photos
53cfa193-6ccb-5448-a3a1-dacf355ef3f8 | note | ONSITE RESPONSIBILITY: Site Engineer
1195d1a6-2704-4016-bc7d-9cc4c728dc0d | section | 6 - As Built
dd6f06d4-031c-429c-b898-35088537465b | checkpoint | 7 - As built information
b297b1eb-d04f-5a8e-a245-d5a4b4044559 | note | VERIFICATION ACTIVITY: RAMM DATA SHEET
be232a8a-21c2-5154-8d60-09681f91df6c | note | METHODS OR REFERENCE:
30ec86ac-8cd8-567f-b1b0-de7e11bfc29a | note | FREQUENCY: Every Site
003b066e-5a01-58bd-aba1-709047b35ace | note | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
bdff6e2f-8813-572a-b457-403530001650 | note | HOLD POINT: In Process Inspection
609f4f6e-35f1-5ee2-bdcc-60a29d4cbfff | note | RECORDS: Asbuilt records
fb4cf7c2-42cc-5e7b-823d-07c7848e2dc6 | note | ONSITE RESPONSIBILITY: Supervisor and Engineer
d25724f1-c67b-4c0d-b806-f4a7d045350b | section | APPROVALS
24c00799-26c4-4719-93bf-68cac854095d | checkpoint | ITP Approval
1af75951-9d92-522e-a8e6-ee0062ef5093 | note | Prepared By: Nithin Thomas
abeb7a1c-6ae1-53ec-864e-98ec2d324bfe | note | Approving Delegate: Daniel Tat